CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
# This summary sheet will be published on GOV.UK. It should be limited to 2-4 pages and be written for a public audience that may not be familiar with the language of programme management and CSSF in particular.
Programme Title	India Cyber Programme
Country and Region	India; UK
Programme ID	C-CYB-0005	IATI Unique ID	CSSF-14-000002
Start date	April- 2023	End date	March 2024
HMG Partners / (Lead department in bold)	• Government of India (GoI): Ministry of External Affairs, National Security Council Secretariat, Ministry of Home Civil Society Organisations and NGOs. / • UK Government: FCDO, NCSC, CO, HO, DSIT, DBT, NCA, NHS
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	N/A	N/A	N/A
Non-ODA	£7.3m	£3.1m	£3,012,342
Total	£7.3m	£3.1m	£3,012,342

## Outputs
Output statements	Individual Output Rating
Improved operational standard procedures and manuals for central and regional police investigation agencies	4
Training for LEA Official and Senior Officials on new standard procedures and Manuals	4
Accessible state level cyber crime reporting portal (for women and children)	1
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
LEA labs’ operating model, procedures and ways of working are enhanced through a commitment to adopt a standard approach and methodology while conducting cyber crime investigations.
LEA officials in targeted states follow standardised procedures when conducting digital investigations, reducing the time taken to conduct specific cyber crime investigation techniques
Updated state level cyber crime reporting portals are more user friendly and accessible for target groups
Outcome Assessment	Overall, the ICP programme achieved a A+ rating with 4 score even though some of the output were not completed, It is because, significant milestones were achieved in fostering bilateral cyber security collaborations, enhancing police training, supporting sector-specific initiatives, and expanding state and community-level engagement. These accomplishments have set the stage for sustained international cooperation and capacity building in the cyber domain.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Amber

## Summary of Programme Performance
Year	2023/24
	Output	Outcome
Programme Rating	4	Green
Risk Rating	Amber
Notes: Output/Outcome score A

## What Support Did the UK Provide in FY 23/24?
UK has committed £3.2M towards the ISF India Cyber Programme designed as providing catalytic and agile interventions, trialling and testing the ground for potentially larger-scale government and industry collaboration on cyber security in future.
## Key Results for FY 23/24
- International Report on Cyber Capacity: In September 2023, a comprehensive report was produced to assess the UK implementer community’s perspective on international cyber capacity, setting a clear foundation for engagement and collaboration in the next FY of the ICP.
- NCA Engagement for UK Incident Management: The project advanced UK cyber incident categorisation and resource allocation through a strategic meeting with the National Crime Agency and Indian authorities in November 2023. This engagement strengthened UK-wide coordination in cyber incident response.
- India-UK Forensic Sciences and Cyber Security Conference: In December 2023, a major bilateral conference brought over 100 experts from India and the UK together, advancing dialogue in digital forensics, AI, cryptography, and cyber psychology. This event facilitated key cross-country learning and collaboration.
- MoU Signing with Gujarat: A Memorandum of Understanding was signed with Gujarat in January 2024, symbolizing a significant collaboration milestone and momentum in cyber security endeavours between the UK and India.
- Collaborations with Gujarat LEA: Strengthened ties between the UK and Gujarat law enforcement agencies (LEA) from the MoU resulted in meaningful police collaborations and capacity building of LEA staff.
- Financial Cybercrime Report in India: A situational analysis report produced in February 2024 provided insights into financial cybercrime in India, guiding future awareness and skills development initiatives.
- Healthcare Sector Collaboration: Joint working groups involving NHS and Indian counterparts were established, fostering knowledge exchange in cyber security practices within the healthcare sector.

- Cyber Exercising and Training Events: Between December 2023 and April 2024, four cyber training events were conducted, training over 100 cyber professionals and police officers. These efforts culminated in the design of Tier 1 police training modules on various cyber forensic procedures.
- India Cyber Chevening Fellowship: Co-funded through the Global Cyber Programme and India Cyber Programme to expand the programme from previous years, 9 Indian fellows undertook a 10-week immersion research programme in the UK delivered through Cranfield University. A Japanese cohort of fellows joined the Indian fellows for the last 5 weeks of the programme delivering skills-building in a trilateral setting, engaging with NCSC, DSIT, FCDO specialists, academics and industry leaders. A full Chevening cyber and tech alumni reflection and networking session was held in the margins of the 2023 Bengaluru Tech Summit.
- CyberForYouth Programme: Initial engagement with DSCI was established in September 2024 to support a youth-focused cyber security program, reinforcing efforts in capacity building from the grassroots.
- Expanded State-Level Engagements: Building on the initial project scope, state-level engagements expanded to include West Bengal, Madhya Pradesh, Karnataka, and Kerala, diversifying the geographical reach of the project for the next FY.
- Cyber Hackathon Proposal: A proposal for a cyber hackathon was developed, with delivery expected in late 2024, further contributing to collaborative efforts in cyber innovation.
- Community Consultations in Gujarat: Primary research involving community consultations in Gujarat laid the groundwork for grassroots involvement in cyber awareness and capacity building.
- Cyber Awareness Workshop in Gujarat: A two-day workshop attended by law enforcement agencies, banking professionals, and educators was held in May 2024, expanding cyber awareness across multiple sectors.
- UK profile-building: UK sessions hosted at Bengaluru Tech Summit, the Data Security Council of India’s Annual Information Security Summit and Vibrant Gujarat Investment Expo to promote the UK’s cyber values to key stakeholders and provide a platform for Cyber Chevening Fellows to present on their UK experiences and reflections.

## Key Lessons:
Building relationships: Strong foundations in relationships are critical. Involvement and support from state-level entities, such as Deputy British High Commission offices, have been highly catalytic.

Agility and responsiveness: Being flexible and responsive to demand is essential. Adjusting inception plans led to increased engagement and demand from stakeholders.

Impact of external factors: National and state elections, along with global events (like G20), have slowed implementation progress. MEA resources have been more constrained than anticipated, resulting in less engagement with the British High Commission (BHC).

UK Subject Matter Experts (SMEs): Involvement of UK SMEs (both in person and virtually) has been a significant driver of progress. Examples include cybercrime engagement with Maharashtra, Telangana, and Gujarat, leveraging input from organizations such as EY, NCA, CYSIAM, and London Police College. UK Healthcare experts were instrumental in workshops, and communication specialists played a role in awareness and skill development.

Indian SMEs: While Indian Subject Matter Resources (SMRs) contributed, their involvement hasn’t been as crucial to progress as initially envisioned.

Language challenges: Using local languages for training and awareness was always seen as important. However, participants’ actual language proficiency (both verbal and written) may be lower than what was self-reported.

Portfolio-wide understanding: There is a need to improve understanding across the portfolio regarding program progress, challenges, and successes, including the sharing of emerging success stories.

## Key Recommendations for FY 23/24:
- Strengthen Relationships and Partnerships: Continue fostering relationships with key stakeholders, such as state-level offices and the Deputy British High Commissions, which have proven to be catalytic. Engage these entities early in the process and maintain consistent communication.
- Remain Agile and Adaptable: Flexibility in planning and responsiveness to emerging needs should be integral to the project management process. Ensure that plans are reviewed periodically to align with changing stakeholder demands and new opportunities.
- Anticipate Disruption and Install Mitigation plan: Plan for slowdowns or interruptions in implementation during national and state elections, and global events such as the G20. Build risk resilience into project timelines to accommodate potential resource constraints, particularly working with the Ministry of External Affairs (MEA).
- Maximise Use of Subject Matter Experts (SMEs): Leverage the involvement of UK-based SMEs to drive progress, especially in areas such as cybersecurity, healthcare, and communication. Continue involving them in both in-person and virtual capacities to enhance the value of their input.
- Tailor Training Materials for Local Language Proficiency: Adapt training and awareness materials to match the actual language proficiency of participants. Simplify content or include language support if participants’ reported proficiency does not match their real capabilities.
- Improve Communication on Progress and Challenges: Strengthen mechanisms to communicate the program’s progress, challenges, and successes across the portfolio. Create a system for regular updates and sharing of emerging stories to keep all stakeholders informed and aligned.
- Resource Planning and Engagement Strategy: Develop strategies to mitigate the resource constraints faced by partners such as the British High Commission. Anticipate periods of limited engagement and plan accordingly to ensure continuity of efforts.