CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Indo-Pacific Cyber Programme
Country and Region	Indo-Pacific (Indonesia, Malaysia, Philippines, Thailand, Japan, Mongolia, Solomon Islands, Fiji)
Programme ID	C-CYB-0004	IATI Unique ID	CSSF-14-000003
Start date	October 2022	End date	March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth & Development Office (FCDO)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£10m	£4.4m	£4.1m
Non-ODA	£4m	£1.2m	£0.7m
Total	£14m	£5.6m	£4.8m

## Outputs
Output statements	Individual Output Rating
Target countries and projects are identified; prioritisation framework established for innovative interventions; projects are scoped and commissioned in line with authority’s Gender Equality and Social Inclusion (GESI) requirements and capitalise on opportunities to promote gender equality	4
Regional stakeholders have collaborated on research areas of mutual interest; multilateral organisations are supported to address cyber security issues strengthening the evidence base	3
National Cyber Agency stakeholders have developed their cyber detection and response operations; OR scoped out new capabilities in active cyber defence; OR reviewed and (re-drafted) their security policies and frameworks in line with non-discriminatory principles	4
Critical Sectors (CNI) resilience: Risk posture of priority sectors has been established; sectoral working groups are set-up to support public and private sector CNI organisations to manage their own security and resilience	4
Citizens or workforce groups (target audience) have improved access to cyber skills curricula and target audiences of women and men have engaged positively with cyber awareness communications campaigns that reach all social groups	4
Collaboration with Regional Country Stakeholders is enhanced through cyber capacity building on specific activities and tactical knowledge transfer at subject matter expert level	3
Countries in the region have improved threat and vulnerability information, allowing them to protect themselves more effectively against cyber-attack	3
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Programme Outcomes / Improved response and resilience amongst stakeholders in priority countries to better protect national and UK CNI and reduce cyber threats in the region; / Increased cyber awareness amongst target audience leads to improved cyber hygiene practice; / More effective UK influence and adoption of UK positions in the region to improve regional partners governance of cyberspace. Increased adoption of gender-sensitive lens towards open and safe cyber space. / Intermediate Outcomes / Stakeholders in regional priority countries have improved capabilities for investigating and disrupting cyber threats; / Stakeholders in regional priority countries understand and manage cyber risks within CNI; / Regional partner countries share UK values, standards and principles, and invest in emerging regional state capabilities.
Outcome Assessment	On balance the overall outcome assessment is scored as Green/4 and is on track to meet or exceed its outcome targets. The programme is clearly shifting from the initiation of tactical interventions towards more strategic interventions as it enters Year 2. There is evidence which indicates that the programme is beginning to contribute to the delivery of its intermediary outcomes. / This scoring also takes into account programme resourcing and a regional focus. The core of the programme team and prime implementer is based in Jakarta and is required to make tactical use of its resource to build relationships and initiate activity across Southeast Asia and the Pacific to support delivery. / Under Outcome 1 and Outcome 2, the programme is showing that it could exceed expectations. On current trajectory, the planned results are at low risk and will continue to benefit from a full year of delivery in Year 2. Where delivery is on track, but where there are some doubts about whether outcome targets will be met, key recommendations have been made. For Outcomes 1 and 2 this encourages the programme to maintain it’s delivery style while refining how it collects and analyses evidence of change. Review recommendations mostly apply to Outcome 3, where plans to refine and improve delivery are already in place. / More broadly, the programme has delivered notable positive wider and unintended effects. To sustain the trajectory of change the programme will benefit from utilising the review recommendations, including on MEL, gender and conflict sensitivity.
Overall Outcome Progress Rating:		4
Overall Risk Rating:		High

## Summary of Programme Performance
Year	2022/23		2023/24
	Output	Outcome	Output	Outcome
Programme Rating	3	3	4	4
Risk Rating	Medium	Medium	High	High

## What Support Did the UK Provide in FY 23/24?
- Delivered training and workshops to National Cyber Agencies and CNI organisations on best practice operating procedures and policies and approaches to managing cyber threats.
- Provided real-time threat and vulnerability data to partners through threat feeds, vulnerability signatures and training.
- Delivered cyber awareness campaigns to support key ministries, CNI entities and SMEs to enhance cyber hygiene practice, public-private partnerships, and cybersecurity management.
- Collaborated with regional partners, including establishing a Women in Cyber Fellowship, supporting the cyber security of the 2023 Pacific Games, and delivery of a cyber capacity building conference for Pacific Island nations.
- Worked with multiple partners to assess cyber maturity and provide recommendations to support the delivery of partner country cyber security strategies.
## Key Results for FY 23/24:

- Increased national cyber agencies understanding of key governance structures, policy implementation, and relationships with critical national infrastructure. Provided priority recommendations for multiple national cyber agencies to strengthen threat response.
- Built enduring relationships with notable National Cyber Agencies and CNI stakeholders to support delivery in Year 2, including a roadmap for delivery of further training.
- Enhanced the practice of cyber hygiene across national cyber agency partners and CNI entities.
- Equipped national cyber agencies with improved access to threat and vulnerability information and enhanced protection against specific cyber-attacks.
- Initiated a Women in Cyber Fellowship which recruited 18 delegates from 9 countries and established a network of cyber security experts in the region.

## Key Lessons:

- Relationship building between suppliers and recipients is the key foundation to enable delivery of activity, training and workshops. This enhances training delivery and provides important challenge that refines future activity.
- As a regional programme multiple opportunities emerge for the UK to develop new relationships or shift activity to support different partners. A flexible and adaptive model, enhanced by the HMG/Supplier joint prioritisation process, has been a useful method to deliver effective short-term impacts that lead to longer term relationships.
- Regional programmes require a more flexible approach to monitoring, learning and evaluation. The breadth of the work allows for multiple change stories, challenges and unintended positive effects to emerge, which should be captured through a flexible evaluation process.

## Key Recommendations for FY 23/24:

- Refine programme Results Framework, including indicators for outputs and outcomes, to enhance evidence collection in Year 2.
- Improve articulation of conflict sensitivity and understanding of risks associated with project delivery.
- Enhance GESI analysis throughout project design and delivery and at programme level.
- Consider recruitment of additional resource to support delivery in the broader region.