CSSF Gender, Peace and Security Portfolio Annual Review (FY23/24)
# A. Summary Sheet
Programme Title	Gender, Peace and Security (GPS) Portfolio has two programmes within scope of this review: / Programme: Women Peace and Security (WPS): Women’s Leadership and Peace and UK Capabilities / Programme: Gender and the Integrated Review Refresh (IRR)
Country and Region	Thematic Portfolio (Gender, Peace and Security)
Programme ID (WPS & UKC)	C-GPS-0004	IATI Unique ID (WPS & UKC)	CSSF-13-000002
Programme ID (Gender & IRR)	C-GPS-0003	IATI Unique ID (Gender & IRR)	CSSF-13-000003
Start dates (both)	April 2022	End dates (both)	March 2025
HMG Partners / (Lead department in bold)	FCDO, MOD
WPS: Women’s Leadership and UK Capabilities	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£ 7,500,000.00	£ 2,500,000.00	£ 2,701,625
Non-ODA	£ 750,000.00	£ 250,000.00	£ 152,416
Total	£ 8,250,000.00	£ 2,750,000.00	£ 2,854,041
Gender and Integrated Review Refresh (IRR)	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£ 7,500,000.00	£ 2,500,000.00	£ 1,189,588
Non-ODA	£ 750,000.00	£ 250,000.00	£ 171,416
Total	£ 8,250,000.00	£ 2,750,000.00	£ 1,361,004

## Outputs
Output statements	Individual Output Rating
WPS: Women’s Leadership and Peace and UK Capabilities
Output 1: Better awareness among HMG officials and decision makers on gender responsive and gender transformative approaches to conflict and security	3
Output 2: Improved engagement and communication within and between HMG and international partners on good WPS and gender-responsive and gender-transformative security policy and practice	4
Output 3: HMG provides more support to women’s rights organisations (WROs), grassroots organisations and key power holders to support and enable WPS work	4
Output 4: Greater access to WPS capability and expertise for officials across HMG working on conflict and security policy and programmes	2
Gender and the Integrated Review Refresh (IRR)
Output 1: Communication channels established between hey HMG actors in this space to share information and good practice.	4
Output 2: CS / SF GPS team signals commitment and importance of HMG to integrate gender-responsive and ideally gender transformative perspectives into work on IRR priority areas.	2
Output 3: Development of an evidence base on gendered nature of security issues in priority IR areas and how gender-transformative interventions can support delivery on IRR objectives	4

Overall Rating of Output Delivery	3

## Outcomes
WPS and UK Capabilities Outcome statement(s)
Outcome 1: HMG actors are better able to take informed decisions on GPS policy and to prioritise, integrate and support the delivery of gender-responsive/transformative approaches within conflict and security programming
Outcome 2: Stakeholder groups and gatekeepers at different levels (local, national, international, HMG) ensure peace and security processes are more inclusive, support women’s rights and meaningful participation.
Outcome 3: WROs and grassroots organisations are organisationally stronger and more sustainable, and better equipped to undertake WPS activities
Outcome Assessment	Outcome 1 – Green / Outcome 2 – Green / Outcome 3 – Green
Overall Outcome Progress Rating: Green		The programme is meeting its targets and is rated Green. However there is an imbalance of attribution of the results with outcome results drawn from three out of five projects
Overall Risk Rating: Medium		Medium – the programme is not currently tracking the contribution of projects towards the programme outcomes.

Gender and IRR Outcome statement(s)
Outcome 1: Security benefits are more equally experienced and inequalities that drive insecurity are reduced through increased and improved participation of women, girls and sexual/gender minorities.
Outcome 2: Increased adoption of gendered perspectives in the UK's policy and programming to address emerging security threats (specifically cybersecurity, climate security/resilience and serious and organised crime).
Outcome 3: Improved understanding among Chief Security Officers (CSOs) and HMG of how pilots and inclusive/ gender transformative programming can support the delivery of wider peace and security objectives (specifically cyber, climate and Serious and Organised Crime (SOC).
Outcome Assessment	Outcome 1 – Green / Outcome 2 – Amber/Red / Outcome 3 – Green
Overall Outcome Progress Rating:		Amber – limited monitoring of outcome change raises concerns as to whether the reported results are sufficiently significant to deliver the intended change. The Programme Manager recognises the imbalance of effort towards external impacts (outcome 1) over internal, HMG focus (outcome 2).
Overall Risk Rating:		Medium

## Summary of Programme Performance
WPS and UK Capabilities
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	3	Amber	3	Green
Risk Rating	Medium	Medium	Medium	Medium	Medium	Medium
The WPS: Women’s Leadership and UK Capabilities programme is meeting its targets. However, outcome targets have been met by the performance of three projects (Queering Atrocity Prevention (AP), Resourcing Change and WPS Helpdesk) with no targets set and results reported on the contribution of the National Action Plan (NAP) Implementation Fund and Zoa Dorcas Project. The NAP Implementation Fund and Zoa Dorcas projects started late however process indicators and targets could have been incorporated within the RF to assess their contribution towards the programme outputs and outcomes.

Gender and the IRR
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	3	Amber	3	Amber
Risk Rating	Medium	Medium	Medium	Medium	Medium	Medium
The Gender and IRR programme is delivering strategically relevant research on the intersections between gender and emerging security threats (output 1). Whilst the targets for output 2 indicators were almost achieved – with knowledge products shared and events held - it is unlikely that these activities will be sufficient to create programme entry points as envisioned by output 2. There has been an imbalance of efforts within this programme towards external delivery through IPs and attention needs to be turned towards improving HMG decision maker use of the research products. Output 3 has also been met.

## What Support Did the UK Provide in FY 23/24?
The Gender, Peace and Security portfolio has supported HMG actors, external women’s rights organisations and civil society organisations addressing cross-cutting conflict and security challenges to prioritise, strengthen their capabilities, and collaborate on progressing gender equality.

Funding was allocated across two programmes:

Women, Peace and Security; Women’s Leadership and UK Capabilities Programme (started 22/23 and ends 24/25:
This programme compromises of two elements:
I) UK capabilities: This element of the programme seeks to enable both domestic and international departments working on national security and in Fragile and Conflicted Affected States (FCAS) to make policy and programmes more responsive to the gendered dynamics of the threat, and/or context. This programme aims to strengthen cross HMG capability on gender by enabling agile responses to new geographic contexts and research on innovative policy approaches. It aims to support UK leadership to prioritise and integrate gender in policy and programmes. This is achieved through:
  - the Women Peace and Security helpdesk which offers HMG actors on-demand analysis and gender expertise to improve the integration of gender within HMG policy and programming.
  - The WPS NAP Implementation Fund was established and supported the Conference on Preventing and Countering Gender-Based Disinformation, MOD hosted event at the UN Conference on the Status of Women and planned Wilton Park Conference on Gender Policy into Practice, identifying barriers within FCDO to delivering gender policies.

II) WPS: this element of the programme provides core and flexible funding to civil society and women’s rights organisations through the Resourcing Change Project, Mass Atrocity Prevention Project and Promoting Gender Transformation in Justice, Law and Order Institutions (Zoa Dorcas) to strengthen their meaningful participation and leadership of women and people of diverse sexual orientation and gender identity in peace and security processes at all levels.

Funding new areas of research and evidence-collection in topics at the forefront of and influencing international security agendas; such as the Sexual Orientation and Gender Identify integration into Atrocity Prevention Frameworks (Queering AP) project.

Gender and the Integrated Review Refresh (IRR) Programme
- This programme aims to explore the links between gender and emerging facets of security highlighted through the Integrated Review Refresh (2023), premised on the evidence that gender-sensitive approaches are more effective and sustainable at tackling security challenges.
- In FY 23/24, the programme implemented projects and research on Integrated Review Refresh priority areas, specifically cyber security and climate security/resilience, including:
  - GENRE II [Natural Resource management in Mali]
  - Women’s Role in the Illicit Wildlife Trade in Ghana, Burkina Faso and Cote D’Ivoire
  - Women’s Resilience Against Environmental Crimes
  - Building Women’s Resilience in addressing climate change in Somalia
  - Building Women’s Resilience to Transnational Crime in Mozambique
  - Understanding Gender and Cyber Security, Chatham House event
## Key Results for FY 23/24
- Providing platforms for WROs, women and people of diverse genders for their voice to influence internationally. Facilitating these WROs at the grassroots to network, learn, build their movements and international communities, and in particularly to influence at the global level.
- Challenging internal barriers through the Helpdesk and the Wilton Park contribution to Gender Policy in Practice, which is fundamental to affecting internal change is to understand the barriers. Important for the NAP implementation Fund.
- Leading the international community in promoting an intersectional model and concrete evidence-based to Mass Atrocity Prevention warning signs and linking those patterns and experiences to through power analysis in the decision-making sphere.

## Key Lessons:
- The need for the GPS Portfolio Board to maintain a strong and clear focus on the ISF strategic direction and principles, to provide strategic guidance to the portfolio team. This is especially important during periods of staffing transition.
- The need to sequence significant shifts in the portfolio to minimise impact on business continuity and pressures on staff. The complete and simultaneous change of portfolio team, with developing capability within the team, alongside a shift of the portfolio from Integrated Security Fund Unit (ISFU) to Office for Conflict, Stability and Mediation (OCSM), and governance restructuring impacted the ability of the portfolio team to take both a strategic view of their programme delivery alongside meeting programme management requirements. Strong knowledge of the WPS evidence and policy space and experience of leading staff to deliver women, peace and security programmes are essential prerequisites for the GPS Portfolio lead role.

## Key Recommendations for FY 25/26:
- Articulate a clear ISF-led purpose for the portfolio, with a narrower focus that links to UK National Security. Ambition should be realistic, based on available resources and levers. A clear route for achieving ambitions should be articulated to ensure that all the projects across the portfolio contribute towards the same goals. Reduce the number of projects. Little bits of value added in many directions, contributing towards different policies has become difficult to quantify overtime. The GPS portfolio have commenced initial steps in FY 24/5 to address this issue.
- Address the uneven alignment with the ISF principles, with a stronger focus on innovation. Only renew projects that deliver localised impact if there are clear links to innovation, learning on improved approaches to addressing the intersection on gender and security that can be applied to programmes or will generate learning to influence policy making within HMG. The GPS portfolio have commenced initial steps to address this issue.
- Embed the new GPS Portfolio Board structure, with ISF to induct new board members on the purpose of ISF. SRO/Board members to have active oversight of the portfolio, ensuring the portfolio is clear on the ISF led purpose of the GPS portfolio and identify challenges and mitigation measures to business continuity risks. The GPS Portfolio board should take an active role in delivering the programme outcomes in influencing HMG decision makers to prioritise, integrate and support gender perspectives in policy and programming.
- Actively use the Results frameworks as a tool for monitoring programme outcomes and outputs. Agree and use a method to monitor programme outcomes. The AR team recommend using the outcome harvesting system that has been developed, and for the programme managers to deepen their understanding of how it works through training or coaching support from the ISF Monitoring, Evaluation and Learning (MEL) team. The GPS portfolio should test the strength of programme-wide outputs and delivery against outcomes. Action the series of challenge sessions to deep dive and scrutinise programme RFs. Ensure that all projects have at least one indicator that they are reporting against in the programme results frameworks.
- Focus more on overcoming internal HMG barriers to advancing gender approaches to conflict and security, using the findings of the Gender Policy in Practice Review. But be more targeted on who within HMG the portfolio seeks to affect change among (senior decision makers, policy makers, programme delivery staff), collaborate closely with them, be very selective on the range of issues around which to generate novel evidence and amplify this learning in order to influence policy and achieve programme outcomes. A learning and influencing strategy could aid this.
- Introduce a Technical Advisory working group of ISFU Gender Advisors to support the identification of policy and evidence gaps areas to advance, and technical advice on the design, development and delivery of research, knowledge products and projects to ensure quality and maximise the update of the findings.
- Establish a definition of VFM, re-establish a VFM processes and undertake a VFM assessment for both programmes.