CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	Environmental Sustainability and Climate Change (ESCC) Programme
Country and Region	UK Overseas Territories (OTs)
Programme ID	C-OTS-0007	IATI Unique ID	CSSF-07-000011
Start date	April 2023	End date	March 2024
HMG Partners / (Lead department in bold)	FCDO
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	1 year - £850,000	£1,200,000 (original) / £900,000 (revised Jul) / £850,000 (revised Nov)	£846,026
Non-ODA	1 year - £356,000	£800,000 (original) / £75,000 (revised Jul) / £95,164 plus £261,004 Admin (revised Nov)	£399,286
Total	1 year	£1,206,168	£1,245,311

## Outputs
Output statements	Individual Output Rating
St Helena Cloud Forest: Through capacity building, knowledge products development and improved infrastructure, organisations on island are able to improve biodiversity management, increase plant propagation and habitat restoration with the overall aim of increasing area of restored habitat by 3ha by March 2025.	3
St Helena Cloud Forest: Through a programme of research and provision of technical assistance St Helena Government and Connect St Helena have a better understanding of St Helena's water resources, and data collected to inform the development of the water resources management plan is being used to influence day to day water management decisions.	4
St Helena Cloud Forest: Increased capacity of in-Territory agencies to effectively manage the Peaks National Park through resourcing the implementation of the management plan, through increased public awareness/engagement and international promotion of the project.	3
ESCC Programme repositioning identifies future programming priorities to align with UK Government (UKG) mandate and CSSF	3
Production of bespoke Rapid Climate Security Assessments to inform OT priorities and climate change needs, leading to targeted interventions by the programme	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement(s)
St Helena Cloud Forest: The people of St Helena better understand and are able to manage, respond to, and be better protected from the risk of climate change through an increased and better managed water supply with greater resilience to the risk of drought.
OT Governments have an increased comprehension of the drivers and impacts of climate change and a clear understanding of how to mitigate and build resilience.
Outcome Assessment	The overall performance assessment for the programme, rated amber/green, indicates moderate progress toward outcome-level goals, with strong gains in specific areas. Key outcomes, including capacity-building, biodiversity restoration, and data-driven water management, show foundational achievements that align well with long-term goals.
Overall Outcome Progress Rating:		Amber/green
Overall Risk Rating:		Medium-High

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	4	Green	3	Amber	3	Amber/green
Risk Rating	Medium-High		Medium-High		Medium-High
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- The ESCC programme provided the Overseas Territories (OTs) with equipment, training and knowledge sharing and capacity building to enable the OT Governments (OTGs) to better understand, prioritise and tackle the causes and resulting risks of climate change.
- The programme supported the St Helena Government (SHG) for a fourth year to tackle climate change related drought by replanting the native cloud forest.
- The provision of guidance to better target CSSF climate support in the OTs, including recommendations on the scope and communication of the ESCC offer and working with OTGs to understand their specific climate change risks, gaps, and priorities.
## Key Results for FY 23/24
- The Cloud Forest (CF) project had mixed success against outcomes due to the pathogen, but because of RSPB’s adaptability and effective financial management, important progress towards programme objectives were still achieved. Yet, there is still concern over the sustainability of the programme as future funding has not yet been secured and the withdrawal of funding is considered to be catastrophic to the continuation of the CF. These sustainability concerns limit the effectiveness of the programme.
- With Atkins, the work conducted had mixed success in delivering against the outcome of enhancing OT government awareness of the drivers and impacts of climate change. This is largely because the initial output, a repositioning report, was replaced upon completion with the CSAs, making the initial work redundant. While this may be an effective stepping stone for future programmatic funding, in terms of delivering this year’s outcome, it was less successful. The final assessments were more useful in informing future UK interventions and aiding smaller OTs’ knowledge.
## Key Lessons:
- In general, it was felt that the level of reporting on the Cloud Forest, especially at the monthly level, was burdensome and arduous. In many cases it was stated that there was a lot of duplication between monthly and quarterly reports, especially for partners where work does not change much monthly. Given the 8 different downstream partners, this puts a lot of pressure on RSPB and the PM to coordinate the report for the deadline. One partner compared the reporting process for the Darwin fund, which was considered less intensive and more appropriate for a project of this nature.
- Delivery partners noted how beneficial the underspend mechanism was, how this had led to the purchase of equipment they otherwise would not have been able to afford and would be able to use past the project end.
- While the programme is now beginning to branch out to consider other sustainable sources of finance, this could have been considered earlier as access to finance is crucial for climate security.
- As a result of the pathogen, one important lesson going forward was to have adaptative management within a framework of diseases that is proactive instead of reactive.
## Key Recommendations for FY 23/24:
- The theory of change is fit for purpose, although could benefit from more of a focus on how to achieve the outcome ‘OTs have a clear understanding of how CSSF and other funding streams can help address climate change in their OT.’
- An overarching approach to climate finance across the OTs would be more useful than relying on specific in-territory projects. To reduce reliance on HMG funding, develop a focused training initiative for OT governments on accessing international climate finance. This would involve identifying accessible funding sources and building skills in grant application and project management, enabling OTs to pursue funding for climate adaptation and resilience projects independently.
- An annual report against the outputs, milestones and their targets would be useful as the quarterly reporting against these was at times unclear.
- To develop a plan to enable access to the Cloud Forest under different contingency situations. Instead of waiting for information, proactive planning could be conducted to anticipate the results and ensure that partners and stakeholders are on the same page.
- Recognise and plan for potential OT capacity constraints by securing senior buy-in early, establishing clear points of contact, and ensuring regular communication with each OT. Additionally, improved coordination between FCDO, Atkins, and other His Majesty’s Government (HMG) departments can streamline the Climate Security Assessment (CSA) process, reduce duplication, and support coherent messaging, enhancing OT alignment with climate security goals.
- Establish a structured forum for regular inter-OT discussions on shared climate resilience challenges. By fostering a space for OTs to exchange strategies and lessons learned, this forum would address mutual concerns, such as water scarcity and biodiversity threats, through knowledge-sharing and collaborative solutions. This initiative could also support joint problem-solving on complex issues, create synergies in addressing climate security priorities, and strengthen OT capabilities through shared resources and expertise.