CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Justice Programme
Country and Region	UK Overseas Territories (OTs)
Programme ID	C-OTS-0009	IATI Unique ID	CSSF-07-000009
Start date	April 2023	End date	March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO) / Ministry of Justice (MOJ)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£3,070,000	£1,154,000	£1,402,293
Non-ODA	£14,253,000	£7,990,000	£7,974,872
Total	£17,323,000	£9,144,000	£9,377,165

## Outputs
Output statements	Individual Output Rating
(No. and statement)
(4) Deliver training, deployments and infrastructure projects across justice system & embed Prison Standards Framework and training support	3
(5) Working with local governments to facilitate the implementation of child safeguarding mechanisms to help them work towards civil and criminal protections for children that are more compliant with international standards and frameworks.	4
Overall Rating of Output Delivery	[Amber / Green]

## Outcomes
Outcome statement(s)
Overseas Territories have effective and sustainable, human rights-compliant criminal justice systems, with better resourced prison, probation, and court services that gain increased political support and public confidence by creating a safe justice system that meets common minimum standards and reduces reoffending.
Social Services strengthens its capability and commitment to deliver better child safeguarding services.
Outcome Assessment	The overall assessment recognises the significant and unique challenges facing individual Overseas Territories (OTs) and reflects the positive approach, attitude and dedication from the stakeholders interviewed and evidence seen via site visits to St Helena and Monserrat. The scope of the Justice programme is broad, and while this review covers the child safeguarding and prisons elements only, we also opted to discuss some aspects of law enforcement where there is a direct read across. This assessment also reflects on the impact of limited funding and resource availability required to deliver an ambitious set of recommendations from the previous review and considers the longer-term approach to ensure a level of sustainability beyond the end of the programme. / The review found that while workloads continue to be high and political and operational challenges remain, the programme has achieved some substantial positive results during FY 23/24 that will provide longer-term sustainability and capability, particularly where the focus has been on training. / The training funded through the programme to improve Prison and Probation capability, largely focusing on Use of Force training, performed strongly across the OTs, equipping the instructors with critical skills to reduce risks and, in the case of St Helena, upskill all operational staff at HMP Jamestown. The additional support provided through a series of workshops held at the Overseas Territories Prison Superintendents Conference, attended by representatives from across the OTs, further bolstered the capability across the OTs. / Child Safeguarding came into the Programme as a key component in FY22/23, and it is early to give a full assessment on the outcome of this work. However, the review noted child safeguarding capability is moving in an upwards trajectory compared to FY22/23 with the successful conclusion of the litigation guardianship work in Bermuda, and a focus on peer mentoring and coaching for social care officers and residential managers resulting in increased learning across islands and the start of the development of robust policies and processes.​ / Several stakeholders pointed to the value of the programme raising concerns on what would happen when the programme ends in FY24/25, pointing to the need for sustainability and consideration on where they could go for continued support. The review recommendations consider the programme shift from CSSF to ISF, with revised Theories of Change and new Results Frameworks expected for FY24/25.
Overall Outcome Progress Rating:		Amber/Green
Overall Risk Rating:		Medium-Low

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	2	Amber / Red	4	Amber / Green
Risk Rating	Medium-Low		Medium-High		Medium-Low
Notes: Output/Outcome score

## What Support Did the UK Provide in FY23/24?
- Aim: The aim of the Justice Programme (JUP) is to support the British Overseas Territories to deliver safe, effective, and human rights compliant justice and safeguarding systems that protect the public with access to UK and International expertise and best practice.  The Programme has three separate components: Law Enforcement, with a specific focus on the police services; Prisons and the wider justice system (formerly known as prisons and probations); and Child Safeguarding (added as a programme component in FY 22/23). The work of the programme spans across the Caribbean, Bermuda and the South Atlantic. The programme has been approved to run until 2025. This review focuses on Prisons and Child Safeguarding.
- Funding: In FY 23/24 the JUP had an initial allocation of £8.6m, and a revised budget after November’s Supplementary Estimates of £9.5m.
- Prisons: Support to HM Prisons in the OTs includes: staffing and resourcing review to improve staff structures; development of training and vocational skilling of prisoners; upskilling OTs prison staff through training and ‘use of force’; and capacity building through sharing of skills and information.
- Child Safeguarding: capacity building to support safeguarding systems to protect vulnerable young children; continued rollout of the Practice Partnerships Project twinning OTs with high performing UK local authorities; litigation guardianship support for Bermuda.

## Key Results for FY23/24
- Development of a detention standards framework, and bolstering security practices within the prison through training / coaching, with a focus on use of force training, leading to better management of ‘use of force’ scenarios and overall improved safety protocols within the prison. In St Helena the instructors now have a rolling programme to ensure all operational staff receive annual refresher training which has given officers new confidence to handle and diffuse confrontational situations.
- Completion of urgent infrastructure projects for example the programme sourced, funded and installed new locks for the prison in Montserrat that were vital for the prison to deliver safe outcomes for prisoners.
- Supported the development of a rehabilitation offer to prisoners in TCI, addressing training and vocational upskilling of prisoners, and meeting community engagement objectives.
- Ongoing implementation of projects such as Practice Partnerships pairing OTs with high performing UK local authorities to provide ongoing technical expertise and support that builds better safeguarding systems.
- Conclusion of the litigation guardianship project in Bermuda with the final version of practice guidance completed in February 2024. The new child centred reporting templates and guidance in Bermuda have ensured reports are better structured with judges and other stakeholders and court users feeding back that reports were much stronger about the voice of the child, in accordance with best practice internationally.

## Key Lessons:
- Funding constraints and project decisions are compounded by lead in times. In effect, decisions on projects need to be made at the start of the FY to ensure that spend can be disbursed in good time for procurements to be made to be delivered within that FY. This affects each OT differently where different structures exist, and OTs have different access to providers, for example more remote OTs often work with limited resources and lengthy procurement processes further frontloading decisions making requirements that have to take place in the first six months if they are to meet their targets.
- Some OTs are less visible than others: feedback flagged concerns whereby visibility of poorer OTs often comes at a cost to those OTs experiencing significant security issues. To ensure greater visibility and a solid understanding of the complexities and context, stakeholders/programme partners should visit relevant OTs to build up a picture of the requirements, leading to better targeted support and greater understanding on the impact made. The benefit of being in an OT and meeting delivery partners on the ground cannot be underplayed.
- Sustainability: multiple programme partners raised concerns over long term sustainability and access to funding suggesting that in some cases once the funding window had closed the long term benefits would likely stall. Being able to better support programmes towards the end of the life of that programme to ensure sustainable longer-term funding or secure further funding from other additional sources would reduce some of the uncertainty and delay.

## Key Recommendations for FY 23/24:
- The Justice Programme is the largest and one of the most complex CSSF (ISF for FY 24/25) programmes and therefore requires a higher degree of programme management expertise and a strong grip of the subject matter. Greater emphasis should be given to programme support in the final year of the programme to focus on and improve long term sustainability outcomes, bolster alignment between the UK government and OTs, and support programming and funding decisions.
- Programme reporting is largely activity focused and could be more enquiring to explore why an action was taken and drill down into the challenges that affected the success of the programme.
- The value of training is evident across the OTs and the positive impact this has had. Work should continue to develop the training offer in relation to prisons and safeguarding across the OTs as part of the Justice Programme, but with an eye to long term sustainability beyond the end of the programme. The training requirements will need to be adapted to reflect the context and operational capability of each OT, which differ considerably.
- The programme should pivot to include more support and greater investment on internet / online safety for both adults and children when it comes to safeguarding, and not just focus on the financial safety awareness aspect of cyber security. This could build on existing platforms through the cyber security
- Quarterly Boards should fully reflect the work of the programme across the OTs and ensure clear emphasis on how the programme is aligned to HMG strategies.
- Open discussions need to take place between delivery partners / beneficiaries to avoid unilateral decision making on programme direction and / or recruitment of personnel.