CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Pacific Programme
Country and Region	South Pacific (Fiji, Tonga, Vanuatu, Solomon Islands, Papua New Guinea, Samoa)
Programme ID	C-APC-0002	IATI Unique ID	CSSF-09-000008
Start date	April 2021	End date	March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth & Development Office (FCDO), Ministry of Defence (MOD) UK Hydrographic Office (UKHO), National Crime Agency (NCA)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	10.35m	4.45m	3.696m
Non-ODA	0.75m	0.1m	0.024m
Total	11m	4.55m	3.72m

## Outputs
Output statements	Individual Output Rating
CONFLICT RESOLUTION AND PEACEBUILDING: Strengthened resilience to conflict and capacity to improve stability in target geographies	3
SECURITY AND JUSTICE: Strengthened legal and judicial systems and legislative frameworks, aligned to the RBIS	3
MARITIME SECURITY: Enhanced compliance with international maritime laws and conventions; and strengthened security ties on maritime security including management of Exclusive Economic Zones (EEZs).	3
RESILIENCE TO DISINFORMATION: Enhanced resilience of public discourse to malign narratives, particularly in relation to governance processes.	3
HMG POLITICAL ACCESS AND INFLUENCE: ISF programme contributes to HMG political access and influencing in support of progress against outcomes 1-4.	4
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement
Pacific island countries remain stable and increasingly resilient to malign external influences through an alliance of likeminded countries.
Outcome Assessment	The CSSF Pacific programme generally performed well in FY23/24. Several issues regarding programme management were improved, and updates to core documents like the theory of change were aligned with relevant strategies and clearly linked to His Majesty’s Government (HMG)’s CSSF objectives. The Head of Programme role gap meant that key project mobilisation and programme management tasks were delayed, and successful delivery required a ‘sprint finish’. Substantial progress with programme management and governance was made in the second half of FY23/24. / Through this programme, the UK continued to refine its security offer to Pacific island countries (PICs), building relationships based on trust, expertise and genuine value-add. Work to strengthen PICs’ integrity institutions and core sectors like media were good value-for-money investments, especially when delivered through partnerships with British institutions or experts, like the BBC Media Action projects in the Solomon Islands and the deployment of a justice to the Vanuatu Judiciary. The BBC’s global reputation and the Justice’s experience of British legislation (and its similarities with processes in Vanuatu) were examples of UK value-add in important national security sectors. / The new projects on maritime security demonstrated the programme’s ability and willingness to response quickly and decisively to strategic steers from the centre, and led to significant and sometimes unintended, positive outcomes, including the finalisation of the North Fiji Basin Extended Continental Shelf submission and ongoing support to the Government of Fiji with its maritime security strategy. The United Nations Development Programme (UNDP) Coastal Communities maritime security has the potential for scale across other PICs. / The ability to scale projects to more than one PIC will remain important for ISF Pacific, which already has a large number of individual projects which puts a heavy administrative burden on the programme team. In doing so, activity in FY23/24 has demonstrated the importance of taking an individual, contextualised approach to each PIC. / Coordination with Australia and other major development partners was strengthened, and will remain key to successful delivery of UK activity.
Overall Outcome Progress Rating:		3
Overall Risk Rating:		MEDIUM

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	3	3	3	3	3
Risk Rating	Medium	Medium	MEDIUM	MEDIUM	MEDIUM	MEDIUM

## What Support Did the UK Provide in FY 23/24?
Through its Conflict, Stability and Security Fund (CSSF) programme – the UK continued to contribute to Pacific regionalism, deliver against the CSSF fund-level outcomes, including conflict and instability, maritime security, state and transnational threats and women, peace and security. The programme focussed on six countries in the Pacific: Fiji, Solomon Islands, Vanuatu, Papua New Guinea, Samoa and Tonga.

The programme provided support in four key areas:
1. supporting conflict reduction between communities in the highlands of Papua New Guinea and working alongside international partners to support progress on the post-referendum political process in Bougainville;
2. providing capacity building and support for a range of policing and legal actors, including strengthening regional cooperation on tackling organised crime, alongside leadership training and mentoring;
3. development of resilience in Pacific society in terms of public accountability through anticorruption initiatives and strengthening media capability, and;
4. enabling initiatives which strengthen maritime security in the region, including facilitating progress on maritime boundary submissions to the United Nations, and providing hydrography training.
## Key Results for FY 23/24
- UNDP PNG brokered two local peace agreements in Wapi and Sugu of Kagua Erave in the Southern Highlands and supported women in the highlands who have been victim to Sorcery Accusation Related Violence (SARV) and gender-based violence (GBV).
- The University of the South Pacific convened the inaugural Track 2 Dialogue, convening academics, civil society and officials including PIFS, producing a report for the Forum Subcommittee on Regional Security.
- The South Fiji Basin submission to the UN Commission on the Limits of the Continental Shelf is complete and awaiting approval from Cabinet in Fiji thanks to legal and technical expertise provided by the Pacific Community (SPC) with CSSF funding. This support catalysed progress on the submission after a 16-year process. Two further joint Extended Continental Shelf (ECS) submissions have also been finalised ready for political level approval regarding the North Fiji Basin (Solomon Islands, Fiji and Vanuatu), and on the Melanesian Plateau (Solomon Islands and Fiji).
- UNDP’s pilot project to strengthen links between outer island communities and authorities in Fiji in order to better monitor exclusive economic zones (EEZs) has delivered unexpected results, catalysing close working with Fiji Police on this initiative, and through mapping the maritime security system, helping convene Fiji’s first cross-government Maritime Security Committee.
- BBC Media Action helped the Solomon Islands Media Association establish stringers to help provide information from all provinces in the run up to and after the elections. With UK support, the Solomon Islands Broadcasting Corporation launched ‘Vois Blo Iu’, the first ever public debate shows in the run up to the National General Election, also recorded in multiple provinces and receiving very positive feedback online.
- UNDP Pacific facilitated a number of peer exchanges to help strengthen integrity institutions.
- The programme enabled the UK to strengthen links with police forces across the region and demonstrate partnership with Australia and New Zealand in this space, through the UK College of Policing, INTERPOL and a bilateral project with the Vanuatu Police Force.
## Key Lessons:
- Flexibility and agility were clearly demonstrated by the programme team, but they must be careful not to overstretch themselves and take on unnecessary risk.
- The UK remains a generally respected and trusted partner, with its political neutrality (compared to Australia in particular) and global institutions like the BBC or offerings from the UK College of Policing offering an edge.
- As identified in last year’s Annual Review, a temporary duty to fill the Head of ISF Pacific role would have helped keep the programme moving and avoided the need to rapidly update key programme documents at the same time as signing agreements and mobilising projects.
- Projects designed regionally (e.g. UNDP Pacific Regional Anti-Corruption project) are unlikely to have the desired effect across PICs without national contextualisation. Regional projects should instead be designed as the BBC Media Action work has been, with a one-country pilot first before harvesting learning and building that into a regional expansion.
- Heads of Mission in Very Small Embassies or Posts (VSEPs) are under significant pressure and early engagement on new projects is important.
- Department of Foreign Affairs and Trade (DFAT) Canberra retain ownership of regional programming in the Pacific, including on security and related issues. Relationships with Australia’s Pacific Posts are important, but the programme team should prioritise visiting Canberra, ideally on an annual basis.
- The focus on increased HMG stakeholder engagement in FY23/24 has been successful, with British High Commissioners across the Pacific reporting that the ISF projects are well-understood and valued in their host countries.
- ISF Pacific projects have made a significant difference in terms of political access and influence, helping accelerate relationships between the UK and PICs, including in Posts which only reopened in 2019 (e.g. Vanuatu). It is crucial that progress made in developing relationships, especially with governments, is not compromised; future programming decisions must be handled sensitively. Work with government partners should generally take precedence.
## Key Recommendations for FY 23/24:
- Continue strengthening programme management. Detailed recommendations are at Section G.
- Plan a forward look of visits to ensure relationships are sustained, including visiting key contacts at DFAT in Canberra.
- Consider how to expand the UNDP Maritime Boundaries coastal communities project to other PICs and use this project and the BBC Media Action projects as models for regional expansion.
- Consider partners’ offers when considering project sustainability and exit plans.