CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Philippines Programme
Country and Region	Philippines, Southeast Asia and Pacific Portfolio
Programme ID	C-APC-0003	IATI Unique ID	CSSF-09-000007
Start date	1 April 2023	End date	31 March 2024
HMG Partners / (Lead department in bold)	FCDO
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£13m	£2.45m	£2,448,291.67
Non-ODA	£0	£0	£0
Total	£13m	£2.45m	£2,448,291.67

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Bangsamoro Autonomous Region in Muslim Mindanao (BARMM) officials and political actors are equipped with bespoke technical skills on governance and democratic participation. (Westminster Foundation for Democracy (WFD), United Nations Development Programme (UNDP), The Asia Foundation (TAF)	4
Women and women-led groups are mobilised and acquired skills to participate in policymaking and peacebuilding initiatives. (Catholic Relief Services (CRS) / , UNDP)	4
Enabling environment for the participation of civil society, marginalised and private sectors is strengthened and institutionalised. (UNDP, TAF, CRS)	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Pluralistic, inclusive and effective BARMM systems and policies are developed and enacted.
Bangsamoro Women participate in political and peacebuilding structures, and their voices and perspectives are meaningfully integrated into decision-making.
Engaged and empowered youth, indigenous peoples, persons with disabilities, and other marginalised communities show willingness and confidence to engage with Parliament and elections.
Outcome Assessment	This programme is on track to achieve all three mutually reinforcing outcomes by the programme is due to complete. The election in 2025 is a critical moment. Progress against these outcomes is judged to be enduring against the risk posed by possible political instability associated with this election.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium-High

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	4	Green	4	Green	4	Green
Risk Rating	Medium-High		Medium		Medium-High
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- Continued support to the peace process in the Philippines to reinforce the Philippines’ strategic reorientation of its defence and security resources. (A stable BARMM reduces the need for Philippine armed forces to manage internal conflicts, enabling them to change focus and address external threats, particularly in the South China Sea.)
- Continued support to aspiring women politicians through political leadership and broader empowerment projects that continue to contribute to overall strengthening of Women, Peace and Security (WPS) outcomes in the wider region as evidenced by efforts to localise the WPS Action Plan.
- More broadly, FY 23/24’s focus has reinforced the work of previous financial years, including transforming former combatants into conflict mediators; reintegrating women recruited into violent extremism; and strengthening women solidarity in the region by supporting women organisations.

Project Name	Implementing Partner	Total budget	Duration
Supporting Democratic Stability in the Bangsamoro	Westminster Foundation for Democracy (WFD)	£750, 621.66	June 2022 – March 2025
Advancing Women’s Meaningful Participation and Leadership	UN Development Programme (UNDP)	£370,000.01	June 2023 – March 2024
Promote Active Civic Engagement among marginalised communities vulnerable to radicalisation: / BRIDGE	The Asia Foundation (TAF)	£157,172	August 2023 – March 2024
Promote Active Civic Engagement among marginalised communities vulnerable to radicalisation: / ACTIVATE	The Asia Foundation (TAF)	£543,929	May 2023 –March 2024
Capacity Building for Journalists in the Bangsamoro Autonomous Region of Muslim Mindanao (BARMM)	Asian Institute of Journalism and Communication (AIJC)	£72,041	Oct 2023 – March 2024
Advancing Inclusion and Political Participation of Women in the Bangsamoro, and Advancing Peace in the Bangsamoro Through Empowered and Engaged Citizens	Catholic Relief Services (CRS)	£400,004	May 2023 – March 2024
Developing Inter-Governmental Analysis and Learning for Ongoing Understanding and Engagement with the ICG	Conciliation Resources	£93,109	August 2023 – February 2024

## Key Results for FY 23/24
- CSSF support to the BARMM Transitional Authority (BTA) in reviewing the Electoral Code and drafting and passing a Local Governance Code through the Moro Islamic Liberation Front (MILF)-led Parliament. This commits the parliament to an anti-dynasty provision, indigenous people's representation and a gender quota (30% of nominees must be women) in local development councils.
- Successful advocacy through the UNDP project on the elimination of Moro law that obligates rape survivors to marry the perpetrators.
- Out of 77 aspiring women politicians trained for leadership roles through this CSSF programme, 48 of these won the seats they contested in village-level elections in October 2023, having campaigned on a peace and gender-responsive political platform.
- 62 women associations gained membership of municipal local special bodies.
- 27 grassroots women leaders were appointed to Local Government Units (LGUs).
- Technical and operational support through the programme to help localise, monitor and evaluate the Bangsamoro Regional Action Plan on Women, Peace and Security (WPS) in five of the six BARMM provinces in October 2023.
- A growing network of women mediators and peacebuilders in the BARMM, with 150 women mediators and peacebuilders recruited and trained to date.
- The establishment of the Ranaw Young Women Leaders’ Initiative which supported 20 young women leaders in the BARMM.
- Dedicated guidelines reserving parliamentary seats for representatives from marginalised groups, such as settler communities and religious clerics.
- The establishment of the first Diploma Course on WPS in Southeast Asia; this is being piloted in Mindanao State University (MSU), with plans to expand to other MSU campuses. (51 students enrolled in the first course.)
- Formulation of WPS training modules which will be utilised by BARMM ministries, agencies and offices and local government units.
- The launch of the Bangsamoro Regional Action Plan on Youth Peace and Security, the third of its kind in the world.
- A Bangsamoro Ministry of Education supported curriculum for high school students on the BARMM’s new parliamentary system is now part of the teaching curriculum in BARMM. This is underpinned by the new Bangsamoro Junior Parliamentarian Programme in 14 selected secondary schools.
- Genuinely inclusive programming achieved. The programme tackled structural barriers to the participation of minorities through outreach to rural and island communities, support to inclusive legislative processes which increased the number of parliamentary seats allocated to minorities, including religious leaders, settler communities and indigenous people; support to female political candidates; and engagement with Moro youth.
## Key Lessons:
- This programme is a unique example of where sustained UK involvement, even when the nature of the involvement changes – is not only actively welcomed but valued above that of like-minded partners. Given the role that the UK envisions playing in the world as a conflict prevention and mediation actor, the peace process in BARMM is a prime example of this in action. Relatively modest financial investment sustained political support, and the offer of mentorship, accompaniment and technical advice have combined well, not only in the interest of the peace process, but wider HMG equities in the Philippines related to maritime security, countering terrorism, consular assistance, and UK trade and investment.
- The importance of relationships and relationship building at personal levels should not be underestimated as political capital in the BARMM. This is a context where trust is a necessity for the progression of the peace process, and belief in peace dividends is essential to prevent the use of violence to express grievances. The Annual Review (AR) team saw evidence of programme activities directly and indirectly building trust and resilience; this is critical ahead of parliamentary elections in the BAARM in May 2025.
- Related to this, the programme has demonstrated what high-level, sustained support can deliver in strengthening bilateral diplomatic relations. As the ISF Peace Processes evaluative report which covers the Philippines points out, leveraging senior UK political figures as peace advocates, like Lord Jack McConnell, showcases the UK’s ability to act as a global influencer in the peace process space.
- The programme exemplifies a comprehensive approach to achieving a WPS outcome. Often, interventions on increasing women’s participation only target women’s capacity and/or confidence, narrowly assuming this is the cause of their exclusion. Projects within this programme helped to ensure that women in political and community leadership positions were being supported with skills training. However, targeting men in the BARMM parliament to achieve attitude and behavioural change is key. The programme team and implementing partners recognise they can go even further in designing a comprehensive WPS programme, for instance, by integrating economic support, should related interventions be permitted and funds made available.
- There are opportunities for the UK to burnish its peace process credentials internationally, by sharing what we have learned through our support to this peace process since 2009 with other countries, for example, Papua New Guinea and the Solomon Islands, officials of which were in Cotabato City recently for learning exchanges on the Philippines peace process. In time, we could also look to share lessons on the Philippines “normalisation track”. This track, which represents a departure from standard disarmament, demobilization, and reintegration (DDR) / security sector reform (SSR) approaches by setting out new security arrangements that combine measures to decommission and disarm the MILF as part of an overall effort to reduce threats, presents the ISF with an opportunity to contribute to the implementation of a DDR process that goes beyond insurgency disarmament and showcases the importance of effective security transitions in peace agreements.
- As the September 2024 ISF peace process evaluative study notes, the CSSF Philippines programme has helped to enhance UK political access and influence through close integration between programmatic and political teams. Combined with the UK’s seat on the UNSC and a pool of experienced peace process experts, this provides the basis from which the ISF could leverage its track record, and position itself as a global influencer in this area.

Key Recommendations for FY 23/24:
Strategic:
- Update the programme narrative. Given the transition from CSSF to ISF and the increased focus on countering state and transnational threats, the programme team should ensure they have a compelling and updated narrative that accounts for how and why continued engagement in the BARMM is strategically relevant to HMG interests in mitigating threats from state actors, especially in the South China Sea (SCS).
- Going forward, consider better utilising a WPS headline for the programme, rather than implementation of a peace process. The ISF has a mandate to implement the UK’s National Action Plan on Women, Peace and Security and this continues to be explicitly referenced in the Fund’s Strategic Framework. Given the high quality of gender mainstreaming in the programme, this could be a more useful framing and justification for the programme in addition to narrative on threats, in future years.
- Focus diplomacy and programming on normalisation: A reluctance by ex-combatants to disarm and by the Government of the Philippines to grant amnesties could lead to frustrated expectations and a return to violence. Continued investment in normalisation related interventions and sustained lobbying for accelerated normalisation could reduce the risk of radicalisation and the reanimation of armed groups
- Maintain geographic focus. With limited resource and years of investment and relationship building, there is a case for maintaining a programmatic focus on BARMM only, rather than spreading UK efforts too thinly across the balance of the country. Retaining a BARMM focus will enable the UK to maximise its unique offer and position in the BARMM, and allow the ISF programme to broaden its thematic focus to additional security threats that blight the BARMM, such as gender inequality, climate change and transnational organised crime.
- Work with implementing partners to develop exit strategies. It was clear from interviews that most partners were not ready to close technical advisory support provision and activities (and were in the process of planning new activities) for projects that had achieved their objectives (voter education and registration, civic engagement activity), despite knowing that the programme ends in March 2025. The AR for FY22/23 recommended an embassy-led discussion on an exit strategy; this continues to be timely not only because of the upcoming BARMM elections, but also because of pressure on the ISF ODA budget. The AR team recommends that this is prioritised.

Operational:
- Tackle wasteful duplication. Two implementing partners used HMG funding through their projects to provide journalists in the BARMM with protective equipment to enable them to perform their roles safely. Similarly, WFD and TAF both train journalists through their projects. Going forward, the programme team should remain vigilant in checking for duplication across projects, optimise synergies between projects, and model implementing partners’ efforts (Catholic Relief Service, The Asia Foundation) in deconflicting and preventing duplication in areas like voter education.
- Work more closely together with the CT team in recognition of mutual priorities. There are close links between the priorities and work of both teams. The successes that the programme has generated, including the successful reintegration of women ex MILF combatants into BARMM communities and CSSF-trained women mediators standing down six Daesh fighters in the BARMM are helping to advance Counter-terrorism strategy (CONTEST) outcomes. Regular (weekly/fortnightly) exchanges of information, intelligence and ideas between both teams could progress Counter-terrorism (CT), peace and WPS agendas. The CT team made clear their interest in learning from the programme team on what worked in women leadership programmes, with the ambition of exporting their women policing leadership programme to Mindanao. Given restrictions on travel to the BARMM, they also relied on the programme team to give them ground truth on conditions there.
- Reflect causal links between internal and external security: Wrapping CT, Cyber and Maritime security into a more developed Theory of Change could help to demonstrate and track the links between internal and external security. This Theory of Change could act as a forcing mechanism in driving internal coherence.
- Maximise the programme’s convening power. At a Monitoring, Evaluation and Learning (MEL) session in Cotabato City at which all implementing partners were present, a few made a point of asking to be joined up with others being funded by the programme in the recognition that they shared objectives and were running complementary activities. To ensure synergies between programmes are optimised, the programme team should make a conscious effort to bring together project leads outside of MEL sessions.
- Share conflict analysis. Given the criticality of ensuring that interventions cause no harm, and the importance of a common understanding of the evolution of drivers, sharing analytical products between partners and the programme team is to be encouraged. The programme team should look to share / present an official version of the BARMM focused conflict analysis currently being finalised to ensure that programming keeps up with and responds directly to evolving drivers.
- Consider introducing conflict sensitivity and conflict context indicators to help assess conflict trends and trajectories and risks to the peace process in what remains a dynamic conflict context. The introduction of conflict sensitivity indicators could aid monitoring the trajectory of the conflict there, and conflict related risks to the peace process. A conflict sensitivity audit over the next 12 months could also help to dive deeper into Implementing Partners’ approaches to conflict sensitivity in what is a politically febrile context ahead and post the 2025 regional election.
- If possible, consider contracting and using third party monitors to validate results. Recognising BARMM’s fragility and the programme team’s inability to make frequent visits to the region because of security risks, independent MEL practitioners based in/able to access the BARMM more regularly will give the programme team the necessary confidence that the programme is delivering outputs as forecast.
- Consider consortia for complementary projects and sign multi-year grants where appropriate. This will help to minimise delays in dispersing funds at the start of each financial year and provide implementing partners with greater ability to plan. Consortia can help to reduce duplication of activities while bringing together necessary capabilities of different implementing partners.
- Ensure board meetings are routinely used to discuss programme management fundamentals. Board meeting minutes did not record any discussion on risk management and conflict sensitivity, for example.