CSSF Annual Review (2023/24)
# A. Summary Sheet
# This summary sheet will be published on GOV.UK. It should be limited to 2-4 pages and be written for a public audience that may not be familiar with the language of programme management and CSSF in particular.
Programme Title	Southeast Asia Maritime Security Programme
Country and Region	Southeast Asia with five priority countries (Brunei, Malaysia, Indonesia, Vietnam, Philippines) but also including other Association of Southeast Asian Nations (ASEAN) member states (Laos, Thailand, Singapore, Cambodia)
Programme ID	C-APC-0004	IATI Unique ID	CSSF-15-000001
Start date	April 2022	End date	March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth & Development Office (FCDO), Department for Transport (DfT), Ministry of Defence (MOD), Department for Environment, Food and Rural Affairs (Defra), UK Hydrographic Office, UK Meteorological Office, HM Coastguard, Joint Maritime Security Centre (JMSC)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£5,050,000	£1,800,000	£610,825
Non-ODA	£1,500,000	£500, 000	£655,775
Total	£6,550,000	£2,300,000	£1,266,560

## Outputs
Output statements	Individual Output Rating
(Number and statement)
Increased commitment to the UN Convention on the Law of the Sea (UNCLOS) by key operational and policy stakeholders	1
UK access to credible partners enhanced expanding pool of stakeholders that share and can support UK values	1
Enhanced knowledge of Illegal, Unreported and Unregulated (IUU) fishing delivers improved national and regional frameworks for cooperation to tackle IUU in SE Asia	1
Leveraging Japan’s regional influence, engagement with other national coastguards is demonstrated	1
National hydrographic and meteorological staff are recognised as integral to maritime security and have the opportunity to contribute their expertise to national strategy and operations	1
National Maritime Domian Awareness (MDA) capabilities have increased and there is greater evidence to inform national and regional objectives	1
Overall Rating of Output Delivery	1

## Outcomes
Outcome statement(s)
Regional partners work together improving collective resistance to coercion and illegal maritime activity, through adherence to Law of the Sea, and promote the RBIS leading to better and sustainable management of marine resources.
Improved MDA of ASEAN partners and respect for international rules-based systems encourages diplomatic settlements of disputes, in line with maritime law, and more effective maritime security responses.
UK seen in region as an active partner for maritime security improving the UK’s soft power.
Outcome Assessment	While the programme supported some activities in this financial year (2023-24), the Annual Review team (ART) could not assess the outcomes due the incomplete results framework. In the absence of a comprehensive results framework, Monitoring, Evaluation and Learning (MEL) plan and a live risk register, the Programme is at a high risk of failing even if it succeeds in delivering the current strands of planned activities. With six-months remaining, it is difficult to assess if the programme would be able to deliver the desired changes at the outcome level by the end of the programme cycle. The results framework should be designed and completed immediately and other documents like the risk register and MEL plan should also be completed immediately to ensure that the Programme Completion Report (PCR) next year is able to assess the outcomes and outputs and capture the success of the programme effectively.
Overall Outcome Progress Rating:		Red
Overall Risk Rating:		Major

## Summary of Programme Performance
Year	2022/23		2023/24		2024/25
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	2	n/a	1	Red
Risk Rating	Medium		Major
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
The SE Asia Maritime Security Programme aims to ensure a more secure, prosperous and sustainable maritime domain in SE Asia. The programme supports the UK’s continued long-term commitment to the Indo-Pacific, and to build and strengthen modern partnerships with allies and regional powers to ensure a free and open Indo-Pacific, whilst building upon current UK expertise and capability in the maritime security context. It seeks to develop relationships and partnerships in the region, including with likeminded partners leveraging UK soft power, using Illegal, Unreported and Unregulated (IUU) fishing, coastguard capability development and the UK Hydrographic Office as credible entry points for engagement on regional maritime concerns.
In this financial year (2023-24), the programme supported the following projects:
- Maritime Security Symposium – led cross His Majesty’s Government (x-HMG).
- International Foundation for the Law of the Sea Summer Academy 2023 – led by International Foundation for the Law of the Sea (IFLOS)/University of Hamburg.
- MDA Assessments for Philippines and Vietnam.
- HM Coastguard Relationship Building – led by HM Coastguard
- Exclusive Economic Zone (EEZ) Course – led by Royal Navy.
The following projects also commenced in the financial year under review, but the activities either were in preparatory phase or didn’t fully start until the beginning of the next financial year.
- Research and Modelling of Future Shelf Sea Conditions on the Sunda Shelf – led by UK Meteorological Office. This project focusses on the impact of sea surface temperature change on migratory fish stocks, mangrove swamps and sea grasses (latter broadened to include coral bleaching).
- Hydrographic Leadership Programme – led by the UK Hydrographic Office.
- Building Capacity to Tackle IUU Fishing in the Philippines – led by Global Fishing Watch / Joint Analytical Cell.
- Preventing Crises and Escalation in the South China Sea (SCS) – led by the Centre for Humanitarian Dialogue.
Other activities under this programme included:
- x-HMG Southeast Asia Maritime Security Workshop in Singapore which brought together 40+ participants to discuss and develop the UK’s maritime security offer in the region.
- a Center for Naval Analysis tabletop exercise to develop greater understanding of Illegal, Unreported and Unregulated fishing.
- support for a strong x-HMG presence at the US Coastguard led Exercise Southeast Asia Cooperation and Training (SEACAT) event in Singapore, attended by over 200 regional maritime security practitioners, showcasing the UK’s ‘whole of Government’ approach to Maritime Domain Awareness and was welcomed by the organisers as an exemplar of good practice
- a UK Department for Transport Port Security ‘train the trainers’ workshop in Vietnam following a direct request for assistance from the Vietnamese government. An immediate outcome of the workshop was additional training being delivered to 17 Vietnamese Port Facility Security Officers (as designated under the International Ship and Port Facility Security (ISPS)). Longer-term outcomes include further training of other Vietnamese PFSOs and an increase in security at Vietnam’s other international ports. A further training visit is envisaged for FY 2024-25.
- the Diplomatic Academy of Vietnam’s annual high-level South China Sea Conference during which the then FCDO Minister delivered a keynote speech on the global importance of the South China Sea. The UK funding as part of the overall conference package helped build and develop stronger relationship with the Diplomatic Academy of Vietnam (DAV) and other Vietnamese departments and agencies. It has helped ensure Vietnam retains a positive view of UK’s maritime security interventions. This has been backed up and evidenced by comments from senior officials, the access given to the visiting MDA team in January 2024 and by the DAV inviting an FCDO Minister to give the keynote speech again this year - therefore providing a platform for the UK to set out clearly its interests in the region and policy on the South China Sea.
## Key Results for FY 23/24

During FY 2023-24, the Southeast Asia Maritime Security Programme achieved some positive results, which include:

- The relationship building project led by HM Coastguard (HMCG) further strengthened HM Coastguard’s relationship with the Japanese Coastguard, which paved the way to secure UK observer status at the Heads of ASEAN Coastguards meeting for the first time, enabling UK observation of, and input into, regional coastguard-related developments. HMCG is now working with the Joint Maritime Security Centre (JMSC) to enable permanent one-HMG representation in the region, thereby ensuring the UK is well-informed of regional dynamics and is well-placed to develop future cooperation interventions eg on search and rescue. It delivers against the programme’s line of effort to build relationships and partnerships.
- The Royal Navy-led Exclusive Economic Zone Course on UNCLOS brought together 30 regional maritime security practitioners from seven countries allowing HMG to strengthen relationships and commitment to joint working on regional maritime security issues with key participants.
- The Maritime Security Symposium brought together over 60 regional maritime security practitioners from four countries to strengthen and build relationships and raise awareness, understanding and capability in support and defence of UNCLOS.
- Support for a Biodiversity Beyond National Jurisdictions (BBNJ) conference hosted by Philippines following the opening for signature of the BBNJ Agreement at UNGA in September 2023 - the UK was an early signatory demonstrating commitment to supporting a secure and resilient ocean.
## Key Recommendations for FY 23/24:
- R1. Programme Documents: The programme has been marked as red which means that ‘Portfolio Board (should be) informed within 1 month (of this review) to facilitate discussion on improvements or the continuation of the programme.’ By the end of November, key programme documents including results framework, risk register and MEL plan should be completed and approved by the Programme Senior Responsible Officer (SRO) and the relevant two-star board on an urgent basis.
- R2. Programme Board: Ensure the programme board meets quarterly (as a minimum) in line with the ISF governance requirements and performs its assurance, oversight and accountability functions effectively. The programme board should approve all programme-related documents, including programme document, results framework and risk register before any spending commitments are made. The risk register should be regularly updated and presented to the board on a quarterly basis. The board should ensure stronger scrutiny of finances and escalate critical issues to the two-star board.
- R3. Threat analysis: To ensure evidence-based decision making on future projects and activities and drive prioritisation, commission a threat analysis by end of October to understand the threat in the region and where possible use country specific Joint Analysis of Conflict and Stability (JACS) to design future activities.
- R4. Coordination, coherence and collaborative working: To further refine activity engage and collaborate with like-minded partners frequently and explore sharing products and readouts where appropriate with close diplomatic allies to amplify impact and avoid duplication of effort by making best use of the UK’s niche expertise.
- R5. Baseline: Drawing on the threat analysis and county specific JACS, review the ongoing programme activities and ensure they address threats to the UK and are aligned with ISF principles and HMG’s objectives in the region. Consider baselining some programmes to FCDO or asses if they are ‘fit-for-purpose’ for a high-risk programme in a high-risk region.
- R6. Gender: The Programme Manager to submit a gender equality problem statement programme objective to the programme board for approval. Once agreed, ensure this is shared with implementing partners, both current and prospective. In addition, accelerate timeline for procurement of Gender Equality and Social Inclusion (GESI) E project, with the aim to sign a contract by end of December 2024.