CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Counter Supply of Illicit Commodities Programme (COSIC)
Country and Region	Global / Africa: Kenya, Mozambique, Nigeria, South Africa / Americas: Brazil, Colombia, Dominican Republic, Ecuador, Guyana, Panama, Peru / Eurasia: Afghanistan, Azerbaijan, Pakistan, Turkey / Europe: Bulgaria, Greece, Hungary, Poland, Romania, Slovakia
Programme ID	C-SOC-0008	IATI Unique ID	CSSF-12-000006
Start date	1st April 2021	End date	31st March 2025
HMG Partners / (Lead department in bold)	Home Office, Foreign Commonwealth and Development Office, National Crime Agency, Joint Narcotics Analysis Centre
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£12,380,000	£4,090,000	£3,628,077.17
Non-ODA	£2,555,000	£900,000	£493,606.85
Total	£14,935,000	£4,990,000	£4,121,684.02

## Outputs
Outputs	Individual Output Rating
Home Office Liaison Officer (HOIO) – Asia	Unrated
HOIO – Africa	Unrated
HOIO - Americas	Unrated
Home Office – Reduction of Firearms Threat to the UK	4
UN Office on Drugs and Crime (UNODC) – Combatting Serious and Organised Crime (SOC) from Afghanistan	Unrated
SOC Network (SOCnet) – Countering the flow of illicit cash	4
Joint Narcotic Analysis Centre (JNAC) – Crystal Methamphetamine Analysis Project	3
Border Force – Artificial Intelligence	Unrated
Overall Rating of Output Delivery	Unrated

## Outcomes
Outcome statement(s)
HMG and partner countries increase operational-level cooperation and intelligence sharing to undermine priority supply chains
Source and transit countries are able to disrupt priority supply chains
Societal demand for change creates momentum for anti-trafficking solutions
Outcome Assessment	The COSIC Programme has contributed to the capacity of international partners in key countries and has enjoyed notable successes in preventing or inhibiting the flow of narcotics, firearms and illicit cash to the UK. This headline, however, belies serious issues with the governance and management of the programme. Basic processes and procedures have not been followed with the result that it is impossible to assess how effective many of these measures have been, risks have not been adequately managed and gender equality has been neglected. One of the programme’s three outcomes appears to have had no resources allocated to it at all. This is the second year running that the Annual Review has raised many of these issues. A mitigation strategy is in place and there is evidence of significant improvement. This should be carefully monitored by the Senior Responsible Officer (SRO).
Overall Outcome Progress Rating:		Amber-Red
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	No score assigned	Green	4	Green	-	Amber-Red
Risk Rating	M		M		M

## What Support Did the UK Provide in FY 23/24?
- A wide range of interventions to reduce border security vulnerabilities and improve intelligence and data sharing at specific points in distribution chains and in priority countries worldwide.
- A project to reduce the flow of firearms from Türkiye and identify threats from 3D printing technology.
- Funding to analyse the flow of illicit commodities including new research into Crystal Methamphetamine from Afghanistan.
- A pilot project to achieve political, cultural and legislative change to promote seizures of illicit cash across central and southern Europe.
## Key Results for FY 23/24
- Supported the construction of a Türkiye-Syria border wall system that has reduced illegal crossings by 90%, led to the seizure of 500kgs of Class A drugs, the dismantling of two Organised Criminal Groups (OCGs) and the destruction of three chemical labs.
- The introduction of new firearms legislation in Türkiye has led to destruction of 400,000 weapons.
- The introduction of legislation similar to the Proceeds of Crime Act in Bulgaria which has strengthened anti-money laundering measures.
## Key Lessons:
- Infrastructure projects must ensure that construction specific project and financial management risks are properly mitigated and should be subject to SRO level scrutiny prior to approval.
- Activity to deliver societal change in partner countries remains largely aspirational. Strategic objectives need to be adjusted or more activity aligned with this outcome if it is to be effective.
- Programme Management needs to be adequately resourced and appropriately overseen by the board and SRO.
- Gender mainstreaming is not apparent and suggested improvements to the Monitoring, Evaluation and Learning (MEL) structure of the programme have not been successfully implemented.
## Key Recommendations for FY 23/24:
- Programme Boards should have a broader remit. They should ensure that they interrogate programme progress towards objectives, actively address risks and support programme management.
- Gender equality needs to be prioritised and driven forward by the SRO. A root and branch gender evaluation are required to understand how a gender lens should be applied to countering the smuggling of illicit commodities.
- Continue to implement programme management reforms and check that they have been effective.