CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Western Balkans Serious and Organised Crime CSSF Programme
Country and Region	Western Balkans - (Albania [ALB], Bosnia & Herzegovina [BiH], Kosovo [KOS], Montenegro [MNE], North Macedonia [MKD], Serbia [SRB] – WB6) and the UK
Programme ID	C-WBK-0004	IATI Unique ID	CSSF-10-000004
Start date	1 April 2023	End date	31 March 2024
HMG Partners / (Lead department in bold)	Home Office (HO), Foreign, Commonwealth & Development Office (FCDO), His Majesty’s Revenue & Customs (HMRC)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£28,300,000	£10,400,000	£10,426,190
Non-ODA	£2,900,000	£800,000	£678,097
Total	£31,200,000	£11,200,000	£11,104,287

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Combating corruption and organised crime in the Western Balkans through strengthening regional cooperation in asset recovery. (Regional)	4
Strengthen BiH judiciary to secure independence and effective fight against corruption and SOC. (AIRE2) (Regional)	4
Building Resilience against SOC in Albania through investigative journalism.	4
Support civil society to increase public oversight and accountability of Kosovo public institutions.	4
Prevent illicit financial flows through strengthening the supervisory role of the Central Bank and Financial Intelligence Unit of Kosovo towards financial institutions.	4
Intelligence-led approach to safer prison management in North Macedonia.	4
Strengthen Intelligence Led Policing and support establishment of special joint investigation teams against illicit finance and organised crime in Kosovo	3 (Project only began late Q4 (2 wks))
SOCnet Illicit Finance Policy Lead. (only started in Q4)	3 (Project not commenced in Q4)
The Observatory of Illicit Economies in South-Eastern Europe. (SEE Obs): Phase 5 Global Initiative (Regional).	4
Countering Organised Crime in the Western Balkans/HMRC Women in Uniform. (Regional).	4
Multi Modal Target Hardening, Intelligence Capture and Border Control in the Western Balkans. (Regional -not Serbia)	4
UNODC: Illicit Finance/Anti-Corruption Roadmap. (Regional).	4
Crime State Nexus. (Albania)	4
Western Balkans Rule of Law Initiative. (Chemonics) (Regional)	4
Support to Albanian Criminal Justice System in the field of Foreign Science.	4
Overall Rating of Output Delivery	Green

## Outcomes
Outcome statement(s)
Reducing the ability of Western Balkan (WB) linked OCG’s (Organised Crime Groups) to launder criminal proceeds (both in the UK and the region) – this will seek to weaken the WB OCG’s illicit finance (IF) critical capabilities (laundering (ML) criminal proceeds and remittance).
Increase financial and political costs for WB politically exposed persons (PEPs) with links to OCG’s – this will weaken the WB OCG’s safe haven critical capability, which allows them to act with impunity, as well as targeting enablers of another critical capability, which is their ability to transport and distribute illicit commodities.
Reducing WB OCGs’ ability to profit from illicit commodities by disrupting their ability to traffic the most profitable commodities. - this will weaken the WB OCGs.
Outcome Assessment	Outcome 1: The programme delivered illicit finance assessments to identify intervention points and fill intelligence gaps, while continuing to increase the capacity of prosecutors and financial experts across the WB6 to successfully conduct financial investigations and asset recovery, including by improving intelligence and forensic capabilities, in areas most likely to yield results based on feedback from posts. At regional and political level, this was backed by ongoing work through the Berlin Process to deliver coordinated action to counter IF/ML and corruption. / Outcome 2: The programme invested in developing targeted sanctions against PEPs in Albania. It supported local institutions to improve the effectiveness and accountability of the judicial system in responding to SOC and impunity through targeted engagement with key institutions and public officials addressing weaknesses in the implementation of justice. These activities were complemented by projects that support civil society and media, expose PEP linkages with OCGs, and advocate for change to reduce the space for OCG influence on PEPs and government officials. Information gaps in understanding the effectiveness of sanctions in the WB and integrity of criminal justice institutions in dealing with high level cases of SOC were explored. Multi-country projects took a bespoke approach to deliver country specific and agile interventions responding to the need for a local context to improve transparency in judiciary e.g. KOS, MNE, BiH, criminal case building and management systems MKD, MNE, and fostering cross-border cooperation between WB6 prosecutors. / Outcome 3: The programme developed specialist units within Passenger targeting (PIU), Maritime Targeting/ Intelligence and land border monitoring capabilities, alongside expertise in the interdiction of concealments in border environments and the identification suspect behaviour as well as insider threat provides the tools to law enforcement to enhance intelligence pictures by increased seizures of illicit commodities. Further investment delivered bespoke training for key intelligence institutions across KOS and MKD to increase their ability to gather reliable evidence on priority subjects involved in SOC.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	-	Amber	3/4	Green/ / Amber	4	Green
Risk Rating		Medium		Medium	Medium	Medium
Communication between the programme team, implementing partners and overseas posts has considerably improved from the previous reporting period. This is down to a very positive and committed programme team and their ability to go the extra yard, and increased capacity, due to the recruitment of a second programme manager. There has been without exception only praise for the WB SOC programme team throughout this review. Their work has focused on developing SOC pathways for each of the WB6 and developing country specific objectives for the programme. The strategic outcomes underpinned by complementary projects has ensured that the programme fully supports UK policy utilising a true xHMG approach. The policy-programme alignment has improved with the refreshed HO WB OCG campaign. This has resulted in strengthening complementarity with other WB programmes and portfolios such as CSSF Migration and Global SOC to maximise impact. Monitoring, Evaluation and Learning (MEL) processes have been enhanced with a stronger focus on stakeholder engagement. This contributes to the xHMG SOC evidence base supporting programme level decision making and learning. Depth of understanding has been provided by using change stories to convey how outputs have been evidenced in outcomes. Following last year’s annual review the Gender Equality and Social Inclusion (GESI) approach to programming has been addressed and it is now fully compliant with CSSF recommendations. The programme is by necessity agile responding to the political and economic instability of the region. The programme team are alive to piloting novel approaches which will support other projects and lead to measurable outcomes such as the JIT project in Kosovo. The approach strengthens the connectivity of the projects in this programme to achieve stated outcomes.

## What Support Did the UK Provide in FY 23/24?
- UK provided support coordinated with other donors maximising outcomes for the benefit of WB6.
- UK developed conversation between regional prosecutors leading to shared vision including the exchange of country owned solutions (MNE) with neighbouring jurisdictions (BiH).
- UK facilitated a wider relationship between S America and Montenegro for global solutions.
Key Results for FY 23/24
- A comprehensive review of evidence relating to WB SOC illicit finance initiated that provided HMG with a holistic evidence based upon which further intervention points were identified.
- Translation of Mutual Legal Assistance (MLA) guidance into WB languages delivered, thus improving WB institution’s ability to draft and submit high quality and compliant MLA requests to the UK. As a result, a higher number of Mutual Legal Assistance (MLA) requests were successfully and timely responded to by the UK and evidence was used during criminal justice proceedings in the WB.
- Disruptive action to exclude several Albanian political figures with ties to criminality and corruption from the UK.
- Built cooperation across law enforcement and defence to assist servicewomen and promote gender equality through a “Women in Uniform” project (drawing attention to the factors stopping women progressing and broadening their experience and progression prospects).
- Established a Regional Maritime Training Centre of Excellence in Montenegro enabling interdictions of people smuggling in Montenegrin waters, and helping enforce sanctions on Russian-owned vessels.
- Supported Montenegro Chief Special Prosecutor (CSP) which led to the arrest of a senior police officer on suspicion of being part of an Organised Crime Group.
- FCLO Podgorica and CSP relationship further positively developed by operational support provided in identifying a new Modus Operandi, previously unknown. Resulting in a large-scale operation and investigations into a significant persons, including Senior Public Officials.
111m cigarettes, with (RLP) value of circa £49million seized reported by project
Supported the introduction of new laws in KOS that make money laundering a stand-alone criminal offence. This was a joint achievement resulting from SOC and FRP projects.
- The seizure of 1.4 tonnes of cocaine in Montenegro, the largest in the country, as a direct result of HOIO support to local law enforcement in FY22/23 catalysed increased support to target harden the Port of Bar.
- Operation Claudius II. Joint Operation between the Customs Administrations of the Western Balkans 6 with HMRC as Operational Control, resulting in multiple seizures of; class A drugs, tobacco, forged documentation and approximately £200,000 in cash, and sharing of intelligence between all six administrations.
## Key Lessons:
- Data Protection Impact Assessments (DPIAs) aid the timely exchange of intelligence. They should be used to ensure the sharing of DNA, fingerprint, criminal records is supported with UK intelligence and financial requests effectively and in a time critical way.
- Communication and regular engagement with implementing partners including monitoring visits and attendance at key events are vital for successful programming upstream. However the current approach could be even further improved through realignment.
- Recipients want more tangible engagement such as mentoring and not merely an extension of 20 years’ worth of training and conferences.
- SOCnet needs authority to carry out its role. It is the glue between policy, programming and operations and should be recognised in operational implementing partner tasking processes.
- JSOC in posts would benefit from a closer engagement with programmes to ensure they can deliver both short term and medium term solutions.
- The only way to identify a UK link for transnational organised crime is to start the intelligence gathering in the UK and deliver it upstream for action. Using hardened secure communications (HRD) evidence will lead to operational successes building on capacity building.
## Key Recommendations for FY 23/24:
- The programme should be aligned thematically as opposed to geographically for maximum effect. The WB SOC projects should be transitioned into a WB OCG programme. This will have an end-to-end mandate as per CSSF priority. Other projects more akin to corruption and illicit financial flows within WB6 can then be placed in the Democratic Empowerment Programme (DEP), or similar which will provide more flexibility in country for HMA’s. This needs to be sensitively handled so no projects are “lost in the cracks” in the change of programme and funding stream.
- The programme should consider whether having a separate SRO for the programme that does not simultaneously oversee departmental HO policy would support better scrutiny and oversight of the programme and objectively oversee xHMG priorities in the spirit of the CSSF. This will allow the programme to better fulfil its mandate and enable it to respond more effectively to xHMG SOC priorities. It would be beneficial to explore what other thematic portfolios have implemented to ensure consistency across the CSSF.
- To comply with CSSF priorities of domestic to international more non-ODA funding should be earmarked for addressing WB OCG’s. Current funding of ODA should not be reduced to achieve this in recognition that WB6 is a high priority in numerous UK strategy documents. NCA/ROCU/Police need to be more engaged in mapping the UK WB OCG environment.
- The use of DPIAs by HOIO should be assessed and if appropriate recommended for wider rollout with operational partners to ensure upstream intelligence sharing is more effective and timely to deal with UK priority issues such as illegal migration (small boats) and cannabis importation.
- Hardened Secure Coms decryption should be fully exploited and supported in FY24/25 to establish the UK link to WB OCGs. The JIT approach being established in projects such as with prosecutors and police across the WB6, and the wider global reach of a realigned programme can use this evidence to benchmark progress.
- The MLA system and FIU timescales to be reviewed and prioritised in UK to assure all stakeholders that a timely response to financial requests is reciprocated between WB6 and UK. This will include monitoring the frequency and quality of requests from UK to WB6 which anecdotally appears to be infrequent.