Annual Review (2022/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Ukraine Programme
Programme ID	C-EEA-0005
Country and Region	Ukraine, Eastern Europe, and Central Asia (EECAD)
IATI Unique ID	CSSF-05-000004
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MOD), Her Majesty’s Revenue and Customs (HMRC), National Crime Agency (NCA)
Total Budget	ODA: £40,697,000	Non-ODA: £10,557,000
Budget this FY	ODA: £40,697,000	Non-ODA: £10,557,000
Spend this FY	ODA: £40,120,833	Non-ODA: £10,925,025
Time Frame	Start Date: April 2022	End Date: March 2023

NB: An overall output score has been given for each thematic ‘pillar’ as individual outputs are too numerous and derived from project results frameworks.

Pillar Outputs	Pillar Output Rating
Stabilisation and early recovery	3.5
Gender inequality and Women, Peace, and Security	3.5
War crimes, accountability, and human rights	4
Security and Defence	2
Overall (weighted) Rating of Output Delivery	3.2

Pillar Outcome Assessment	Stabilisation – Amber/Green / Gender Inequality and Women Peace and Security (WPS) – Amber/Green / War Crimes, Accountability, and Human Rights - Green / Security and Defence - Amber/Red
Overall (weighted) Outcome Progress Rating:		Amber/Green
Overall Risk Rating:		High

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	4 (A)	Amber	3.84 (A-)	Green	3.23	Amber/Green
Risk Rating	Medium/High		Medium/High (Pre-invasion)		High
Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?

The core of the FY 22/23 CSSF Programme aimed to respond to Russian aggression, provide emergency support to the government of Ukraine and communities, support the most disproportionately affected and vulnerable groups, and start to lay the groundwork for inclusive post-war recovery. In FY 22/23, the UK government provided over £50m of support across four pillars of effort.

The CSSF is a cross-government funding mechanism accessed by a range of HMG departments to run programmes. CSSF uses ODA and non-ODA for work focused on conflict & stabilisation, women peace and security, and countering state threats and transnational threats. The CSSF Ukraine programme scaled up rapidly during FY 22/23 to reflect new needs and priorities following the full-scale Russian invasion in February 2022.

The programme responded to full scale invasion as follows:
- Temporarily extended some humanitarian components until a more substantial humanitarian response could be set up;
- Scaled up and adapted civilian stabilisation efforts to the new context;
- Expanded and re-focused defence reform activity;
- Continued non-lethal (medical) military training;
- Adapted Women, Peace and Security (WPS) interventions to the war-time context and associated threats;
- Activated grants to Ukrainian civil society organisations (CSOs) to allow them to adapt and continue to operate;
- Refocused strategic communications efforts, and
- Designed and delivered a new War Crimes Accountability pillar, given the need to build capacity in this new area for Ukraine, to underpin Ukraine’s future societal resilience and further HMG’s objective to hold Russia to account.

Sample of Key Results per Pillar for FY 22/23

Stabilisation and Early Recovery
UK leadership leveraged five co-donors' financing to secure a collective uplift of £55m (to £90m) to our flagship stabilisation programme, Partnership Fund for a Resilient Ukraine (PFRU) to manage new stabilisation challenges driven by the full-scale invasion and subsequent liberation of territories, unrelenting hostilities, widespread displacement, and the onset of winter amidst attacks on the critical infrastructure. PFRU worked across Kyiv, Chernihiv, Sumy, Kharkiv and Kherson to bring communities together with their administrations to address immediate priorities and put them on the road to recovery. Over 126 rapid recovery projects in more than 24 hromadas were launched in 2022. Among many achievements, this enabled more than 5,000 children to return to school and provided more than 100,000 individuals and families with renewed access to healthcare, power, and water supplies.

Gender Inequality and Women, Peace & Security
- United Nations Population Fund’s (UNFPA) work under the Enhancing National and Regional Mechanisms to Build Responsive, Accountable and Cost-Effective System of Gender-Based Violence (EMBRACE) project has enabled key political actors in Ukraine to prioritise establishing and maintaining safe spaces for women and girls. Buy-in from state authorities secured through the project has led to creation of centres as safe spaces for Gender Based Violence (GBV) and Conflict Related Sexual Violence survivors including allocations of funding in state budgets. This includes twenty shelters for GBV survivors, thirteen day-care centres, seven crisis rooms across different regions of Ukraine and a range of services to provide complex specialised support to women and girls.
- During 22/23 we established the Civil Society Grant Fund, which provided support to 94 CSOs under the Emergency Grant Window, to strengthen their capacity, capability and resilience to meet the evolving wartime, humanitarian and other pressing needs, including relocation of CSOs from the newly occupied or heavily shelled regions and work to advance gender equality and social inclusion (GESI).

War Crimes Accountability and Rights Violations
CSSF programming provided training and advisory support to the Ukrainian Office of the Prosecutor General (OPG) related to the several aspects of war crimes accountability. Through Global Rights Compliance (GRC) it supported the development of a War Crimes Strategy, enabling the OPG to identify and build the experience and expertise they need for more complex and comprehensive investigations, identifying high-level suspects for war crimes (including conflict-related sexual violence - CRSV) committed in Ukraine, and to retrieve and preserve high-quality evidence to links them to the crimes. Advisory support on handling prosecutions involving CRSV and crimes against children promoted a survivor-centred approach and led to a CRSV Action Plan to institutionalise good practice and structures across investigation and prosecution. CSSF Ukraine provided training and mentoring to the National Police of Ukraine (NPU) and Ukraine’s judiciary on war crimes investigations and case management.

Security and Defence
Defence Reform technical expertise supported Ukrainian MOD the creation of two new Defence Procurement Agencies to reduce opportunities for corruption and non-transparent procurement processes, as well as the re-start and growth of the Building Integrity, Transparency and Ending Corruption (BITEC) school of the National Defence University.

Key Lessons

- During wartime, investment needs to be in those areas that the Government of Ukraine (GoU) sees as essential for state survival. The alignment with HMG strategic priorities may not be immediately apparent in the early stages of projects but where those projects aim to support the continued existence of Ukraine as a State and as a partner, the alignment is implicit. Immediately following a crisis it can be difficult to understand how programming amounts to more than the sum of its parts and some recognition may need to be given to counterfactual considerations – for example, state systems that did not completely collapse or communities that were not forced to flee due to the restoration of priority resources. While important to maintain an emphasis on use of evidence in programming, it may be necessary at times to consciously lower the threshold for evidence collection in a State-survival context, where control group comparisons may be distortionary.
- The multi-donor PFRU, was designed to be a politically informed response to Russian aggression towards Ukraine. Initially this was oriented towards Government-controlled areas near the Line of Contact in the east, and areas vulnerable to Russian interference in the south. PFRU scaled up and pivoted quickly to the change in context brought by Russia’s full-scale invasion. Its framing of priorities – through the prism of Ukraine’s resilience – gives it the flexibility at the local level to understand and focus on the issues that should have the greatest effect most quickly, as opposed to other programming that is constrained by thematic goals or pre-defined activities.
- Delivery risk appetite was high throughout the FY due to the fast pace, high demand and needs, and pressures to deliver. The Programme tested the team's capacity to deliver to the maximum - they wanted to do more and were given the funding to deliver more. But this placed significant strain on the team and trying to deliver so much meant that it was difficult to step back, re-prioritise and match and align capacity. This lesson, along with the need to streamline into more coherent sub-programmes, has been taken up in the design of the FY 23/24 programme.

Action on Recommendations of Last AR

Implementation of recommendations from the FY 21/22 review was not consistent across the programme, primarily due to capacity and platform limitations. A table of progress against specific recommendations from last year’s annual review is included in Annex A to this review. The programme team will integrate outstanding review recommendations into a new recommendation tracker, which will include the recommendations from this review.

Key Recommendations for FY 23/24

Recommendations to focus on this financial year fall into three broad categories.

1. Continue progress towards splitting the current single overarching CSSF Ukraine Programme into more coherent standalone programmes. In FY 22/23 some projects were grouped and managed in ‘pillars’ to help break the programme into more coherent areas, but this should go further to formally create thematically coherent programmes which are clear in their scope and their intended impact – even if that intended impact must be realistically set given the volatility of the context. It is recognised that this takes time so this year efforts should focus on:
  1. Conduct separate annual reviews for pillars/sub-programmes next FY - As CSSF Ukraine programming has developed and is beginning to yield outcome-level results, the team would benefit from each of the thematic pillars being reviewed in their entirety rather than each year working through recommendations that only speak to a partial snapshot of the overall programmatic effort. If this approach is agreed with JFU it would supersede previous years’ recommendations to agree an alternative approach to the Annual Review which is more suitable to a programme of this size and breadth.
  2. Refine outcome-level statements to more clearly reflect the programme/pillar contribution to its thematic space. The Programme expanded into new areas following the full-scale invasion and many of the programme level outcomes in the Results Framework (RF) contribute to an overall goal in terms of the desired end state for Ukraine rather than being specific to CSSF Ukraine programming. Now that more is understood about Ukrainian needs and the donor landscape in these areas, pillar theories of change should be refined.
  3. These revised outcomes should be used to more clearly express the unique contribution of the CSSF and the Programme’s benefit against the CSSF/ISF ‘change areas’. With new FCDO-baseline programmes set-up in 22/23 and more planned for 23/24 there is more pressure on the CSSF to define its space, fit alongside these and ensure additionality. The CSSF Ukraine programme should continue its efforts to refocus in order to ensure its fit with CSSF (and in future ISF) change areas.

1. Continue steady improvements to programme management practice now that the situation is more stable than in FY 22/23. In particular:
  1. Ensure more projects meet the minimum requirement of being Gender Equality and Social Inclusion (GESI) level C by continuing to build implementing partner understanding of social inclusion and intersectionality. Gender analyses underpinning and strengthening projects outside the WPS pillar should be prioritised in FY23/24.
  2. Take a more deliberate approach to ensuring sustainability of projects is considered as early as possible in the life of the project, while maintaining the flexibility to review those plans.
  3. Strengthen conflict sensitivity analysis to ensure that it forms part of a feedback loop and leads to programme adaptation and adjustment in line with that analysis. More work should be done in the next FY to build the capacity of implementing partners to carry out effective conflict sensitivity analysis.

1. Improve MEL systems and support. A dedicated MEL Adviser will start in FY 23/24. Their priorities are:
  1. To build MEL capacity at the ground level, supporting PMs to scrutinise their projects’ reporting and working directly with priority projects to improve their MEL.
  2. Ensure a systematic and coherent alignment between pillar-level theories of change, the programme results framework, and project level logframes. This will help the PRO and SROs to provide scrutiny of results as comprehensively as they do for new projects.