 Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Global Cyber Programme (GCP)
Programme ID	​​C-CYB-0003
Country and Region	​​Global; Americas; Middle East; Commonwealth​
IATI Unique ID	CSSF-14-000001
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) / MoD, HO, GCSi, DCMS, NCSC, DBT, CO, DSIT
Total Budget	Total Planned / FY 22/23 £5.6m / FY 23/24 £6.55m / FY 24/25 £17.3m	Planned ODA / FY 22/23 £2.7m / FY 23/24 £4.2m / FY 24/25 £6.4m	Planned Non-ODA: / FY 22/23 £2.9m / FY 23/24 £2.35m / FY 24/25 £10.9m
Budget this FY	Actual Total FY 22/23 £5.6m	Actual ODA / FY 22/23 £2.7m Actual Non-ODA: / FY 22/23 £2.9m
Spend this FY	Total ODA spend FY 22/23: £2.165m	Total Non-ODA spend FY 22/23: / £2.75m
Time Frame	Start Date: April 22	End Date: March 25

Outputs	Individual Output Rating (low 1 to high 4)
Average project RAG rating from section B3 of the Quarterly National Cyber Strategy (NCS) Pillar 4.1.1. returns	3
Overall Rating of Output Delivery	3

Outcome Assessment	In FY22/23, the GCP delivered a wide range of projects focused on tackling cyber security threats, building resilience, and increasing UK international influence. / Just some of the highlights: GCP funding enabled the delivery of cyber threat exercises by Royal United Services Institute (RUSI) and BAE Systems (BAES) in Indonesia, Malaysia and Japan, and catalysed further financing for the MoD to deliver Defence Cyber Marvel 2, involving 750 cyber specialists from 11 countries. These exercises strengthen partner countries cyber resilience while improving UK understanding of their cyber maturity. / The GCP continued to work with the Commonwealth Secretariat (Comsec), building Commonwealth countries capability to tackle cybercrime. This included supporting cybercrime regional conferences take place during the year in Singapore, Ghana, Papa New Guinea and Jamaica, training on the use of electronic evidence (which has already been put into use) as well as the publication of Commonwealth Cybercrime Journal and Cybercrime Casebook. / Through the partnership with the Organisation of American States (OAS), the GCP funded a series of masterclasses for members of Cyber Security Incident Response Teams in LATAC as well as training in cyber diplomacy. / In Oman, the GCP funded the final year of the Gulf Women in Cyber Fellowship, which has been so successful as to have been taken on to the FCDO baseline for FY 23/24 onwards. It also funded the UK Oman Digital Hub, which since 2021 has been working with key Omani institutions to develop a cybersecurity workforce framework. During FY 22/23 this was piloted and was subsequently adopted by the Ministry of Labour. / The GCP also continued to fund projects with a global scope like Shadowserver and Global Forum on Cyber Expertise (GFCE). / The GCP achieved all this against a fast-evolving backdrop. FY22/23 was the first year for the Global Cyber Programme, which emerged from the restructure of the CSSF cyber portfolio alongside the Ukraine, Georgia, India, Indo-Pacific and Africa Programmes and the Digital Access Programme. The response to Russia’s invasion of Ukraine led to a dramatic reduction in the GCP budget from a planned £13.8m to £5.6m. The Programme Team needed to reconfigure the programme to accommodate this, while supporting the creation of the new programmes, responding to the recommendations of the Cyber & Tech programme 21/22 annual review, and adopting the new Monitoring, Evaluation and Learning (MEL) approach of outcome harvesting. / Programme Document refresh began in Q4 FY 22/23 and first GCP programme board held in May 2023. / Since for FY22/23 the programme had no defined success criteria, scoring it represents a challenge. The approach taken by this review is to extract the six change story summaries and contribution ratings from the outcome harvesting data repository and assign them to the most relevant January 2022 Theory of Change Portfolio Outcome. Where one or more change stories are assignable to a given outcome it scored either at Amber-Green or Amber. Where no change stories are assignable to a given outcome it is scored at either Amber-Red or Red.
Overall Outcome Progress Rating:	Amber
Overall Risk Rating	Medium/High

What Support Did the UK Provide in FY22/23?

- GCP focused on tackling cyber security threats, building resilience, and increasing UK international influence. This included supporting implementation of the 2018 Commonwealth Cyber Declaration, a UK priority as Chair-in-Office of the Commonwealth. The UK cyber leadership was highlighted at CHOGM 2022 in Rwanda and the contribution of the programme towards the National Cyber Strategy was recognised in the 2022-2023 Annual Progress Report.
- The funding allocation for the programme was £5.6m (reduced from £13.8m), with £2.7m ODA and £2.9m non-ODA. The programme was delivered in partnership with a broad group of implementers, including: international organisations, UK Government Departments, NGOs, the private sector and academia.

Key Results for FY 22/23:

- The GCP produced six change stories that demonstrated behaviours changed in key actors in line with CSSF cyber portfolio objectives.
- The GCP provided £0.75m to the Ministry of Defence (MOD) to aid the department to better respond to cyber training exercises delivered by partner governments, as well as host UK cyber exercises. This GCP commitment enabled the MOD to attract further financial resources, with DCM2 costing £2.4m, in total.
- At the end of the year, the Gulf Women in Cyber Fellowship that had been supported for several years by the GCP and the Cyber and Tech Programme before it, was taken onto the FCDO baselines. This was a recognition of the projects’ success and a vindication of the role that the GCP can play as a risk-taker and incubator.
- The cybercrime project with the Commonwealth Secretariat ended in March 2023. Highlights in the year included holding cybercrime regional conferences in Singapore, Ghana, Papa New Guinea and Jamaica, and publishing the Commonwealth Cybercrime Journal and Cybercrime Casebook.
- The GCP devised a clear action plan to address the recommendations of the previous Annual Review.
- Successfully delivered a UK in Chair Commonwealth Cyber achievements package ahead of the Commonwealth Heads of Government Meeting in 2022.
- Completion of BAE Cyber Threat exercises project which delivered bespoke table-top style exercises remotely to varied countries and organisations. Particular benefits in the Indo-Pacific (I-P) region and which helped develop contacts and trust which were taken forward in new I-P programme. This showed agility through quickly meeting India’s request to prepare a scenario to be used by the Ransomware Taskforce.
- Launch of Shadowserver’s global threats dashboard, which was a new tool to help identify cyber threats and trends (and has contributed to a change story in Q2 FY23/24).
- Able to flex allocation and staffing to enable quick set up of Ukraine programme whilst maintaining existing contractual, regional and policy commitments. GCP supported the set-up of the other regional programmes, for example by handing over established relationships and projects.

Key Lessons

- As far as possible, GCP programming needs to be multiyear, with minimal inflight modifications, to give implementers sufficient time to deliver and to provide the timeframes needed for change stories to arise.
- The programme team have made significant progress in streamlining the GCP but more remains to be done to give the programme a tighter focus and make it more manageable.

Key Recommendations

1.	Harmonise the GCP and CSSF Cyber Portfolio theories of change completely with the NCS outcomes, progress markers and change areas. I.e. rather than referring to global governance as
Portfolio Outcome 2, refer to it as Outcome 4.2.1. This will require ensuring that the workflows are in place for NCS outcome owners to coordinate activities with different NCS Pillar (4 and 5) outcome owners and to report on one-another’s outcomes.

2.	Consider briefly in the Programme Document how, where and why the GCP intends to land the Programme ToC programmatically to meet which NCS Outcomes. Where available draw on existing XHMG and NCSC work. E.g. the NCSC-C has developed a country prioritisation and the NCSC-A has looked at 5-year risks for AI (and can be commissioned by OGDs to carry out further assessments). The strategy should include only a small number of priority areas of action selected primarily on the basis of their contribution to the NCS and strategic fit with other NCS actors but that also meet CSSF/ISF criteria.

3.	Consolidate programming further to give fewer, larger, longer programmes. Potential ways of doing this:
•	Programme for a minimum of two years (with break clauses to be exercised in extremis).
•	Provide the timeframes needed to produce change while preserving agility by staggering the end dates of multi-year programming so that, for example, a third of the programme budget was available for reallocation every three years.
•	Tender multiyear programme with a prime contractor for a given theme or region.

Joint Fund Unit has advised against making large-scale changes for the final year of a spending round so this recommendation might be more appropriate for FY25/26

Make the intended contribution of projects to programme-level (UK National Cyber Strategy (NCS)) outcomes clear within each project indicator framework and Theory of Action. Use intermediate indicators between outputs and change stories to demonstrate what the programme is achieving in addition to or in the absence of a change story. These could be based on the Cyber Maturity Model framework to provide coherency across projects.

5.	Define what good looks like. How many change stories (with what contribution and what significance) are enough for an outcome and for the programme? What are the consequences of projects producing or not producing a change story. And of the programme meeting or not meeting the definition of what is good enough.