Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	India Cyber Programme
Programme ID	C-CYB-0003
Country and Region	India
IATI Unique ID	CSSF-14-000002
HMG Partners / (Lead in bold)	Government of India (GoI): Ministry of External Affairs, National Security Council Secretariat, Ministry of Home Civil Society Organisations and NGOs. / UK Government: FCDO, NCSC, CO, HO, DSIT, DBT.
Total Budget	ODA: Nil	Non-ODA: £8.5 million
Budget this FY	ODA: Nil	Non-ODA: £1.0 million
Spend this FY	ODA: Nil	Non-ODA: £8.3 million
Time Frame	Start Date: April 2022	End Date: March 2025

Outputs		Individual Output Rating
PH1	Stakeholder Mapping and Initial Engagement - Delivered	4
PH2	Programme Management Office Structure established, including contracting, SoWs, Governance, Risks, Commercials, etc. - Delivered	4
PH3	Draft Comms & Engagement Strategy Outline and Methodology - Delivered	4
PH4	Draft Monitoring, Result, Evaluation and Learning (MREL) and Results Framework Outline and Methodology - Delivered	4
PH5	Output Mapping and Wireframes - Delivered	4
IR1	Inception Project Plan (POAP) - Delivered	4
IR2	Engagement Plan to consult UK and International Stakeholders - Delivered	4
IR3	Leveraging Funds Paper - Delivered	4
IR4	In-country engagement and regional research - Delivered	4
IR5	Selection and approvals - Delivered	4
IR6	1 Pilot Intervention - Delivered	4
FR3	Implementation Plan - Delivered	4
FR4	MREL Strategy for Implementation (and Gender Equality and Social Inclusion (GESI)) - Delivered	4
FR5	Comms & Engagement Plan for Implementation - Delivered	4
FR6	Matched funding (if applicable) - Delivered	4
FR7	Human Rights Assessment and Overseas Security and Justice Assessment (OSJA) (for relevant projects) – Not Delivered	2
Overall Rating of Output Delivery		3

Outcome Assessment	It has been directed within the Terms of reference for this annual review that it be ‘light touch’ as the India Cyber Programme (ICP) project in 2022/23 was in inception and set up phases. The reporting on Outcomes is not required. However, it is considered that the overall ICP outcome assessment for FY 22/23 would be Amber, meaning that the planned results are at moderate risk. / The review team consider that the programme deliverables are in line with the Theory of Change as set out in programme documentation, and which was later revised by the implementing Partner, EY. There was some planned delivery during the final quarter of FY22/23, which can be seen aligned with programme objectives. Some programme documentation was still under development in Q4. Performance indicators and systematic reporting were developed in the early stages of FY23/24 with clear linkages to the revised Theory of Change. It is considered that targets and milestones set for the programme are ambitious yet realistic, and if reached, will support overall programming outcome objectives by March 2025. / During this review, 5 meetings and 5 interviews have been conducted, and programme related documentation reviewed.
Overall Outcome Progress Rating:		Not to be reported for FY 2022/23
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	N/A	N/A	N/A	N/A	3	Green
Risk Rating	N/A		N/A		Medium

Note: Output / Outcome score – Not reported in this annual review

What Support Did the UK Provide in FY 22/23?

Key Activities and Decisions (August 2022 – February 2023):

Inception
- In September 2022, UK (through BAE Systems) delivered a ransomware virtual exercise to test preparedness in the electricity distribution sector, ‘jointly-hosted’ with India as part of the global counter-ransomware ransomware initiative. 14 other countries participated virtually across 3 hours. Following the exercise, the Indian National Security Council Secretariat issued a statement via their public information bureau referencing the UK and BAE. The FCDO amplified this statement through its social media channels. The exercise was also mentioned on All India Radio (Hindi language service) the following day.
- A UK-India Joint Working Group was held covering Critical Information Infrastructure in November 2022 with Indian Government representatives and UK (NCSC, FCDO, DSIT etc).
- Programme Advisor and Operations Manager recruited.
- The Programme Manager spoke at police cyber showcases in North-Eastern Indian states, and at CERT-IN events, to promote the UK’s approach, the upcoming programme, and build relationships with various state law enforcement agencies.

Procurement of Prime Implementer (August 2022 – February 2023):
- Inception phase reports, including implementation plans for work streams, were submitted and reviewed.
- Stakeholder engagement plans, communications strategies, and MREL strategies developed.

Key Activities and Decisions (March – August 2023). (Beyond scope of the FY22/23 review but included for completeness):
- Repeated proposals submitted to, and discussions with, Indian key decision-making authority with varying levels of success.
- Design phase for EY implementer – all contracting and inception reports finalised.
- Joint Working Group on cyber CNI / health with Government of India and UK (NCSC, DHSC and NHS representatives from England, Wales and Scotland).

Key Results for FY 22/23:

It is assessed that the programme is broadly achieving its aims, and notwithstanding the delays experienced during early delivery phases in 2022/23, quality progress was made in Q4, which deepened as the programme matured into FY23/24. There is evidence to support the expectation that activities within the project support early progress towards impact and outcome delivery for the programme.

Key Lessons

The ICP offers several key lessons:

Adaptive Planning: Flexibility is crucial. The program experienced a pause due to lack of engagement from Indian nodal department and needed to adapt its delivery approach, emphasising stakeholder engagement and demand-driven activities. This demonstrated the ability of being adaptable in response to unforeseen circumstances.

Bilateral Relationships: Over the inception phase of the programme there were increased tensions bilaterally between the UK and India that impacted delivery progress, which was beyond the control of the ICP team. Appropriately considering this within risk management processes, and improving resilience of activity planning through diversifying local stakeholders we work through, will help reduce their negative impact on programme delivery.

Monitoring, Results, Evaluation, Learning (MREL) Challenges: Reporting contribution to high-level indicators such as UK cyber resilience posed difficulties due to complex supply chains and program delays. Addressing these challenges justified the requirement for robust MREL strategies aligned with program objectives.

Theory of Change (ToC) Development: The initial ToC was developed, together with ToA’'s, and validated with stakeholders during the inception phase. Constant revisited and adjustments of the ToC will continue to be necessary to ensure they remain relevant and aligned to changing circumstances.

Resource Management and VfM: The program demonstrated effective resource management by underspending during the inception phase, enabling flexibility and expansion during implementation. The emphasis on Value for Money (VfM) strategies, such as accurate resourcing and cost-effective planning, was evident. Moving into programme delivery has provided challenges to effective planning, resulting in a likely underspend for the following FY.

Incorporating GESI and Other Cross-Cutting Themes: Gender, Equality, and Social Inclusion (GESI) markers were seen to be built into program activities. Ongoing assessment and monitoring will be necessary to ensure continuous alignment with these cross-cutting themes.

Learning and Adaptive Management: There is a strong MREL component in the programme and a desire to learn lessons offered through the MREL process.

Networking and Influencing: The programme recognises the delivery benefits of face-to-face engagements with stakeholders demonstrating that visibility, familiarity, and accessibility remain key factors in building relationships, trust and collaboration.

These lessons underline the significance of flexibility, robust monitoring and evaluation, adaptive planning, effective resource management, integration of cross-cutting themes, contextual adaptability, and a strong learning culture within the ICP.

Key Recommendations from FY 22/23

Already Underway

1. Programme continuation: The India Cyber Programme, which is assessed as providing value for money, should be continued, to offer greater opportunity to deliver against its outcomes.
2. Engaging & Influencing: Maintain, support, and prioritise face to face in country contact with key stakeholders, including through ensuring implementers fully utilise their in-country staff and contacts, to support creation and development of collaborative, effective relationships while providing value for money.

To be completed within three months of publication

1. Transparency and accountability: Maintain high levels of transparency in the program's activities and outcomes. Establish clear accountability measures to demonstrate the impact of the program and build trust among stakeholders, including participating countries, donors, and the public.
2. Programme Engagement: Ensure FCDO maintains a consistent level of engagement with the implementing partner EY to maximise performance benefits in delivering the bilateral cyber capacity development projects. Consider most effective ways of escalating questions or issues up through programme governance structures to help unblock delaying factors. Ensure all stakeholders have representation at each board through staff with the appropriate qualifications, expertise, or relevant background to participate fully in meetings.
3. Long term sustainability: Assure delivery of strategies that seek to ensure the long-term sustainability of cybersecurity efforts beyond the program's duration. Ensure programme design prioritises investment in local skills development, promoting cyber education, and establishing frameworks for ongoing public and private collaboration in the cybersecurity domain.
4. Monitoring and evaluation refinement: Continuously refine the program's monitoring and evaluation mechanisms to enhance the measurement of outcomes and impacts. Regularly assess the effectiveness of projects and adjust strategies based on lessons learned to ensure continuous improvement and lever learning from previous lessons within the programme. Share best practice concerning MREL across the Cyber Portfolio to lever best practices and share learning.
5. Gender inclusion: Assure gender inclusivity in the program's initiatives, recognising the role of women in cybersecurity. Ensure the promotion of equal participation and representation, fostering diversity in perspectives and skills within the cybersecurity workforce.
6. Emerging threats: Assure a proactive approach to identifying and mitigating emerging cyber threats. Foster agility in program strategies and response mechanisms to stay ahead of evolving cyber risks and challenges.
7. Priority funding areas: Develop a finance strategy to utilise any potential programme underspends, demonstrating Best Value to align delivery impact with strategic outcomes.

To be completed within six months of publication

1. Programme Impact: Demonstrate clearly the strategic and operational impact of the India Programme through robust governance mechanisms and reporting frameworks. Assure strong and responsive linkages to monitoring, results, evaluation and learning processes.
2. Theory of Change: Keep the Theory of Change under continuous review to ensure that programme outcomes are clearly supported and delivered against in a consistent manner.