Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
Programme Title	The Bay of Bengal Maritime Security Programme
Programme ID	CSSF-09-000012
Country and Region	Bangladesh, Sri Lanka, Maldives (Bay of Bengal)
IATI Unique ID	N/A
HMG Partners / (Lead in bold)	FCDO (This programme falls exclusively to the FCDO baseline.)
Total Budget	ODA: £900,000	Non-ODA: £1.5m
Budget this FY	ODA: £200,000	Non-ODA: £882,900
Spend this FY	ODA: N/A	Non-ODA: £730,930
Time Frame	Start Date: 6 April 2022	End Date: 5 April 2023

Outputs	Individual Output Rating / 1 - 4
1.1 HMG identifies policy and strategy gaps, defines key stakeholders and develops roadmaps for future engagement	2
1.2 Stakeholders in each focus state show increased awareness of marine resources, opportunities, threats and vulnerabilities	2
2.1 Representatives of focus states demonstrate increased commitment towards improving maritime security	1
2.2 Focus states demonstrably improve selected maritime security capabilities.	2
3.1 HMG and partners identify technical capability gaps and likely means of addressing them	2
3.2 Stakeholder engagement results in a deepening and broadening of the maritime security community of practice	3

Overall Rating of Output Delivery	2

Outcome Assessment	Intended outcomes: / Littoral states have an improved Maritime Domain Awareness in their Exclusive Economic Zones and the wider region / Littoral states are better able to develop strategies that address traditional and non-traditional security threats and vulnerabilities / Littoral states have a clearer understanding of their maritime security deficiencies and are in a position to mobilise resources to address them / UK access and influence increases. The UK is increasingly seen as a key partner in regional maritime security and is well connected to important influencers. / The CSSF Bay of Bengal (BoB) Maritime Security (MarSec) Pilot Programme emerged out of the incipient bilateral Bangladesh CSSF programme established in 2020. Owing to COVID (and, indirectly, the ODA pause), the programme was repurposed into a regional MarSec programme covering Bangladesh, Sri Lanka and the Maldives with the aim of delivering the priorities set out in the (then) newly published Integrated Review (IR2021). The revised programme took a further year to design and develop in consultation with new stakeholders across FCDO and HMG. The final product comprised three pillars: (i) research; (ii) technical assistance; (iii) maritime domain awareness. The programme was consciously intended as a pilot phase with a large research component with a view to establishing a baseline for a more substantive investment over the course of the programme cycle out to March 2025, testing entry points and establishing working relationships in each of the three focus countries. The programme has delivered modestly against its outputs, but less substantially against its higher-ambition outcomes. The amber-red rating reflects the fact that this was a pilot programme designed as a testbed to inform future activity. The programme has successfully tested demand in the host countries and advanced a number of small but significant UK priorities. It has also demonstrated proof of concept for a more substantive body of programming in the remainder of the programme cycle and beyond. However, there are a number of internal policy and governance challenges to address if the programme is to achieve its full potential. In its pilot phase, the programme has run ahead of the policy and been set back by a number of internal governance challenges that will need addressing in the next phase of the programme.
Overall Outcome Progress Rating:		Amber-Red
Overall Risk Rating:		Medium-High

Summary of Programme Performance
Year	2020/21		2021/22		2022/23
Programme Rating	N/A	N/A	N/A	N/A	3	2
Risk Rating					Medium-High

Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?

The CSSF BoB MarSec Pilot Programme undertook a set of exploratory activities categorised into three pillars: (i) research; (ii) technical assistance; and (iii) maritime domain awareness (MDA). As a pilot, the programme focused heavily on research to provide an evidence base for a more substantive body of programming in future years. It also worked to increase maritime domain awareness among the three focus countries (Bangladesh, Sri Lanka, Maldives) and provide some exploratory technical assistance to establish frameworks for mitigating maritime security threats and improve regional cooperation.

Pillar 1 commissioned primary and secondary research as follows: (i) a main report setting out the main maritime security vulnerabilities in the region informed by experts; (ii) a literature review; (iii) perception surveying of local communities; (iv) economic analysis; (v) records of symposia in Dhaka and Colombo with practitioners and experts; (vi) a paper setting out insights and options from the research project.

Pillar 2 commissioned UN Office on Drugs and Crime (UNODC) to provide technical assistance in four areas: (i) research and proposals for a revenue scheme to enable fines from IUU fishing to fund law enforcement; (ii) work with Bangladesh and Maldives to protect submarine cables in line with UN Convention on the Law of the Sea (UNCLOS) best practice; (iii) academic engagement to tackle maritime crime; and (iv) promoting inter-agency cooperation on disaster at sea.

Pillar 3 commissioned the Royal Navy (RN) to conduct maritime domain assessments in Sri Lanka and the Maldives. These have both established a baseline for the governments concerned. A planned assessment for Bangladesh did not materialise owing to staff turnover.

Key Results for FY 22/23:

Pillar 1: Despite a number of limitations, the research pillar of the programme has established a working baseline of knowledge about the maritime environment in the Bay of Bengal and provided a set of recommendations for interventions. The two symposia have created a nascent ‘community of practice’, bringing together experts and practitioners across the three countries who remain in contact. The research exposed wide variations across the three countries in terms of: vulnerabilities; priorities; state capacity and capability; the maturity of national strategies and frameworks for tackling maritime threats; the maturity of public debate around maritime security; and public trust in state institutions.

Pillar 2: The UNODC projects were largely small-scale scoping exercises. They confirmed demand from the region for technical assistance on issues of maritime security. In Bangladesh, one of the projects led to the creation of an inter-agency team to protect submarine cables led by the Ministry of Foreign Affairs. Two of the four projects have subsequently been continued with funding from another international donor.

Pillar 3: The Royal Navy conducted maritime domain assessments in two of the focus countries (Sri Lanka and Bangladesh). The assessments from the UK’s flagship provider are part of the HMG’s competitive advantage in raising awareness about the maritime domain. The assessments have provided a baseline that will be useful in reinforcing both the effectiveness the maritime sovereignty of the focus countries.

Key Lessons

Alignment: The pilot phase of the programme has been challenged by the absence of an underpinning regional maritime policy for either the Bay of Bengal or the Indo-Pacific writ large. In particular, the top level priority on maritime security set by the Integrated Review in 2021 has yet to be translated into a comprehensive strategy for the Bay of Bengal region.

Performance: The programme has delivered modestly against the outcomes, and unevenly against the outputs. Notably it has not yet led to better maritime security policies or strategies in the three focus countries. The outcomes are commensurate with the level of investment in a pilot programme that was designed to gain evidence and test entry points on a ‘fail forward fast’ principle. It has exposed an important gap in UK regional maritime security policy, which is now being addressed with impetus from the programme.

Governance: The internal governance of the programme has constrained progress. The programme was overseen by four successive Senior Responsible Officers (SROs). Being a pilot programme there has never been a formal Programme Board. Buy-in to the programme at Post has been mixed at both policy and programme levels. This is partly attributable to staff turnover, but also ambiguities over ownership in a programme driven by the centre.

Resourcing: The programme has relied heavily on an external consultant to design the programme, but has consistently lacked a dedicated Programme Manager. As a result, the programme has developed an over-reliance on the capability of the consultant to perform some aspects of programme management that are more appropriate to a permanent member of staff.

Key Recommendations for FY 23/24

Ensure the Bay of Bengal Maritime Security Programme is anchored in an HMG-agreed policy that sets direction and prioritises between traditional and non-traditional maritime security vulnerabilities in the region.

Rename the programme as the ‘Indian Ocean Maritime Security Programme’. Distinguish more clearly between the different vulnerabilities and needs of focus countries.

Assume that shifting the dial on maritime security will require a long-term political and programmatic commitment based on sustained trust-building and relationship-building with the region. Ensure the UK’s bilateral political agenda is informed by programmatic insights.

Hire a dedicated Programme Manager. Appoint an empowered SRO. Create a dedicated Programme Board. Ensure maritime security objectives are included in Country Business Plans.

Share knowledge, learning and experience between the Bay of Bengal, South East Asia, and Pacific maritime security programmes. Convene HMG maritime security practitioners across the Indo-Pacific to share knowledge.

Introduce a comprehensive Results Framework and dynamic Risk Register. Ensure that programming, procurement and contracting take place before the start of FY 2024/25.