Annual Review/Programme Completion Review (22/23)
A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	​Countering Strategic Threats​
Programme ID	C-MLS-0008
Country and Region	Multilateral
IATI Unique ID	​​CSSF-01-000004
HMG Partners (Lead in bold)	​​FCDO, BEIS, Cabinet Office, MoD​
Total Budget	ODA: £1.02m	Non-ODA: £3.78m
Budget this FY	ODA: £0.34m​	Non-ODA: £1.26m​
Spend this FY	ODA: £0.06m	Non-ODA: £0.91m
Time Frame	Start Date: April 2022	End Date: March 2025

Change mechanisms (CM)	Individual CM Rating
1: Providing multilaterals with expert advice and/or funding to tackle HMG priority thematic and geographic areas.	3
2: Providing political access and influence in support of wider HMG policy objectives through convening and alliance building	4
3: Enabling feedback loops between multilaterals, Whitehall and the UK Delegation	2
Overall Rating of whether programme is delivering activities and outputs necessary for change at outcome level	3

Outcome Assessment	Although some progress markers were missed, overall, the evidence collected indicate that most outcome targets were or will be met. The missed progress was likely on course to be met, if they consistently make progress (which was not possible to evidence in this annual review).
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Low

Summary of Programme Performance
Year	2020/21		2021/22			2022/23
Programme Rating	4	Amber		4	Amber	3	Amber
Risk Rating	Low			Low		Low
Note: Output / Outcome score

What Support Did the UK Provide in FY 22/23?
- Seconding up to eight officers targeting Integrated Review priorities in multilateral organisations
- Grants to the Organisation for the Prohibition of Chemical Weapons
Key Results for FY 22/23:
All of the secondments provided evidence of tangible deliverables and impact delivered through UK investment into these positions.
Key Lessons
- Lessons learnt in making the recruitment, deployment and onboarding process of Voluntary National Contributions (VNCs) better and more efficient after years of significant difficulties, with the trailing and introduction of a new approach status.
- A small level of additional funding available to each secondee could help them deliver additional wraparound activity that could supplement and multiply their aims.
- Could the programme team facilitate a more effective discussion cross-HMG about using programme activities to greater effect?

Key Recommendations for FY 22/23
- The programme should use the transition from CSSF to ISF as an opportunity to strengthen strategic alignment.
- The programme should explore options to provide secondments with access to small levels of funding to deliver additional activities and projects in support of their objectives.
- The programme should consider reinstating secondments into other multilaterals beyond NATO, as has been the case in previous years.
- The programme should consider different ways of tracking longer-term impact of secondments and VNCs, and their deliverables, beyond their tenure in those roles.