Annual Review/Programme Completion Review (22/23)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	CSSF MuSt Peacekeeping and Conflict Resolution
Programme ID	C-MLS-0007
Country and Region	Multilateral
IATI Unique ID	CSSF-01-000003
HMG Partners / (Lead in bold)	FCDO, MOD & Metropolitan Police
Total Budget	ODA: £2,747,500	Non-ODA: £1,297,500
Budget this FY	ODA: £2,747,500	Non-ODA: £1,297,500
Spend this FY	ODA: £2,856,731	Non-ODA: £1,159,968
Time Frame	Start Date: 01 April 2016	End Date: 31 March 2025

Outputs[1] (for selected projects only)	Individual Output Rating
1. Peacekeeping operations are enabled to (1) systematically assess their operating environment; (2) use data and analysis to evaluate progress towards their goals; (3) provide UN leadership with information and analysis to make more evidence-based decisions in delivery of their mandate to de-escalate conflicts and improve security in some of the world’s most fragile countries; and (4) enhance reporting to Member States through increasing the use of data analytics and visualization.	4
2. Strengthened the performance of the uniformed component of UN peacekeeping operations.	4
3. Military Staff Officers (MSOs) improve operational approaches to mission assessment, planning and performance.	2/3
4. Increase the number of civilian women at senior level in UN peace operations.	3
5. The implementation of the second programming round of the UN Elsie Initiative Fund.	3
Overall Rating of Output Delivery of selected projects	3
[1] In the absence of a programme results framework (RF) for Q1-3, outputs have been extracted from various documents including the theory of change, Programme Document and United Nations Extra-Budgetary logframes. The new RF, introduced in Q4, does not use outputs in its methodology.

Outcome Assessment	The programme has continued to demonstrate progress in strengthening planning, assessing performance and managing pledges to improve the effectiveness and agility of UN peacekeeping operations. The dynamic and challenging environment in which the programme operates was illustrated by the evolving situation in Multidimensional Integrated Stabilization Mission in Mali (MINUSMA). A revised MEL approach in Q4 should enhance reporting and allow for analysis of the progress towards achieving the desired outcomes and allow for agile in-year decision-making and refocus of funding. That said, implementation of the new process will rely on sound programme management and better stakeholder management, including with beneficiaries. This will help recognise where change is emerging and how to capitalise on it.
Overall Outcome Progress Rating:	Amber
Overall Risk Rating:	Low

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c		2022/23
Programme Rating	B	A	B	A	A	B	B	3	Green/ Amber	3	Amber
Risk Rating	Low	Low		Low		Low		Low		Low
Programmes changes during this period	There were no new projects funded for the F/Y 22/23.

What Support Did the UK Provide in financial year (FY) 22/23?

- The UK continued to support UN peacekeeping in becoming more effectively funded with more agile resources and increased capabilities to deal with the challenges of modern peacekeeping as well as helping to deliver UK peacekeeping reform priorities.
- Specifically, UK support involved:
  - Improving the effectiveness and efficiency of UN peacekeeping. This included direct support to a range of extra-budgetary (XB) projects in the UN Departments of Peace Operations (DPO) and Operational Support (DOS) to improve mission planning processes, generate new pledges of troops and police to contribute to the safety of deployed troops and in turn civilians affected by conflict.
  - Direct funding to the UN Elsie Initiative Fund (EIF) to support and incentivise the increased meaningful participation of uniformed women in UN peace operations and security institutions in line with the UN Secretary-General’s (UNSG) 2030 gender strategy.
  - Deployment of up to 15 UK military and police officers to UN peacekeeping missions and HQ to help make UN missions more effective and better able to fulfil their mandates. As well as providing an enhanced feedback loop to UK geographic policy leads to enhance pursuit of UK aims in UN negotiations.
- This annual review has been directed to focus only on specific projects set out in its terms of reference. These projects are:
  - Extra-budgetary projects: The Strategic Force Generation Cell (SFGC), Comprehensive Planning and Performance Assessment System (CPAS), and the Senior Women Talent Pipeline (SWTP).
  - Non-extra-budgetary projects: The EIF.
  - Deployed Military Staff Officers: UK military officers deployed to the UN peacekeeping missions in Mali (MINUSMA) and the Democratic Republic of the Congo (MONUSCO).

Key Results for FY 22/23:

Key results have been broken down into the 3Ps, in line with the review’s terms of reference.

Planning

- CPAS implementation is improving mission assessments; of impact, databases, reporting and decision-making, as well as integrated strategic and operational planning.
- Every UN peacekeeping mission conducted at least one CPAS impact assessment during the reporting period, providing senior leadership with reports to support evidence-based decision making.
- Five UNSG reports have been informed by CPAS and six UN Security Council (UNSC) briefings have received a CPAS factsheet, thereby strengthening the information which informs the Council’s decision-making.
- MONUSCO utilised CPAS impact assessment reports to inform its transition planning.
- MONUSCO’s Joint Human Rights Office successfully integrated key indicators into CPAS enabling detailed visualisation of violations. The new human rights violations' dashboard gained rapid acceptance and is accessed daily by UN Mission and Country Team staff.
- The MONUSCO Force HQ (FHQ) military planning team's integration of civilian components has been a notable step towards more comprehensive and effective planning.
- UK Military Staff Officers (MSOs) continued to drive planning efforts for the military component in MINUSMA and MONUSCO.

Performance

- The Strategic Force Generation Cell (SFGC) facilitated eight UN performance feedback meetings with troop and police contributing countries (T/PCCs), to enhance peacekeeping performance.
- The Senior Women Talent Pipeline (SWTP) has increased its membership by 30% following its 4th intake of members. This has helped ensure the organisation is better placed to meet the complementary goals of gender and geographical diversity when filling positions in the field.
- SWTP supported 145 candidates through the recruitment process, resulting in six women gaining senior appointments (grades P5-D2). SWTP supported 66% more women compared to last year.
- UK MSOs enhanced the planning capability of international military staff at Force HQ.
- With support from EIF, the Ghana's military battalion deployment to UN Interim Force in Lebanon (UNIFIL) exceeded gender parity targets, increasing women peacekeepers in the unit from 16% to 19%, including 15 women in command positions, and 150 women in technical and combat roles.

Pledges

- All uniformed units deployed to peacekeeping operations were force generated through the SFGC Peacekeeping Capability Readiness System (PCRS).
- SFGC conducted 13 advisory and verification visits on priority units registered in the PCRS, including those in the rapid deployment category earmarked for MINUSMA.

Key Lessons

- The programme should avoid making large-scale changes to how it tracks results and collects data so late in the year. This decision created unnecessary confusion among project leaders, deployed UK MSOs, and the annual review team. There would have been benefits in delaying the change to the following reporting year, including the development of a revised theory of change (ToC).
- A results framework (RF) should be built on a clear understanding for how the programme will enable change. The new RF, introduced in Q4, was designed without an effective ToC in place. A revised ToC would have helped develop a RF with appropriate progress markers.
- The programme should consider engaging with beneficiaries to capture individual and organisational behavioural change. Trying to gather this data via UN project leads can be a sensitive and confidential issue. Other ways to capture behavioural change, aside from the regular quarterly reports, should be considered.
- Effective and strong management of the programme ensures that reporting and analysis informs decision making throughout the year. Due to a higher-than-normal turnover of staff in this FY, not all the key responsibilities and requirements of running the programme effectively were retained in this FY.
- UK MSOs are not being fully utilised in peacekeeping missions to fulfil programme related outcomes. MSOs should understand the programme and be briefed on the impact, including access and influence the UK is hoping to achieve through their deployments.
- Political access and influence (PAI) activities are not being captured and analysed to inform in-year decision making. The evidencing of PAI has been highlighted in previous annual reviews. A sustainable process should be considered to ensure these benefits are captured in a systematic way.
- There would be benefit in having a CSSF programme manager based in New York (NY), to enhance the interaction between the programme manager, UKMIS NY staff and UN project leads, and help to leverage programme opportunities.

Key Recommendations for FY 23/24

- Implement consistent programme management to improve oversight, governance and analysis of the programme to enhance decision making.
- Implement a programme-level risk register.
- Implement a sustainable mechanism to capture, exploit and demonstrate impact of PAI arising from the programme.
- Planning should begin for exit strategies for each project in partnership with the UN and Member State partners to ensure sustainability.
- Work with partners to develop a strategy for MSOs, to identify how to maximise the opportunities that arise from these deployments.