CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Enablers Programme
Country and Region	Global
Programme ID	C-CTP-0005	IATI Unique ID	CSSF-01-000015
Start date	1 April 2022	End date	31 March 25
HMG Partners / (Lead department in bold)	Cabinet Office, FCDO, Home Office
	Total overall Programme Allocation (3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	0	0	0
Non-ODA	£4,700,550	£850,000	£976,648
Total	£4,700,500	£850,000	£976,648

## Outputs
Output Statements	Individual Output Rating
A1.1: Increased UK engagement with priority Counter Terrorism (CT) partners.	Green
B1.1: Improved HMG data on risk	Green
B1.2. Improved HMG data on partner capability	N/A
B2.1: Improved results data that enables effective and timely decision making	N/A
C1.1: Research, pilot project design and engagement that informs / enables HMG CT activity.	Amber
C2.1. Teams equipped with the knowledge and skills for effective interventions with a focus on project design, Monitoring, Evaluation & Learning (MEL) and Programme & Project Management (PPM).	Green
Overall Rating of Output Delivery	Amber

## Outcomes
Outcome Statements
Enabler A: HMG’s CT partnerships are strengthened
Enabler B: HMG CT community understands: the risk posed by current and future international terrorism; the most effective tools available; the impact of our actions on the risk.
Enabler C: HMG internal systems support international CT effort
Outcome Assessment	Enabler A and B are delivering towards the outcomes and doing it well in spite of the system (enabler C) not set up well or achieving it’s intended outcome to support the international CT effort.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating			Green	Green	Amber	Amber
Risk Rating			Medium	Medium	Medium	Medium
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- Central Asia/Afghanistan – Developing security partnerships with Uzbekistan and Tajikistan, including a compliant detentions pathway - £150k
- Across Europe – Deepening relations across European partners - £170k
- Somaliland (+ Kenya, Ethiopia & Djibouti) - Support to Horn of Africa regional CT conference – £25k
- Morocco (Hedaya) – Rehabilitation and Reintegration of women and children vulnerable or exposed to Violent extremisms - £130k
- Global Community Engagement & Resilience Fund GCERF (Global) – GCERF Core Contributions - £200k
- Monitoring, Evaluation & Learning, Technical Advisory Service (MELTAS) contract – M&E support to portfolio - £400k
## Key Results for FY 23/24:
- Relationships in over 10 European countries were strengthened leading to better understanding of CT capabilities and risk. There were notable successes in France, Germany, Ireland and Sweden.
- The Somaliland Conference has led to continued collaboration between Somaliland and Ethiopia
- Funding of GCERF has enabled the UK to shape GCERF’s future strategy and deepen partnerships with US and European counterparts.
## Key Lessons:
- Due to chances in structures and processes the Results Framework (RFW) for enabler’s C is not fit for purpose. Thought should be given to amending indicators in-year if they are no longer relevant.
- The sample size of some indicators is too small to make a reasonable evidence-based assessment. Sample size should be considered when setting milestones.
- Greater synergies with could be realised with the other FCDO-led programmes if the Enablers SRO was based in the FCDO.

## Key Recommendations for FY 23/24:
- Enablers Fund should not be used to top up other programmes. There should be strict adherence and projects only funded if they directly support the Enabler programme’s outcomes. If a project doesn’t meet the threshold for other programmes, then it should only be funded by the Enabler’s fund if it meets Enabler’s outcomes. A rebranding could help, alongside efforts to re-educate seniors on the objectives of the programme, some of whom misunderstand the purpose and benefits of the programme.
- Identify new and improved ways to share learning and lessons across the programme, particularly research or what has/hasn’t worked in building relationship. Consider how we want to influence and what we want to do in key countries so that we can use Enabler’s projects to drip feed ideas for the future and support future scoping. (Enablers & Counter Daesh Communications Cell (CDCC) are doing this in Central Asia).
- Reconsider the MEL component in its current form and whether the contract and oversight structures are fit for purpose and has the right budget allocation to deliver what is needed. Consider having a smaller contract to deliver products for the Board and have in-house programme M&E advisers for each programme who can support tailored reporting, guidance and improve lessons sharing across the portfolio. Consider whether the MEL component should remain in Enablers or be managed as a separate standalone contract (e.g. funded under Portfolio admin lines), or otherwise fully implement Programme Responsible Officer (PRO) oversight of the MEL component equivalent to other Enablers projects.
- Consider having the SRO for Enablers sit within Counter Terrorism Department (CTD) FCDO to strengthen synergies across programmes and the overseas network