CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Tunisia ISF Programme
Country and Region	Tunisia, Middle East and North Africa
Programme ID	C-MNA-0032	IATI Unique ID	CSSF-O6-000028
Start date	1 April 2023	End date	31 March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£6m	£2m	tbc
Non-ODA	£0	£0	£0
Total	£6m	£2m	tbc

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Tunisian Government supported to implement economic reforms	4
Private sector, Civil Society Organisations (CSOs) and academics/researchers provided with opportunities to influence Tunisia's economic reforms	3
Decision making is supported by quality data	4
Gender-based violence (GBV) prevention and response systems strengthened	4
Women's access to leadership and decision-making positions in the public administration and in their communities is enhanced.	4
Journalists equipped to recognise and tackle mis- and disinformation.	4
Skills for Success	3
Kumulus	4
Ministry of Interior (MoI) supported to implement national Counter-Terrorism strategy in a way that respects human rights	4
Civil society and researchers engaged to reduce violent extremism and improve social cohesion	3
Tunisian Government supported to develop a National Centre for Crisis Management (NCCM)	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Tunisia’s economic reforms are implemented more inclusively.
Tunisia’s social and civic backsliding is slowed.
Tunisia can more effectively prevent and respond to violent extremism.
Outcome Assessment	The overall outcome progress rating is Amber. This is largely a reflection of the ongoing risks given the challenging operating environment and subsequent impact on delivery of some outcome targets. As predicted in the last annual review (AR), the operating context in Tunisia has hardened, but the team’s adaptability ensured progress, even when key projects were delayed. There is also strong evidence of the team leveraging activity to maximise impact. Synergies with other His Majesty’s Government (HMG) and international priorities have delivered good results in a very short timeframe. / The team’s decision to pursue a strategy of flexibility and breadth appears correct. Short, sharp interventions not only complement longer-term, multilateral projects well, but also enabled the team to directly engage a broader range of stakeholders, thus improving Tunisian Government (GoT) inclusivity and exposure to UK expertise. This, in turn, has enabled the UK to strengthen its presence (perhaps more than the team realise) in a political context where GoT is otherwise reducing its interaction with foreign governments. Further budget reductions would significantly impact outcome delivery and damage the UK’s reputation and influence in the country.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2020/21		2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	4	Green	4	Green	3	Amber	4	Amber
Risk Rating	Medium		Medium		Medium		Medium

## What Support Did the UK Provide in FY 23/24?
Socio-economic reforms
- Through the World Bank, the UK continued to fund:
  - Delivery Unit (DU) advisory services to address specific requests by the Prime Minister’s Office (PMO) to aid implementation of reforms;
  - Technical assistance and consultation (including international expert engagement) on a range of policy areas, including:
    - Green Bonds and renewable energy sector development.
    - Digital government payment systems
    - Data literacy
- Additional support to:
  - the African Development Bank (AFDB) Entrepreneurship Innovation and Advice (EINA) project – helping i) inform Tunisian Government policy on entrepreneurship and small and medium-sized enterprises (SMEs), and ii) support the Ministries of Economy, Finance and Employment to promote the development of micro small and medium enterprises (MSMEs),
  - the Ministry of Industry, Energy and Mines through the European Bank for Reconstruction and Development (EBRD), to promote the valorisation and reclassification of phosphogypsum (a phosphate by-product)
  - the United Nations Development Programme (UNDP), to help prepare key industries for the establishment of the European Union’s Carbon Border Adjustment Mechanism (CBAM) in Tunisia. (Activities to commence FY24-25.)
  - Tunisian Youth NGO Action Gabes to support a conference on social economic growth models

Open and inclusive Society:
- Through the Organisation for Economic Co-operation and Development (OECD), the programme continued to strengthen gender-based violence (GBV) prevention and deliver initiatives to increase female representation.
- Through the International Foundation for Electoral Systems (IFES), the programme trained and mentored local journalists, helping to advance their skills in accurate reporting, including identifying and countering dis/misinformation.
- Through Kumulus, provided safe drinking water to six schools in the water-stressed region of Kairouan (serving over 1,000 students), helping to tackle school drop-out rates and address drivers of social and economic instability.
- Scoped Skills for Success project to equip vulnerable youth in marginalised areas with life skills through the teaching of English language, including critical thinking to boost resilience to mis-/disinformation and other social threats.

Improved Security
- Through continued support to the UNDP Tarabot Project, the UK helped launch and start implementation of Tunisia’s new Counter Terrorism Strategy; and improve the coordination function of the Counter Terrorism Commission (CNLCT). It also supported civil society organisations to foster social cohesion at grassroots level.
- Supported scoping for a Tunisian National Centre of Crisis Management.

## Key Results for FY 23/24
- Supported PMO to: map sectoral strategies and assess options for restructuring central government; delivered leadership training and capacity building for PMO.
- Through World Bank and UK Office for National Statistics collaboration, trained GoT officials in data literacy, helping to improve the use of data to inform economic policies and decision making.
- Through the EBRD, supported the declassification of phosphogypsum as dangerous waste enabling the recycling of phosphate waste.
- Supported AfDB to conduct an entrepreneurship profile survey, which informed GoT’s Entrepreneurship and MSMEs Strategy, in collaboration with the Ministry of Employment and Vocational Training; This project also helped to unlock a $90 million AfDB loan, which is expected to create approx. 100,000 jobs in Tunis.
- Trained 193 journalists to identify and counter mis/disinformation; Over 1.5 million interactions with a digital awareness campaign on mis/disinformation.
- Supported OECD to expand its work on GBV into three further governates - improving awareness of GBV and delivering a more coordinated response; Roadmap on gender inclusiveness developed alongside the Ministry of Women; 153 Youth House staff and members were trained on gender sensitivity and gender equality.
- Through the UNDP Tarabot project: launched the Counter Terrorism (CT) Strategy, which reflects UK best practice and promotes coherence between ministries and civil society organisations. Tunisia’s National Counter Terrorism Commission (NCTC) has an increasingly visible role across GoT as a more inclusive CT coordination body.
- Also through Tarabot, supported 15 grants to local NGOs to implement social cohesion initiatives, which help to support prevention of violent extremism (PVE).

## Key Lessons:
- Synergies elevate delivery. Projects are most impactful when there is strong coordination across the embassy and HMG. Coordination/communications improve the team’s ability to identify and synergies.
- UK contributions are valued by multilateral partners. Key for maintaining access. Concerns about dilution of UK visibility in international fora/ G7 etc. should not be exaggerated.
- Breadth of focus has yielded good results – makes sense in the current context. Flexibility and responsiveness enabled the team to seize opportunities and maximise impact through quick and strategic allocations of resource to smaller projects. However, this success comes at a price: taking on more projects, however ‘small’, adds extra pressure on an already stretched team.
- The outcome and wider impact of projects with short turn arounds are difficult to assess, particularly when evaluation is not included in project design/budgeting. This also raises the questions as to the sustainability of interventions and how much thought is given to what happens next and sufficient exit strategies. The team should aim to prioritise monitoring and evaluation, reflect all activities in the Framework for Results (F4R) and update evidence on a regular basis.
- Opportunity and appetite for greater communication/closer coordination with programme team remains. This review echoes last year’s recommendation encouraging greater communication across the Embassy and with HQ.

## Key Recommendations for FY 23/24:
- Maintain broad, responsive approach rather than focus on two or three areas, to spread the risk of delays in delivery, given volatility surrounding government appointments and approaches.
- Consider innovative ways to flex and adapt interventions in other pillars (as has been done in the economic pillar with the Economic Flexible fund), remaining careful to maintain a strategic approach when prioritising potential activities.
- Explore ways to adapt Monitoring, Evaluation and Learning (MEL) tools to better suits the needs of the programme: As small team with stretched resources, explore ways to reduce the time burden of MEL. Working with the MSPT MEL adviser, consider how other ISF programmes have reworked systems to better suit their portfolios. Consider also long-term ambitions when setting how results are captured within individual output areas. How some targets are quantified can restrict setting more ambitious targets in successful projects.
- Continue to focus on improving comms and coordination across the embassy and HMG, particularly through more ad-hoc, informal meetings to discuss possible strategic alignments and risk assessments. An increased focus on comms to broadcast successes and demonstrate the value of the Tunisia programme is encouraged. This could be achieved through more regular communication with colleagues at post and in London.
- Make better use of London/desk -as per last year’s recommendation to improve visibility, but also gain support. This could help reduce the burden of activity at particularly busy periods.