ISF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet

Programme Title	CSSF Iraq Programme 2023/24
Country and Region	Iraq, MENA
Programme ID	C-MNA-0007	IATI Unique ID	CSSF-06-000029
Start date	April 2021	End date	March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO)
	Total overall Programme Allocation (e.g. 3 years) / 8 years from 2016-2024	Allocation FY2023/24	Spend FY 2023/24
ODA	£ 98.67m	£8.345m	£8.353m
Non-ODA	£ 5.36m	£1.92m	£2.008m
Total	£104.04m	£10.265m	£10.361m

## Outputs
KEY Output statements	Individual Output Rating
1.1 Methodology for Systems Approach to Training (SAT) components is adapted to the Iraqi curricula	4
1.2 Curricula review findings adapted, and process implemented for incorporating international training material update	4
1.5 State threat areas agreed, ventures developed, approved and implemented	4
1.6 Capability of the Government of Iraq (GoI) and Kurdistan Regional Government (KRG) beneficiaries built through STAFFI training, mentoring, and coaching activities	4
1.7 Products* have been co-developed or refined with GoI and KRG to enhance security and counter state threats.	4
2.2 Capability of GoI and KRG beneficiaries built through TAFFI training, mentoring, and coaching activities	4
2.3 Products* that have been co-developed or refined with GoI and KRG to support economic and political reform.) / 3.2 Women’s Rights Organisations (WRO)s in Iraq provinces are supported and show evidence of sustainability	4
3.3 women and girls' and wider communities directly and indirectly receiving support and services on account of project WROs / Civil Society Organisation (CSO) engagement	4
4.1 Displaced communities and key stakeholders have increased engagement in the identification of priority areas of intervention to enable sustainable, inclusive and peaceful returns and progress towards durable solutions	4
4.2 Internally displaced persons (IDPs), returnees, and host communities prioritized needs are addressed have increased access to basic services through quick impact projects (QIP’s).	4
4.3 IDPs, returnees, and host communities have increased income generation capacity through individual livelihoods assistance (ILA) to support sustainable reintegration.	4
4.5 Climate-change-affected communities in the Kurdistan Region of Iraq have access to Natural Resource and Conflict Management Committees	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Greater flexibility within Iraqi military training and increased Iraqi capability in order to better respond to relevant threats.
Increased capability, changed motives, and enhanced opportunities for the government of Iraq to implement economic and political reforms.
Women and young people’s civic engagement skills enhanced, increasing participation in local and regional political processes, decision-making and peace building to the benefit of communities.
Improved living conditions and resilience in targeted communities as well as increased data on migration drivers.
Outcome Assessment	The Iraq programme was effective in delivering against all programme level outcomes in what continues to be an extremely challenging context. Despite a difficult year, most notably the heightened tensions and instability in the region and within Iraq due to the Israel-Gaza conflict, the programme had some key successes and real tangible deliverables. The programme achieved 100% spend against their allocation, without the use of a donor funding mechanism. These are notable achievements, and the Team should be commended, particularly as many of the CSSF team were drawn down from platform for up to 4 months. / The Programme Team demonstrated strong Implementing Partner (IP) management, enthusiasm and resilience. This is evident from the feedback we received from multiple stakeholders, both external and internal who sighted the engagement and collaboration of the programme team and support from the wider Embassy as crucial to successful delivery. As a result, the programme has maintained the UK’s excellent relationship with Iraq. / The Technical Assistance Venture (TAV) mechanism continues to play a critical role in providing high impact tangible interventions. TAFFI continues to be highlighted as a project which generates sizeable political access and influence (PAI) with the Iraqi government
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		High

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	4	Green/Amber	4	Green
Risk Rating	High		High		High

## What Support Did the UK Provide in FY 23/24?
The ISF Iraq programme acted as an agile and innovate tool to provide for a more stable, accountable, capable and inclusive Iraqi state that is better able to tackle its own security concerns whilst meeting the needs of its people. The activities strengthened the capacity of Iraqi ministries and institutions as well as support the Government of Iraq (GoI) and Kurdistan Regional Government (KRG) in tackling destabilising influences that could potentially trigger unrest and localised conflict. At the local level activities supported stability and community cohesion, as well as promoted the inclusion of women & girls and young people. Namely, ISF Iraq across 23/24 has:

Strengthened the Iraqi military capability by establishing a Systems Approach to Training (SAT) that will enable Iraqi Security Forces to develop and embed their own training curricula, thus catalysing further longer-term support from NATO Mission Iraq.

Continued to support better economic management and improve the democratic process via TAFFI, thus strengthening the social contract between the people and the state.

Built capacity of GoI security agencies to better respond to malign state threats through agile, flexible ventures and interventions focusing on areas that will include cyber security, counter-disinformation, serious organised crime (SOC), and digital forensics.

Continued to enable Iraqi youth activists and future political leaders to strengthen their credibility among minimally engaged Iraqi citizens and subsequently mobilise these citizens through localised, issue-focused advocacy campaigns to demand better local and national government performance and accountability.

Sustained support to Iraqi women’s rights’ organisations to strengthen the role of women across federal Iraq and KRI, and lend further support to the inclusion of women, female youth and women-led civil society in conflict prevention and resolution.

Strengthened resilience at community level through supporting the co-ordinated re-integration of IDPs and tackling root causes of climate induced displacement.

## Key Results for FY 23/24
In the final year of delivery for TAFFI 1.0, 16 technical assistance ventures were delivered contributing to Iraq Business Country Plan outcomes across all three main pillars;

TAFFI deliverables included significant progress on support to the National Digital Forensics Strategy (NDFS) project delivering training to the three major Iraqi security institutions with digital forensics capabilities.

On Cyber, TAFFI support to IMOD across 23/24 culminated in the procurement of a Security Operations Centre (SOC) thus enhancing sustainability and delivered training to the Cyber Security Directorate (CSD) on its operational use. Installation of the SOC within IMOD CSD will occur under TAFFI 2.0 supported by a directive across IMOD, outlining CSD’s role as responsible for protecting IMOD’s digital networks from cyberthreats and cyberattacks.

On anti-corruption, TAFFI support directly led to Iraq gaining membership to the Egmont Group, allowing Iraq’s Financial Intelligence Unit (FIU) to exchange financial intelligence with the other 169 member nation’s FIUs.

A TAFFI hosted week-long workshop bringing together the Financial Investigations Unit with KRG law enforcement agencies, including the judiciary and police, demonstrated how the intelligence produced by the FIU - through the new Anti-Money Laundering/Counter-Financing of Terrorism software installed with TAFFI support - can be used as evidence to support and strengthen criminal prosecutions.

TAFFI continued support to the Iraq Fund for Development (IFD) – Iraq’s first strategic investment fund ($2.4bn) – saw the IFD develop the necessary compliance and governance controls to ensure the Fund was established according to international best practice. Support to the strengthening of IFD is now one of HMA’s network priorities,

Training Systems Development Programme (TSDP) has successfully met/exceed all year one targets. Delivery has been under-pinned by high levels of cooperation between TAG International, the Defence University for Military Studies, the Staff and Military Colleges and NATO Mission Iraq. Wide Iraqi key stakeholder engagement, buy-in and understanding of a Systems Approach to Training (SAT) is key to the success of the project and Y1 of delivery has offered strong evidence that this is being achieved.

Women's Voice First (WVF) women’s inclusion activities including grant funding to women’s rights organisations has directly supported 14,813 women and girls across Iraq as well as over 5,000 men and boys. An additional 126,641 beneficiaries have indirectly been reached through a range of self-identified women, peace, and security (WPS) activities throughout Iraq. Notably, the project's sustainability strategy proved effective by providing 29 WROs with essential fundraising and business skills to secure grants beyond the project's scope: 24 of whom successfully obtained additional funding grants.

Political and community activists leveraged their knowledge and skills gained through ISF funded technical and financial support to implement a number of impactful advocacy campaigns that led to tangible changes at the community level. 54 activists (of which 19 were women) received direct training and over the two-year project delivery. As a result of these efforts, IRI/EPP reached more than 2,090 (808 women) citizens in person and more than 500,000 individuals via social media. In addition, the EPP project led to significant change at the individual and community level as demonstrated through qualitative change stories shared by programme partners/validated by IRI

Institute of Migration (IOM) Building Peace and Stability Iraq met or exceeded targets towards ensuring that Iraqi people impacted by conflict and displacement have improved living conditions through safe durable solutions pathways and peaceful, sustainable reintegration into society. The five identified IDP host communities across Diyala, Anbar, and Salah al-Din co-produced community-based plans outlining the main identified needs and potential solutions, with IOM consulting local authorities to ensure that these plans align with government priorities. These consultations and plans were then further developed into six quick impact projects (QIPs) which were delivered in Q4, for the rehabilitation of vital community infrastructure in targeted areas of return.

ISF funding via IOM helped strengthen the resilience of climate affected communities in KRI to help better mitigate factors that directly attribute to internal mobility/displacement, as well as irregular migration. This pilot project focused on community level support through provision of (community generated) quick impact infrastructure projects, livelihood activities and local co-ordination around natural resource management. The project also ed analysis and data-sets that improved GOI and HMG’s evidence base on climate-induced mobility and fragility. 23/24 outputs included a Climate Vulnerability Assessment which found that access to natural resources was the main driver of movement, tension and conflict in 12 locations across KRI. In parallel to this IOM recorded 23,364 families (140,184 individuals) as internally displaced because of drought conditions across 12 of Iraq’s 18 governorates, primarily in central and southern Iraq. 5 of those 12 governorates will be targeted and supported through this project in the coming one to two years.

## Key Lessons:
Collaborating x British Embassy Baghdad (BEB) and British Consulate General Erbil (BCGE) reaps benefits for all. Strong linkages between the programming work that ISF performs, and the policy work that BEB undertakes demonstrates how programming is supporting, reinforcing and underscoring policy priorities and vice versa. During 23/24, xBEB engagement has enabled coordination between policy and programming. e.g. Women's Voices First Programme has enabled the political team to address one of their priorities in strengthening local civil society and supporting grassroots organizations. The activities provided a tangible example that the team leveraged to enable them to obtain crucial information about the status of women's rights organizations. This collaboration should continue to be developed.

The process of assigning a policy lead has helped to ensure buy in and strategic engagement from other xBEB stakeholders, e.g. SOC and CT. Useful opportunities for discussion on activities to determine the strength and justification for undertaking activities, e.g. just because activities are running and results were good, does that justify continuing the interventions? Are they still aligned with what the teams are trying to achieve through the policy priority objectives? Feedback highlights healthy and constructive challenge from across teams which the CSSF/ISF team has valued.

On the deployment of consultants for TAFFI, there is a need to consult wider BEB on the timings. For instance, BEB political teams have relevant context that can lead to deployments and/or timings being unnecessary or even counter-productive for their objectives. Therefore, all deployments should continue to be coordinated x-embassy to better align within wider BEB efforts.

Engage the Programme team (PT) in xBEB governance design. The new governance set up took time to bed in and required adaptation to enable ways of working. The ISF country board has been replaced with a cross BEB board. The team should ensure that the new oversight structure and the replacement of the CSSF Country Board offers the programme sufficient assurance and strategic direction.

## Key Recommendations for FY 23/24:

Use XBEB and xBCGE comms more effectively to amplify CSSF/ISF interventions and successes. ISF team to engage with any developed x mission comms strategy.

Conflict sensitivity gap:
collation of evidence, undertake a JACs and SOCJA to underpin and inform future programming, need to capture Conflict sensitivity. Suggest exploring developing a stability tracker (to demonstrate the change in context) and conflict sensitivity scorecard.

Monitoring and Evaluation:
- Articulate better the theory of change (ToC) and the connection with the log framework. A narrative and an Outcome Tree can support the ToC and better connect it to the log framework.
- Produce and maintain Value for Money (VFM) framework.
- Establish a PAI framework to monitor, collate, coordinate and capture influence to catalyse and leverage x mission work.
- Ensure ToC alignment with the new Joint Analysis of Conflict and Stability review (JACS) and Overseas Security and Justice Assistance (OSJA) resulting in a more cohesive and realistic pathway from activities to long-term impact.
- Simplify indicators to be better defined with a clear description of how they will be measured and to include cross-cutting themes. A consistent baseline assessment would greatly improve the system's usability and effectiveness.

Resourcing:
- Recommend that ISF programme team appoint a dedicated PM to oversee and represent KRI at programme level in BEB.
- Investigate possibility of having a dedicated/regionally shared MEL advisor.
- Attempt to stagger ISF staff rotations/Posting timings to avoid institutional knowledge gaps.

Programme scope:
Retain TAFFI functionality, allowing for quick short-term interventions that can readily respond to emerging issues or changing contexts.
- Crucial to get early sign off from key stakeholders otherwise no matter what they propose, interventions are unlikely to be approved or be severely delayed whilst retaining assurance of process
- Can TDSP be scoped under TAFFI for future delivery?
- Scorecards could be used to assess TAV selection on x cutting themes, e.g. Conflict sensitivity. This will enable a clear approval process for TAVs to capitalise on the efficiency element that the TAFFI facility offers.

Community cohesion: currently enabled through BPSI and climate migration projects.
The team should continue even though this becomes more challenging within the context of the ISF priorities. Even with more of a hard-edge security focus, ISF Iraq still need gendered outcomes to enable sufficient focus on gender and community led engagement.

Consolidation: Given the complementarity, consider consolidating climate and BPSI programming into one funding stream, managed by one team/PM.

Procurement:
Ensure that IPs have the necessary security clearances to enable them to engage across the full range of activities, particularly when activities adjust in a responsive and agile way, e.g. ASI do not have any staff who have the necessary security clearances.