CSSF Annual Review 23/24 – Summary Sheet
Programme Title	Eastern Route (Turkey) Programme
Country and Region	Turkey
Programme ID	C-MIG-0005	IATI Unique ID	CSSF-01-000006
Start date	April 2017	End date	March 2024
HMG Partners / (Lead department in bold)	Foreign, Commonwealth & Development Office (FCDO) / Home Office
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY 2023/24	Spend FY 2023/24
ODA	£16.9m	£1.97m	£1,977,175.42
Non-ODA	£0.13m	0	0
Total	£17.03m	£1.97m	£1,977,175.42

Output statements - assessed	Individual Output Rating
Output 1.1: Presidency of Migration Management (PMM) proactively responds to irregular migration through strengthened operational and coordination capacity with primary countries of origin and with strategic partners at national, regional and international levels	3
Output 2.1: Women from refugee and vulnerable host communities in Kayseri have improved social cohesion, access to labour market and increased awareness of sexual and gender-based violence	4
Output 2.3: Afghans in Turkey have improved access to asylum and basic services in coordination with migration agencies including law enforcement	4
Output 3.2: PMM proactively respond to migration flows through human rights compliant policy making, operational and technical capacity to improve return operations and strengthened international cooperation	3
Output 4.1: Evidence is produced to guide planning and implementation of sustainable and inclusive recovery interventions in the local labour markets of the region affected by the 2023 earthquakes	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement(s)
Outcome 1: Irregular Migration. Turkey forms partnerships with the UK and key countries of origin to tackle OIC risks at the borders.
Outcome 2: Self Reliance. Non-Syrian migrants and refugees have greater access to International Protection, are informed about their rights and have better access to economic opportunities.
Outcome 3: Capacity and Compliance. Institutions have capacity to formulate and deliver evidence-based policies that are inherently human rights compliant, gender and conflict sensitive.
Outcome 4: Seed Money Evidence Base. Develop the evidence base/proof of concept for longer-term interventions that can be supported through longer-term bilateral funding.
Outcome Assessment	The CSSF 23/34 programme achieved its intended outcomes, despite the challenges presented by external factors, including the long-lasting effects of the earthquakes that took place in south-eastern Turkey and the nearby region in 2023. This is a testament to the programme’s agility and responsiveness, but the success of the programme is underpinned by the close relationship the in-country programme team sustains with government beneficiaries and implementing partners.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low/Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Green	3	Green	3	Green
Risk Rating	Low/Medium		Low/Medium		Low/Medium
Notes: Output/Outcome score: Overall, the programme successfully met its targets, but the outcome and output level indicators in the results framework could be more effective at measuring progress. A recommendation suggesting improvements to the results framework has therefore been included in this review.

## What Support Did the UK Provide in FY 23/24?
The Eastern Route (Turkey) Migration Programme is part of a multi-year programme delivered through eight projects during the financial year 2023/24. The programme has taken a whole-of-route approach in incorporating projects that:
- Developed Turkey’s ability to address its migration challenges, particularly on irregular migration (including through upstream work)
- Promoted the self-reliance of non-Syrians in Turkey
- Enabled Turkey to maintain compliance with its human rights and legal obligations – particularly around the management and return of migrants.

Five projects have been covered during the 23/24 Annual Review:
1. Strengthening Cooperation with Countries of Origin and Fostering Cooperation with Strategic Partners to prevent Irregular Migration (COMPLEMENT)
2. Multi-sectoral Approach for Fostering Resilience among non-Syrian Refugee and Vulnerable Host Communities
3. Fostering International Protection (Asylum) for the Most Vulnerable Refugees (Afghans) in Turkey
4. Pilot for the Establishment of a Screening System to identify Migrants' Protection Needs at the Borders (CONTRIBUTE)
5. Seed project: Generating evidence to support the post-earthquake recovery of the labour market

## Key Results for FY 23/24
- Under the Irregular Migration project (COMPLEMENT), enhanced returns cooperation with various countries of origin was established via a study visit to Nigeria and the organisation of irregular migration consultation meetings with representatives from Afghanistan, Morocco, Pakistan and Turkmenistan.
- Under the Fostering Resilience project, “My Life Community Centres” were established in Kayseri and Aksaray cities, within which, Turkish language courses and awareness raising sessions on social cohesion, gender-based violence (GBV) and sexual and reproductive health (SRH) were delivered to refugees and the local community.
- The Fostering International Protection project, reached 33,953 beneficiaries in total. Needs analyses and protection assessments were conducted and subsequently 28,420 beneficiaries were supported with 68,757 emergency kits, including food, clothing, hygiene and shelter. 10,642 irregular migrants were provided with protection counselling either in physical offices or by mobile teams.
- For the CONTRIBUTE project, there is good evidence that project activities supported PMM in strengthening its policy-making and operational capacity in irregular migration, risk analysis and return, in adherence to human rights and international standards. The tailor-made training sessions targeted law enforcement officials who play an active role in return processes and included teaching on human rights considerations and 91% of participants reported that they would use the knowledge gained in the training in the future. The project created a baseline for a new nationwide screening system to identify migrant protection needs that is the first of its kind in Turkey.

 Key Lessons:
The CSSF programme encompasses a wide range of interventions, including upstream work with countries of origin, social cohesion efforts, capacity building, and incubating projects to develop a proof of concept for longer-term interventions with bilateral funding. In particular, the programme has significantly supported the welfare of the vulnerable refugees and migrants fleeing conflict and instability, in turn, promoting development in the recipient country. The programme has supported Turkey in hosting its migrant and refugee population in a way that maintains social cohesion which reduces conflict between migrant and Turkish communities and addresses the risks at the borders and along the Eastern Route.

Key Recommendations for FY 23/24:
1. Results management: the programme demonstrates an ongoing commitment to manage results effectively, but inputs to the Results Framework (RF) could be standardised and more rigorously assured. It is recommended that further training sessions on the RF be provided to implementing partners and government beneficiaries following this review to ensure they are suitably equipped to complete the framework in adherence to the suggested modifications above.
2. Financial management: The programme has good tools in place to manage budgets, but there will inevitably be changes to projects caused by internal and external factors. Robust planning should be in place to prepare for variances and minimise the impact on the programme. It is recommended that there is a keener focus on 1) feasibility: agreeing a realistic level of ambition for projects in relation to the short-term nature of the CSSF programme and identifying a reasonable duration and budget in line with the requested activities; and 2) collaboration: programme design teams should try to engage early and widely with a range of people to ensure balanced perspectives and inputs.
3. Cross-cutting themes: the interaction between the programme and themes such as gender, human rights and conflict sensitivity continue to be important. The gender analysis and action plan should be refreshed to ensure an ongoing strategic approach to gender policy and programming. There is a clear demand for further sessions on gender training, so further gender-focused clinics should be provided to implementing partners and government beneficiaries.