CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Economic Deterrence Initiative (EDI) portfolio – Cross-Cutting and Capability Programme (FCDO), Trade Sanctions Implementation Programme (DBT), EDI Transport Programme (DFT), and Financial Sanctions Programme (HMT)
Country and Region	UK
Programme ID	C-EDI-0001	IATI Unique ID	CSSF-19-000001
Start date	01/04/2023	End date	31/3/2025
HMG Partners / (Lead department in bold)	FCDO, DBT, DFT, HMT, HMRC, NCA, DCMS, MOJ, DSIT
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	0	0	0
Non-ODA	£50m	£15m	£9.35m
Total	£50m	£15m	£9.35m

## Outputs
Output statements	Individual Output Rating
Streamlined licensing system reduces unnecessary burdens on legitimate business and reduces cost of compliance.	3
Guidance is more comprehensive, joined-up and accessible.	2
Regular, coordinated outreach to increase awareness and compliance, working to ensure all sanctions stakeholders benefit from engagement comparable to current financial sector outreach.	3
Implementation of certain sanctions measures is improved by ensuring access to specialist expertise from across Whitehall.	3
Enhanced powers, capability and capacity to undertake monitoring and detection of breaches of all types of sanctions measures, including leveraging all information sources.	3
Enhanced powers, capability and capacity to take forward civil monetary penalties for all types of sanctions measures where appropriate.	2
Enhanced powers, capability and capacity to take forward criminal investigations and prosecutions for all types of sanctions measures where appropriate.	3
Greater information sharing and deconfliction of cases between intelligence, monitoring and enforcement functions.	3
More robust sanctions policymaking and designations processes, based on greater capacity, capability and use of external expertise.	2
Greater capacity and specialism on handling litigation.	2
Reduced legal risks through better resourcing for legislation drafting.	3
Improved sanctions implementation and enforcement in UK Crown Dependencies and Overseas Territories.	3
Greater coordination with allies through expanded international sanctions network.	3
Overall Rating of Output Delivery	3

## Outcomes
Outcome statement(s)
Strengthened implementation of UK sanctions. Increased effectiveness and deterrent effect of UK sanctions by ensuring that those who are willing to comply with UK sanctions have the awareness and information they need to do so. Driving up compliance while removing unnecessary barriers to legitimate business.
Strengthened enforcement of UK sanctions. Increase the effectiveness and deterrent effect of UK sanctions by making it more difficult for those bound by UK sanctions to act in breach of them and taking action against those in breach.
Reduce wider sanctions risks. Building capability and professionalism required to deliver UK sanctions in a robust manner, reducing the chances of unintended consequences and mistakes and therefore reducing our policy, presentational and legal risks.
Outcome Assessment	The overall outcome score is Amber. Some good results have been achieved across the programmes already and change stories in Q1 of Year 2 (Y2) show promising results e.g. to make more effective the enforcement of UK sanctions across the Overseas Territories. ​However, while a number of the programmes are broadly on track according to basic milestones and indicators, due to delivery only getting underway during the course of the year and the fact this was always conceived of as a two-year programme, it is unclear yet whether this will lead to achievement of the high-ambition outcomes in all areas during the timeframe of the programme. In addition, programmes that started delivery later on in Year 1 (Y1) (e.g. cross-cutting, Department for Transport (DFT)) are less able to demonstrate evidence of outcome level change than those that were able to start activity earlier in the year. Notable achievements following the timeframe of this report which have significant potential to effect outcome level change include the launch of the Office of Trade Sanctions Implementation (OTSI) in October 2024 and multiple shadow fleet sanctions.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating					3	Amber
Risk Rating					M	M
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- Support to the FCDO to support robust implementation and enforcement of sanctions, underpinning their effectiveness as a tool for addressing global security and human rights by reducing the risk of legal challenge to the UK sanctions regimes and designations made under those regimes; coordinating across HMG to provide guidance to help businesses and other organisations effectively comply with sanctions; addressing capability gaps within the UK, Overseas Territories; and promoting joined-up international policy on sanctions implementation with states that are a high circumvention risk or where stronger sanctions policies are needed.
- Support to HM Treasury (HMT) to improve financial sanction enforcement and implementation, focused on enhancing the UK’s operational capability to implement and enforce its financial sanctions regime and delivering novel sanctions, such as the Oil Price Cap (OPC).
- Support to multiple departments to support improvements in trade sanctions implementation and enforcement, in order to maximise the impact of UK sanctions regimes, the central deliverable of which is the creation of a new Office of Trade Sanctions Implementation (OTSI) within the Department for Business and Trade (DBT).
- Support to DFT to enhance the UK’s ability to enforce transport sanctions via both criminal and civil law channels and improve compliance within the transport sector, with both transport sanctions and the UK’s other sanctions regimes.

## Key Results for FY 23/24

Trade sanctions programme
- Creation of the new Office of Trade Sanctions Implementation, launched on 10 October 2024, which will work with partners across government and in industry to help ensure that businesses understand trade sanctions, and that they are properly implemented and enforced.
- Additional support for HM Revenue and Customs (HMRC) to investigate and prosecute the most serious sanctions breaches.
- Work to expand the range of penalties that can be imposed for breaches of sanctions measures.

HMT programme
Reinforcement of the Office of Financial Sanctions Implementation (OFSI), particularly through enhanced capability to implement novel financial sanctions, including the Oil Price Cap.

Transport sanctions programme
- Specialist capability within the Joint Maritime Security Centre (JMSC) and the National Crime Agency (NCA), increasing the UK’s ability to detect and respond to breaches of maritime and transport related sanctions.
- Work to expand the range of penalties that can be imposed for breaches of sanctions measures.

FCDO cross-cutting programme
- Investment in building lasting sanctions capability across government, recognising the specialist skills and expertise required.
- Expansion of the network of sanctions specialists in UK diplomatic missions to build collaboration with third countries and support intensified efforts to tackle sanctions circumvention.
- Targeted technical assistance for third countries.
- Support to the Overseas Territories to strengthen their sanctions enforcement architecture.

## Key Lessons:
- The pragmatic, proportionate and risk-based approach taken by FCDO and the portfolio team enabled rapid approval of projects at the outset to ensure delivery started as quickly as possible.
- The ISF training that the portfolio team provided to some programmes and Senior Responsible Officers (SROs) was welcome and ISF Unit (ISFU) / future such portfolios should ensure ISF training is provided to all departments involved at the outset.
- Accurate forecasting across different departmental baselines, and ensuring all programme teams have a clear understanding of how to forecast, from the outset is critical to minimise underspend. Communication of deadlines and the development of a financial community of practice across EDI programmes has improved forecasting and expenditure.
- In Y1 many projects suffered from optimism bias which may have contributed to underspend. In nearly all cases delivery took longer than estimated to get underway.
- Recruitment processes often took longer than anticipated, and in many cases it was challenging to get delivery underway without programme staff (NB although DBT were able to mobilise a cross-disciplinary team and obtain business case approval within 2 months). Future programmes should factor in realistic recruitment timelines when implementing against set milestones, unless HR and security procedures can be more flexible. Delivery of two-year programmes which involve recruiting significant numbers of civil servants is likely to be challenging without more flexible HR and security procedures.
- Using civil servants was cheaper and built enduring capability, a key aim of the portfolio. Some work could also only be done by civil servants due to its nature or sensitivity. However at least one project could have been delivered quicker using external support from the outset due to multiple failed recruitments. Successful programmes used a blend of methods e.g. surging staff, managed moves, out-sourcing where contractors had expertise, and recruitment. When delivering to tight timeframes, programmes should consider all possible options for delivery.
- Diplomacy played an important role alongside/to ensure successful delivery of programmatic interventions e.g. with the British Virgin Islands (BVI), on the OPC or with third countries on circumvention.
- Departments found the cross-government way of working embedded by EDI governance mechanisms very beneficial and it helped cement the use of newer tools e.g. transport sanctions.

## Key Recommendations for FY 24/25:

Portfolio team
Ensure the portfolio team closely monitors programme spend on a monthly basis to minimise risk of underspend, as well as delivery against results frameworks more broadly. Ensure the portfolio finance team continues early and active management of emerging underspends in Y2.
Project documents within programmes
Conduct programme-level audits to identify the extent to which projects are compliant on mandatory documentation (e.g. results frameworks, risk registers, theories of change) and agree with ISFU the minimum standards of documentation that an EDI programme or project should meet.
Monitoring, Evaluation and Learning (MEL)
- Ensure the portfolio team builds capacity to provide MEL support to the programme teams to monitor and report results against results frameworks, and collect qualitative and quantitative evidence that will help demonstrate outcome-level change at the end of Y2.
- As with finance, EDI should work towards developing a community of practice on MEL. This could be done by increasing Programme Managers’ MEL capacity through training and setting up a cross-programme network of MEL Champions to share best practice.
- Consider greater use of cross-cutting programme to collect quantitative and qualitative external evidence in Y2 across all types of sanctions.
- The portfolio team should refine the Theory of Change at EDI level. The Theory of Change (ToC) does not currently outline outputs from activities and how these feed into outcomes. Assumptions underpinning causal linkages should also be fleshed out. There could also be greater clarity on how HMG’s increased capacity on sanctions will deliver change in the operational context.
- The portfolio team could generate a cross-programme results framework which could more clearly layout the causal links between programme level outputs and outcomes. It would also be opportune for the Portfolio Team to develop qualitative outcome markers for the programme. The markers could then be used for qualitative outcome monitoring at six-monthly intervals. This approach would help the portfolio to showcase progress on what the team would ‘expect to see’ ‘hope to see’ and ‘love to see’ would complement change stories developed by the programmes.
- For the next annual review, or programme completion reviews, consider separate reviews for the FCDO cross-cutting, DBT trade sanctions and HMT financial sanctions programmes (a stand-alone review is unlikely to be proportionate for the transport sanctions programme).
Value for Money
Consider portfolio level value for money against the 5 ‘E’s and the development of a value-for-money indicator at programme or portfolio level, or alternative way of monitoring value for money across the programmes as part of Y2 reporting. The Portfolio Team could bid for 10% of an economist’s time to develop value-for-money indicators. Please contact the head of profession to discuss this possibility or discuss the option with economists operating through any of the programmes.
Governance
Ensure appropriate governance arrangements are in place for those elements of the trade sanctions programme that will continue after OTSI is launched, notably the HMRC programme. Given that DBT is due to close activity after the launch of OTSI, it would likely no longer make sense for them to manage the remaining programmes. It would be opportune for alternative arrangements to be considered e.g. absorbing activity into the FCDO cross-cutting programme.

Sustainability
- Ensure the programmes have plans in place to ensure benefits are not lost following the end of EDI, and that decisions to retain or drop activity are made in a coherent manner. The portfolio board may wish to take a discussion paper on exit strategies in Q3 24/25.
- As part of sustainability, ensure the benefits of the integrated ways of working established by EDI are preserved beyond EDI whether through existing sanctions boards or bespoke mechanisms e.g. a combination of the Cross-HMG Sanctions Board (with standing agenda items on implementation, enforcement and capability), OFSI and OTSI boards plus subject-specific ad hoc working groups.
ISFU
- When setting up new portfolios, ISFU should have initial oversight of portfolio teams and SROs to ensure basic training is taken up and minimum expectations of programme set-up are made clear.
- When establishing multi-department portfolios, consider use of Memorandum of Understanding (MoU) to ensure clarity on accountability and reporting when transferring money across baselines where proportionate.