CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Sri Lanka
Country and Region	Sri Lanka, India and Indian Ocean (IIOD)
Programme ID	C-SAA-0010	IATI Unique ID	CSSF-09-000003
Start date	April 2022	End date	March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO) and Ministry of Defence (MOD)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£10,567,500	£ 3,522,500	£ 3,402,374
Non-ODA	£450,000	£150,000	£ 56,932
Total	£11,017,500	£ 3,672,500	£ 3,459,305

## Outputs
Output statements	Individual Output Rating
(No. and statement)
Mine and explosive remnants of war affected land released, Vocational training, education and psychosocial support for demining operatives.	3
Resettled communities are supported, protected and engaged in durable livelihood activities	4
Committees capacitated and mechanisms establish to carry out more effective oversight of public finance and increase engagement with marginalised people (Westminster Foundation for Democracy (WFD))	4
Civil society capacitated to work safely, remote network established, government policies strengthened to improve civil society management (United Nations Office for Project Services (UNOPS))	4
Military capacitated to promote democratic values, human rights and modern military standards (MoD)	3
Innovative pilots developed to address climate-driven conflict co-designed and implemented based on mapping, results and lessons documented and shared (International Water Management Institute (IMWI), Centre for Poverty Analysis (CEPA), Chrysalis)	4
Government, civil society and users capacitated to prevent and respond to Cyber Sexual and Gender-Based Violence (CSGBV) and trends in CSGBV monitored (Search for Common Ground (SFCG), #Generation)	3
Number of evidence products or analytical pieces developed	4
Overall Rating of Output Delivery	4

## Outcomes
Outcome statement(s)
Conflict drivers addressed through opportunities for rehabilitation & reintegration
Democratic values are supported, and independent voices are strengthened
Emerging sources of instability mitigated through innovative approaches
Outcome Assessment	The overall outcome assessment for the programme is Green. The programme is currently on track to meet or exceed two out of the three outcome targets (Outcome 1 and 3), and while there is less certainty for Outcome 2, strong progress has still been made under one of the indicators, 2.3, in which UNOPS, through its project titled ‘Vriddhi’, demonstrated that there are opportunities in Sri Lanka to support democratic values and strengthen independent voices. / As set out in last year’s review, the political and economic crisis, Official Development Assistance (ODA) funding pauses, and the diverted attention of staff due to British High Commission (BHC) Colombo Crisis Watch, all contributed towards delays in project implementation. Despite these pressures, all projects have and continue to deliver activities without notable delays or obstructions. The programme team should be praised for the progress that has been achieved in a shorter timeframe given the challenging and complex set of issues they dealt with in the first year which meant that the team were behind schedule. The team have not only overcome these challenges but ensured the programme is back on track with a significant amount of progress being achieved in FY 2023/2024. The programme team reflected that this year had gone relatively smoothly and that its relationships with both partners and the Sri Lankan government were positive and productive. This was evident in meetings with partners, and it is clear to see the programme team have cultivated constructive and collaborative partnerships with implementing organisations.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Medium

## Summary of Programme Performance
Year	2022/23		2023/24		2024/25
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3 Amber	3 Amber	4 Green	4 Green
Risk Rating	M	M	M	M
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?

Pillar 1: Conflict drivers
- Landmine Clearance. To enable protracted refugees and Internally Displaced People (IDPs) to resettle, improve livelihoods and encourage a return to stability in conflict-affected areas. Partners: The Hazardous Area Life-support Organization (HALO) Trust and Mines Advisory Group. Budget £ 1,120,000 ODA.
- Reintegration and sustainable settlement. To support for durable resettlement and reintegration for conflict-displaced refugees and internally displaced people. Partner: United Nations Development Programme (UNDP) and International Organization for Migration (IOM). Budget £700,000 ODA
Pillar 2: Reducing democratic fragility.
- Parliamentary strengthening. To build institutional trust in parliament by strengthening financial oversight and promoting inclusive processes in areas relevant to the prevailing political and economic crisis. Partner: Westminster Foundation for Democracy (WFD). Budget: £200,000 ODA
- Civil Society Organisation (CSO) strengthening. To preserve civic spaces by investing in civil society protection, performance, skills development and coping mechanisms, to enable CSO self-reliance and self-care. Partner: United Nations Office for Project Services (UNOPS) and United nations Office on Drugs and Crime (UNODC). Budget: £ 200,000 ODA
- Defence Engagement. Build military capacity to deliver against the role expected of a modern military to keep communication channels open on sensitive topics, including raising human rights issues and concerns where appropriate. Partner: UK Ministry of Defence. Budget: £150,000 non-ODA.
Pillar 3: Reducing future inter-community tensions due to climate change.
Climate/conflict. Pilot to improve water resource management while addressing local conflict issues leading to more equitable benefits to community members. Partners: International Water Management Institute (IWMI), Centre for Policy Analysis (CPA) and Chrysalis. Budget: £ 498,508 ODA.
Pillar 4: Tackling gender-based violence in society and barriers to women’s inclusion.:
Caught in the Web (CitW). To advance effective responses to Gendered Online Hate Speech (GOHS) and Cyber Sexual and Gender Based Violence (CSGBV) in Sri Lanka. Partners: Search for Common Ground (SFCG), Centre for Equality and Justice (CEJ) and Hashtag Generation. Budget: £ 326,718 ODA

## Key Results for FY 23/24
The projects achieved their milestones, in large part, and delivered core activities. Some detailed project output highlights:
Pillar 1: Addressing legacy conflict drivers.
- Landmine Clearance: To enable protracted refugees and Internally Displaced People (IDPs) to resettle, improve livelihoods and encourage a return to stability in conflict-affected areas.
  - The project has reached 6987 direct beneficiaries and 23,291 indirect beneficiaries.
  - HALO and Mines Advisory Group (MAG) have collectively cleared 460,502m2 of land leading to the safe destruction of 2469 items of Explosive Ordnance (EO).
  - From the released land, 43% (66,543m2) will be used for agriculture, 38% (58,226m2) for natural resources (wood collection, hunting and foraging), 14% (21,110m2) for access, 4% (6,816m2) for residential purposes, 0.5% for community and/or public services (1,2195m2) and 0.5% (739m2) for infrastructure.

- Reintegration and sustainable settlement. To support the durable resettlement and reintegration of conflict-displaced refugees and internally displaced people.
  - Families living in welfare camps and refugee returnees from India supported to sustainably resettle in the North and East:
  - 58 returnee families assisted to complete construction of their houses and restart lives in their places of origin.
  - 206 returnees supported with livelihood initiatives in the fisheries, livestock and agriculture sectors, and micro and small enterprises. Beneficiaries from the fisheries sector saw an increase in their monthly income ranging from 8,000 LKR – 30,000 LKR.
  - 855 returnees supported to obtain civil documents, enabling them to prove their legal identity and access essential services such as health, education, and financial services, including bank accounts and credit facilities. This also allows them to exercise their voting rights and obtain legal employment, access to land allocation schemes or property restitution mechanisms.
Pillar 2: Reducing democratic fragility.
- Parliamentary strengthening. To build institutional trust in parliament by strengthening financial oversight and promoting inclusive processes in areas relevant to the prevailing political and economic crisis.
  - Produced a study report on the cost of politics in Sri Lanka. This was disseminated among former and current provincial councillors, the media, civil society activists, members of political parties and election observers.
  - Supported the Elections Commission of Sri Lanka (ECSL) to form a joint implementation and enforcement mechanism for the Regulation of Election Expenditure Act (REEA)
  - Supported ECSL to build the capacity to highlight compliance obligations under the REEA, working with all registered political parties.
  - Supported CSO’s in developing robust monitoring methodologies to track election campaign expenditure.
  - The Economic Inclusion Working Group (EIWG) formed by the project was renamed as the Coalition of Inclusive Impact (CII) and obtained company registration to ensure its sustainability after project funding ends. The CII is grouping of members from Civil Society, Members of Parliament, media personal and academics.
  - Research reports were developed on inclusion and access gaps in the health and transport sectors. The CII designed policy briefs based on research recommendations and presented to former Minister of health and transport. As per the recommendations, the Ministry of Health committed to providing additional government medical officers to 11 clinics in the estate sector.
  - Following the launch of the research report on transport, an MP who is also a member of the CII tabled the report in parliament during the budget debates. This led to calls for the government to develop a comprehensive, integrated transport policy as recommended in the report and urged evidence-based policy-making in future planning.
  - The CII budget consultations have delivered tangible results related to period poverty - the Chair of the Committee on Public Finance (COPF) presented CII’s findings in Parliament. This intervention led to the government indicating its commitment towards allocating LKR 4 billion (GBP 9.8 million) towards providing free sanitary napkins to school children.
  - The CII held roundtable discussions with CSOs and experts on the Government’s proposed Economic Transformation Bill and also decided on approaches to work during an election year.
- Defence of civic space. Support a CSO network to preserve civic spaces by investing in civil society protection, performance, skills development, and coping mechanisms, to enable CSO self-reliance and self-care.
  - Mapping and reporting of land cases in the North-Eastern Provinces and incidents affecting Civil Society Organisations (CSOs) and the community including Anti-Terrorism Act, and emergency regulations.
  - Briefings held on cases related to land and key protection incidents in Northern and Eastern provinces for civil society, Human Rights Commissions of the respective provinces, donors and diplomats and other UN agencies.
  - Trainings, awareness raising and capacity building for members of CSOs on: access to state services and redress mechanisms; project management; grants management; social accountability and language rights; Anti-Terrorism Act; Draft Act on Non-Governmental Organizations; right to information; language rights and legislations in Sri Lanka; geographic information system mapping; MapSwipe; google workspace; and cyber security.
  - Two networking events held in North, East and Hill country to strengthen existing CSO regional networks.
  - 11 CSOs supported with small financial grants to implement projects.
- Defence Engagement. Build military capacity to deliver against the role expected of a modern military to keep communication channels open on sensitive topics, including raising human rights issues and concerns where appropriate.
  - The CSSF supported Defence Engagement via completion of the Political Economy Analysis of the Sri Lankan Defence Review and the Sri Lankan military.
  - A Sri Lankan Airforce 2* attended the Building Integrity for Senior Leadership course as part of UK support to development of accountable leadership across Sri Lankan Armed Forces.
  - Sri Lankan Navy officer has completed the Advanced Hydrographic Survey course in the UK and is now employed in a core role Hydrographic Survey role responsible for delivery of Sri Lanka’s responsibilities for Safety of Life at Sea.
  - A student has completed the Ground Sign Awareness and Counter-IED course in UK and is leading on development of a training package for Sri Lankan Armed Forces personnel to disseminate knowledge on the skills acquired to support building of the Armed Forces capabilities to identify improvised explosive hazards.
  - 24 Students from across the Armed Forces completed an International Humanitarian Law (IHL) course delivered by the International Institute of Humanitarian Law (IIHL). The course instructional staff included a female SL Air Force lawyer (former student on a CSSF sponsored course) who delivered the Gender Based Sexual Violence module.
Pillar 3: Reducing future inter-community tensions due to climate change.
- Climate/conflict. Pilot to improve water resource management while addressing local conflict issues leading to more equitable benefits to community members.
  - 6 divisional level water infrastructure project interventions benefited around 1500 paddy and livestock farmers. Increased water security reduced the potential for conflict and increased farmers’ yields and income, especially for marginalized producers.
  - 16 Climate Change Resilience Building Plan (CCRBP)s co-created with local communities and government stakeholders. This was the first experience of collective planning with government stakeholders for these communities.
  - 47 community mobilisation activities completed with 2957 direct beneficiaries to manage climate-water resource-driven conflicts.
  - Above 63 Community-Based Organizations (CBOs) were mobilized with the objective of enhancing resilience to climate change-related challenges within their respective GN divisions.
  - Due to the project interventions, 65% of the community members reported changes in their perception of technical solutions for climate-related conflict mitigation. 82% of targeted communities, especially women and youth, use technical solutions to sustain their economic activities.
Pillar 4: Tackling gender-based violence in society and barriers to women’s inclusion.
  - Caught in the Web: To advance effective responses to Gendered Online Hate Speech (GOHS) and Technology-Facilitated GBV (TF GBV) in Sri Lanka.
  - Big tech platforms started to respond to CSGBV: TikTok had a 90+% response rate and Meta 55+% to the issues CitW flagged.
  - Across Sri Lanka, CitW trained 153 women in local government and 349 lawyers on conflict sensitive and effective CSGBV response.
  - The consortium held The Learn, Collaborate and Transform forum with the participation of South Asian and South East Asian stakeholders working on the issue of CSGBV and GOHS in March 2024, in Colombo with more than 100 international participants.
  - 150 complaints received by civil society/government institutions, such as Sri Lanka Computer Emergency Readiness Team (SLCERT), about online gender hate speech and cyber SGBV that were addressed.
  - 927 of Children Desks Policewomen trained on Gender, CSGBV, GOHS, relevant cyber laws & response mechanisms, and developed Standard Operational Procedures

## Key Lessons:

- The Programme Team found that some project partners increased salaries without proper consultation. As a result, a thorough invoice checking process was implemented. Partners were instructed to provide advance notification with strong justifications for any salary increases. HALO and MAG requested an increase in daily rates, which was carefully reviewed by the FCDO commercial team. However, the request to increase staff daily rates was rejected, and the situation was handled appropriately. A financial audit of the WFD work has been initiated to ensure that the financial process was followed adequately. Adhering to the FCDO standard MoU and Grant Agreement templates without modification is recommended to make the implementers accountable in case of any disputes.
- The Programme Team and the donor community strongly believe that the Sri Lankan government should take more responsibility and lead the demining efforts. The British High Commission has been seeking opportunities to collaborate with the National Mine Action Centre and the resettlement unit under the presidential secretariat. The senior leadership of the British High Commission could emphasize the importance of the Sri Lankan government taking the lead on landmine clearance during various diplomatic discussions. BHC Colombo has initiated coordination meetings among demining donors such as Australia, the U.S, Switzerland, and Japan. This has helped the donors collectively advocate National Mine Action Centre on the challenges. Additionally, there was a shortfall of approximately £320,000 in funding for HALO & MAG, which was critical for maintaining operational and job security for over 200 staff. After confirming the request with the donors, the BHC Colombo provided the needed funding.
- From the BHC field visits and reporting from partners, the Programme Team understood that supporting and strengthening CSOs at the grassroots level is crucial. These organizations provide vital information regarding sensitive issues such as land grabbing. Given the high level of government scrutiny, building capacity in these organizations is also important. This is captured in quarterly reporting and our monitoring visit report. No adaptations were made, but their learning validates the programme’s approach to civil society.
- Monitoring election campaign expenditure is too resource, labour-intensive, and time-consuming for just one monitoring organization. Therefore, collaboration between civil society election monitoring bodies and international development partners on monitoring compliance with the Regulation of Election Expenditure Act (REEA) is crucial for the election. WFD observed this through discussions with civil society and international development partners. WFD considered the findings of the Political Economic Analysis (PEA) against a dynamic political situation and has adapted its programme in response. WFD facilitated a forum for civil society organizations working in this space to collaborate on activities rather than in isolation and duplicating activities—the joint development of the online monitoring tool results from this collaboration.
- Regional collaboration and collective bargaining are key to engaging with Big Tech companies. However, engaging with these companies during the CITW project implementation was challenging due to their limited responses and interest in addressing Technology-facilitated Gender-Based Violence (TF GBV) issues. Tech companies generally show little interest in TF GBV, focusing more on content that triggers communal violence. Additionally, due to the Online Safety Act, tech platforms have disengaged with Sri Lankan stakeholders, making engagement activities difficult. Despite attempts to engage with Meta, Google, and other tech companies, challenges persisted. It was found that there is more government buy-in when TF GBV is framed as a priority to protect children from online harm rather than as a serious concern for women. Initial discussions prioritize cyber violence against children, with the gendered nature of it explained later to ensure buy-in.
- The Programme Team was informed by the climate and conflict partners that certain project activities could potentially lead to tobacco farming in the proposed district interventions in Jaffna. This information was discovered during a field visit to the project locations. In response, the Programme Team informed the partners that according to ODA rules and the International Development Act 2002 internal policies, UK ODA is not allowed to fund the tobacco sector, including agricultural production and processing. As a result, the project was relocated from Jaffna to Kilinochchi.

Key Recommendations for FY 23/24:

Programme Narrative: For this FY, the programme could revisit the evidence and narrative between the current activities and outcomes, and highlight their links with wider Sri Lankan stability, and its role in supporting UK national security. This can include direct links, and impact, to the UK of online hate speech from Sri Lanka, or on improved economic governance to counter Chinese economic interests, or how climate security aligns with the UK’s national objectives on climate, Rules Based International Systems (RBIS) and climate leader (e.g. Community of Parties (COP)). The programme could also show it links to wider regional security, e.g. India, UK diaspora etc.

Politically Leveraging the Programme: Political colleagues and partners can be utilised more to leverage the programme and projects to maximise impact and value for HMG. While some staff and contacts already engage with the partners and projects, some projects provide more analysis, political access and influence that can help achieve or contribute towards multiple BHC Country Business goals, especially considering the relatively small footprint at Post (headcount and programme resources). This should also include influencing the new UN RC and the Peace and Development Advisor who can push UK interests through the local UN systems, and shape central UN funding, e.g. the Peacebuilding Fund’s (PBF’s) new land programme.

Post-election Political Economy Analysis and Programme Stocktake: after the result of the election, BHC Colombo should map the new government, stakeholders and policies against the programme and its stated outcomes, charting new risk or opportunities. This could involve undertaking a light touch political economy analysis for the programme, especially where government has a close link to the programme, e.g. the Resettlement Unit. Trends under the last government should also be tracked, e.g. growing identity politics. The programme should then make mitigations or adapt to move into gaps if available.

Conflict Analysis: Further work should be done to map the JACS refresh findings onto existing programmes, highlighting where both the analytic and programmatic gaps are. Longer-term, a new fresh JACS should be commissioned with a more focussed policy and programme specific lens, to understand where new ISF, or other HMG funding, is of best fit.

SOC: the JACS refresh highlighted SOC as a new and growing issue. Assess the genuine threat of SOC and its real UK linkages through further SOC analysis, including potentially a SOCJA.

Transitional Justice and Land: likewise scope the programmatic gaps for new work on transitional justice (TJ) and land, bringing in a specialist TJ and land expert for a discrete piece of analysis. The lack of TJ since the conflict is a potential driver of instability and conflict but is an exceptionally difficult area to programme in, as to be effective it usually also needs strong political will/buy in, some form of formal peace agreement or negotiated settlement and long-term programming/donor support). This recommendation suggests first scoping the feasibility of practical interventions in this space, both programmatic and political. The Programme Team should continue to assess the likelihood of impactful or politically sensitive intervention. Related, assessing ‘land’ as a conflict driver in itself would be beneficial, and scope how to tackle it as structural cause of conflict, and a source of other proximate drivers.

Monitoring, Evaluation and Learning (MEL): building on last year’s annual review recommendations on MEL, the programme should further consolidate partners results at an outcome and impact level. Share findings with Desk, across Whitehall (XWH), and likeminded to help build wider evidence bases, and crowd in funding on areas of shared interests with proven models.