CSSF Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Future Frontiers
Country and Region	Multilateral
Programme ID	C-MLS-0011	IATI Unique ID	CSSF-01-000024
Start date	April 2022	End date	March 2024
HMG Partners / (Lead department in bold)	FCDO, DSIT, Home Office, Cabinet Office, and DEFRA
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	2,229,200	1,029,200	971,820
Non-ODA	813,500	173,500	326,672
Total	3,042,700	1,188,000	1,298,492

## Outputs
Output assessment per project	Individual Output Rating
Support to Our Common Agenda – United Nations Executive Office of the Secretary General	3
Shaping Multilateral Action on Cyber, Digital and - UK Foreign, Commonwealth and Development Office and Department for Science, Innovation and Technology	4
Promoting Democratic Values in AI governance with the African Union – Organisation for Economic Co-operation and Development	4
An Inclusive United Nations (UN) cybercrime treaty – United Nations Office of Drugs and Crime	3
CGIAR: Food Security Strategic Communications Technical Assistance – Cabinet Office	4
Support to Global Digital Cooperation on Governance of Artificial Intelligence – United Nations Office of the Special Envoy on Technology	3
Support to UN Complex Risk Analytics Fund (CRAF’d) - United Nations Executive Office of the Secretary General	4
Strengthening Frameworks to Prevent Sexual Violence against Migrant Women and Girls – Organisation of American States	4
Cyber– Council of Europe	4
Strategic Foresight and Risk – United Nations Executive Office of the Secretary General	4
Overall Rating of whether the programme is delivering activities and outputs necessary for change at outcome level	4

## Outcomes
Outcome statement(s)
Increasing and improving the use of data and technology in response to traditional, emerging, and future threats
Influencing and shaping norms and frameworks for future frontiers
Embedding governance systems within future frontier norms/frameworks that are inclusive and transparent
Outcome Assessment	All projects have demonstrated progress towards impacts. It will take a longer period to be able to fully assess the scope of the individual impacts.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		Low

## Summary of Programme Performance
Year	2022/23		2023/24
	Output	Outcome	Output	Outcome
Programme Rating	3	Amber	4	Green
Risk Rating	Low		Low
Notes: Output/Outcome score

## What Support Did the UK Provide in FY22/23 and 23/24?
- Future Frontiers is a £1.2 million investment, responsive to His Majesty’s Government (HMG) priorities and Integrated Review Refresh (IRR)-identified threats. In the last two years, the programme funded projects covering all four IRR pillars, across eight multilaterals/agencies, such as the UN, the Council of Europe, the Organisation for Economic Cooperation and Development and more and integrates the work of five government departments: Foreign, Commonwealth and Development Office (FCDO), Department for Science, Innovation and Technology (DSIT), Home Office, Cabinet Office, and Department for Environment and Rural Affairs (DEFRA).
- Projects supported multilateral organisations and Middle Ground countries to develop frameworks for new and emerging technologies such as artificial intelligence and digital technologies. The programme also supported inclusive cybercrime negotiations at the United Nations while also championing Council of Europe’s Budapest Convention.
- The programme supported the use of data and strategic communications as tools for conflict prevention strengthening how multilaterals approach.
## Key Results for Financial Year 22/23 and 23/24:
- Help the UN to establish a gender and regional balanced high level Advisory Board on AI through deployment of an expert to design recommendations.
- Leveraging UK expertise on data and strategic foresight to improve UN prevention and response to crises (e.g.: the strategic foresight and risk project increased UN capacity, and the funding to the Complex Risk Analytics Fund supported both the crisis and conflict data ecosystem and UK through access to advanced datasets).
- Supported inclusive multilateralism (especially women) from Global South countries by supporting their participation in the UN cyber-crime treaty negotiations.
- Strengthened legal and normative frameworks in St. Lucia with policy and training aimed at tackling the exploitation of women and girls in the tourism sector. Similarly in Panama, the programme increased trainings and sensitisation workshops to prevent sexual violence and exploitation of migrant women and girls.

Key Lessons:
- The programme was built around new and evolving policy areas often making project interventions hard to define but also agile. As a result, the programme supported small projects across a range of IRR priorities. The programme could have benefitted from a more defined scope.
- Although small, the programme supported impactful interventions that add and compound on existing His Majesty’s Government (HMG) efforts, whether programmatic or policy. This could have been better tracked to understand the overall value of the projects especially since long-term change can be difficult to track in multilateral organisations. The programme team needed to be realistic in what the projects could achieve in a few months with small amounts of funding.
- Collectively, the projects demonstrated the UK to be a leader in cybercrime policy with its support to Council of Europe (CoE) with a UK aligned policy on cybercrime and to the United Nations Office on Drugs and Crime (UNODC). The two projects in UNODC and CoE complemented one another catalysing the impact the programme had on two major cybercrime treaty processes.
- The programme enabled and highlighted the UK’s influence as a convener as demonstrated in the Global Digital Compact, the African Union (AU)/Organisation for Economic Co-operation and Development (OECD) project and others.

## Key Recommendations for Financial Year 22/23 and 23/24:
- One pager explainer or flow chart for policy teams on how to bid, timelines, flexibility for Future Frontiers type of projects.
- A large portion of the Future Frontiers programming consists of smaller or pilot interventions. It may be beneficial to demonstrate how these fit into the larger Multilateral Strategy.
- Consider the balance for reporting requirements for short or small value investment.
- Look at whether it is feasible to use a common contract for UN projects.
- Even with this programme ending in its current form it will be important to continue to track the longer-term success of the interventions.