Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Global Pursue (GP) programme
Programme ID	C-CTP-0010
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) CT Department (CTD), Home Office CONTEST Unit (CU), Cabinet Office, Department for Transport (DfT), HM Treasury (HMT), Ministry of Defence (MoD)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
2.3.1.1. Capabilities built of land, air and maritime border law enforcement personnel.	3 (Aa)
2.3.2.1. Security, human rights and improve living conditions in North East Syria camps.	3 (Aa)
3.2.1.1. CT investigations, including to work cross-regionally in South East Asia.	2 (Ba)
3.2.2.1. Human rights compliant detention conditions and treatment and physical capacity.	2 (Ba)
3.3.1.1. Prosecutors’ and judges' capability to prosecute and sentence in CT cases.	2 (Ba)
3.4.1.1. Capacity and capabilities built on joint CT operations and CT information-sharing.	3 (Aa)
Overall Scale of Output Delivery	2 (Ba)

Outcome Assessment	In FY 20/21, GP performance held at a similar level to FY 19/20. GP was on track, with some doubts about whether intermediate outcome targets will be fully met where the coronavirus (C-19) pandemic limited HMG’s ability to monitor and advise national partners. Contribution to CT strategic outcomes overseas can be further improved.
Overall Outcome Progress Rating:		Amber (Ba)
Overall Risk Rating:		High (of human rights abuse by partners)

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	B	A	B	B	B	2 (Ba)	Amber (Ba)
Risk Rating	High	High		High		High		High
Programme changes during this period		North East Syria camps were added. Some delivery was pushed to Q3. Some countries transitioned: Somaliland Justice and Human Rights Partnership (JHRP) ending.
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

Support included four JHRPs providing end-to-end CT-within-criminal-justice-system pathway support and more targeted CT-within-criminal-justice-system support in several countries.

Key Results for FY 20/21:

A selection of results is highlighted below include:

234 arrests and seizure of improvised explosive device (IED) materiel. This included two high profile arrests of people on the run for 18 years involved in the Bali bombing which killed 28 British Nationals (BN) in 2002 and subsequent Jakarta hotel attacks. Arrests included people responsible for weapons testing, training and bomb making, and former senior leadership of terrorist groups.

12,000 extremist posts taken down by an HMG-trained social media team leading to 16 people charged, two of whom advocated for Bali-style attacks.

Communications and reconnaissance activity illuminated and disrupted a planned Bali-style attack. GP either prevented or delayed such an attack in the future.

At least one person was detained in FY 20/21 with a significant amount of explosives using skills and equipment provided by GP and denied entry to an international event.