Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	International Prevent programme (IPP)
Programme ID	C-CTP-0008
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	CONTEST Unit (CU), Home Office (HO), Foreign, Commonwealth & Development Office (FCDO), Cabinet Office (CO)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
Output 1. Partner governments in priority countries have developed an understanding of radicalisation	3 (Aa)
Output 2. Capacity of partner built in order to provide targeted support in a human rights and gender sensitive manner, to those showing early signs of radicalisation or are at risk of being radicalised	3 (Aa)
Output 3. Direct support provided to individuals or groups at high risk or showing early signs of radicalisation and vulnerability to recruitment leading to terrorism	3 (Aa)
Output 4. HMG and partner countries have an improved understanding of radicalisation and recruitment influences and mechanisms	2 (Ba)
Output 5. Work delivered to disrupt influences into/out of the UK (including preventing terrorists from using media platforms to disseminate propaganda or otherwise radicalise, recruit, inspire or incite).	1 (Ca)
Output 6. Capacity of partner built in order to provide rehabilitation/de-radicalisation support in a human rights compliant and gender sensitive manner	4 (Aa)
Output 7. Vulnerable individuals, those convicted of terrorism released from detention centres/prisons and their families are provided with a programme of support	3 (Aa)
Output 9. Cross-cutting Output: Outputs that contribute to greater conflict-sensitivity / gender-sensitivity	4 (Aa)
Output 9. Capacity of partner built in order to identify and combat flow of ideological terrorist influences across borders and deliver strategic communications	3 (Aa)
Overall Scale of Output Delivery	3 (Aa)

Outcome Assessment	The International Prevent Programme delivers against objectives in the overseas elements of the CONTEST strategy. Activities are focused on counter-terrorism (CT) priority areas identified by National Security Ministers (NSM). Terrorism undermines stability and security, and fuels conflict, in some of the world’s poorest countries. The Programme aims to reduce the threat posed by terrorist groups by working with partners to reduce terrorist intent and restrict the ability of terrorist groups to recruit and influence. / Performance of IPP in FY20/21 held at a similar level to that in FY 19/20. In 2020/2021, the IPP managed approximately 20 projects. The IPP aimed to disrupt individual intent to engage or re-engage in violence / terrorism. / The IPP made progress in a challenging context: it was particularly successful in projects working with offenders or regarding returning foreign terrorist fighters. The programme achieved some demonstrable results including evidence of reduced likelihood that individuals or groups will engage in extremist activities leading to terrorism.
Overall Outcome Progress Rating:		Green (Aa)
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	B	B	B	A	A	Green / (Aa)	3 / (Aa)
Risk Rating	N/A	N/A		High		High		High
Programme changes during this period
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

In FY 20/21, the IPP effectively delivered projects in countries that posed terrorist risks to UK interests, and to support partners overseas. The IPP is designed to reduce the likelihood of individuals or groups from engaging in terrorism. The programme advanced this objective through: (1) working with identified at risk individuals, or those showing early signs of radicalisation; (2) countering radicalising influences into the UK; and (3) disengaging, reintegrating and rehabilitating offenders including violent extremist offenders. It achieved these objectives through direct work with at-risk groups and through capacity building with partner governments.

Key Results for FY 20/21:

A selection of these results is highlighted below.

1. Reduced risk of vulnerable individuals re-engaging in extremist activities as a consequence of vocational training and other support.
2. Improved partner ability to assess risk and deliver responses around disengagement and reintegration.
3. Strengthened partner capacity to identify and provide support to individuals or groups at risk, or those showing early signs of radicalisation and recruitment leading to terrorism.
4. Improved understanding of radicalisation influences between the UK and partner countries.
5. Strengthened relationships with CT partners.