Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Counter Da’esh Communications Cell (CDCC) programme
Programme ID	C-CTP-0011
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	Foreign, Commonwealth & Development Office (FCDO), CONTEST Unit, Home Office (HO), Cabinet Office (CO), Ministry of Defence (MoD)
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
Output 1.1.1. A – Global Coalition partners have access to other members and up to date information on Da’esh.	4 (A+ a)
Output 1.1.1. B – The Cell maintains appropriate* representation of diversity in events they lead / host.	3 (Ba)
Output 1.1.2. A – Improved capacity of community organisations to deliver resilience-building initiatives.	4 (A+ a)
Output 1.1.2. B – Strategic communications challenge and undermine violent extremists.	4 (A+ a)
Output 1.3.1. – Influencers, stakeholders and journalists are given information and have access to guidance on responsible reporting.	3 (Ba)
Output 1.3.2. – Key influencers, target audiences for campaigns have access to original content and information about the Global Coalition.	3 (Ba)
Overall Scale of Output Delivery	3 (Aa)

Outcome Assessment	CDCC outcome assessment improved in FY 20/21 compared to last year. The programme demonstrably reduced vulnerability to violent extremist narratives, provided accurate and timely public health messaging at the onset of coronavirus (C-19) pandemic which countered Da’esh and Boko Haram’s efforts to exploit the pandemic and undermined support for these groups; the programme also contributed to a reduction in support for Da’esh in North-East Syria. / CDCC maintained and developed its strong and trusted platforms; communicated in support of the Coalition’s kinetic capability; highlighted Da’esh’s crimes; and supported the broader stabilisation effort by amplifying activities being undertaken by other organisations. / The programme structurally embedded relevant political access and influence outcomes and began to engage with Sub-Saharan African states to support the Coalition’s pivot into countering Islamic State West Africa Province (ISWAP), amongst others.
Overall Outcome Progress Rating:		Green (Aa)
Overall Risk Rating:		High

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	B	B	B	B	B	A	A	Green / (Aa)	3 (Ba)
Risk Rating	N/A	N/A		High		High		High
Programme changes during this period		In FY 20/21, CDCC was decoupled from the International Prevent programme; prior to FY 20/19 these formed CTPF ‘Strand 1’.
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?

The programme delivered seven core projects across three lines of effort: engagement with partners in the Global Coalition against Da’esh (the ‘Global Coalition’) to align communications efforts; public communications (public communications) to undermine the influence of Da’esh messages and increase support for the Coalition; and campaigns to challenge extremist narratives and increase resilience. CDCC worked with defined communities at risk of providing material and personnel support to terrorist groups.

Key Results for FY 20/21:

A selection of these results is highlighted below:

CDCC showed improved resilience to terrorist narratives in several countries, with the effect of undermining Da’esh ability to project a compelling narrative targeting a UK audience.

Accurate and timely public health messaging, particularly at the onset of the pandemic, helped improve credibility and trust in CDCC channels.

CDCC overachieved its targets for positive public engagement targets in several countries, contributing to a decrease in public support or sympathy for Da’esh by men in north-east and north-west Syria.

The programme led the Coalition’s Communications Working Group (CWG), convening partners to align communications efforts, and creating smaller interest-based groups to address specific crosscutting challenges, such as responsible media reporting on terrorist attacks.