Annual Review (20/21 Ver.) - Summary Sheet

Programme Title	Enablers programme
Programme ID	C-CTP-0005
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000014
HMG Partners / (Lead in bold)	CONTEST Unit (CU), Joint Intelligence Operations, Joint Terrorism Analysis Centre, Defence Intelligence, Defence Sciences and Technology Laboratory, National Security Research Group (NSRG), OSCTRA; Foreign Commonwealth and Development Office (FCDO), Home Office (HO), Ministry of Defence, British Council, Cabinet Office
Time Frame	Start Date: 1 April 2020	End Date: 31 March 2021

Outputs / Note: a For comparison with the preceding year, equivalent score using FY 19/20 scale is provided in brackets.	Scale of Delivery
A.1.(i) Increased cooperative engagement between HMG and government CT contacts.	3 (Ba)
B.1.(i). Improvements to HMG data sets in key areas of exposure and partner capability.	3 (Ba)
B.2.(i). Programme level results frameworks revised, refreshed, used by programme staff.	4 (Aa)
B.2.(ii). Staff capacity increased to use Monitoring Evaluation and Leaning (MEL) tools, incorporate best practice approaches to gender, human rights and conflict sensitivity and to improve programming on the basis of lessons learned.	4 (Aa)
C.1.(i). Effective cross-departmental work by HMG staff.	3 (Ba)
Overall Scale of Output Delivery	3 (Ba)

Outcome Assessment	Compared to FY 19/20, there was an improvement in Enablers programme performance in FY 20/21. In FY 20/21 Enablers supported delivery of CONTEST strategy overseas, contributing to improving HMG’s understanding of the terrorism threat, and the effect of CSSF programming on risk-reduction.
Overall Outcome Progress Rating:		Amber (Ba)
Overall Risk Rating:		Medium (delivery risk)

Summary of Programme Performance
Year	2016/17b	2017/18c		2018/19c		2019/20c		2020/21d
Programme Rating	N/A	N/A	N/A	N/A	N/A	B	C	3 (Ba)	Amber (Ba)
Risk Rating	N/A	N/A		N/A		Medium		Medium
Programme changes during this period		N/A
Note: b output scores; c output / outcome scores; d scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 20/21?
- In FY 20/21 Enablers supported three CONTEST strategy enablers outcomes: A, maintaining and expanding human-rights compliant partnerships amongst host nations, multilaterals and counter terrorism (CT) partners; B, helping the HMG CT community better understand the risk posed by current and future international terrorism, the most effective tools and critically, the impact of HMG actions on risks; and C, ensuring that HMG’s systems support the international CT effort.
- Enablers’ projects focussed on Europe, followed by North Africa, Asia and the Gulf. The programme also provided a central monitoring, evaluation and learning (MEL) resource to support seven CSSF programmes with MEL.

Key Results for FY 20/21:

A selection of these is highlighted below:

- The programme improved the standard of MEL across the Counter Terrorism Portfolio Fund (CTPF); better articulated individual programme contributions to CONTEST strategy outcomes; improved programme-level results frameworks (RFWs); and helped analyse impact to inform CTPF programme design, decision making and progress.
- Enablers also improved HMG’s understanding of terrorist threats overseas through liaising with cross government departments to address gaps in HMG’s understanding of terrorist groups overseas, and helped maintain and strengthen international partnerships.

Key Lessons

- Although there is appetite to improve the quality or results reporting across the programme, some projects and programmes continue to focus on delivering outputs rather than change. These projects often struggled to measure progress and articulate impact.
- The programme can help improve the quality of reporting and challenging assumptions, such as the links between training outputs, behaviour change, and the application of new skills to reduce risk to the UK.