## OIP
Odour Improvement Plan Maple Lodge STW
Review Date |  | 2023-08-24
Process Stage | Owner | Plan | Action | Expected difficulties | Measures to mitigate | Timeframe
Storm Tanks | James Howells | Ensure effective cleaning following storm | Investigation of amajet performance is now complete. Seek funding for amajet replacment/upgrade. | Funding | Manual clean as required. | AMP 7
OCU | James Howells | Action recommendations laid out by monthly health checks | Action recommendations laid out by monthly health checks | Achieving funding |  | ongoing
Sniff Testing | Odour Specliast | Implement sniff testing procedure | Procedure written for sniff testing, in order to achieve effective sniff testing personnel needs to be identified to carry out the procedure who are not acclimatised to smells on site. | Resource | OCU monthly health checks, site rounds | 6 month from permit issue