CSSF Annual Review/Programme Completion Review (23/24)
# A. Summary Sheet
Programme Title	Occupied Palestinian Territories (OPTs) and Israel Programme
Country and Region	Occupied Palestinian Territories (OPTs) and Israel, Middle East and North Africa
Programme ID	C-MNA-0023	IATI Unique ID	CSSF-06-000023
Start date	April 2022	End date	March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO); Ministry of Defence (MOD)
	Total overall Programme Allocation (e.g. 3 years) FY22 – 25)	Allocation FY2023/24	Spend FY 2023/24
ODA	£30.518m	£7.7m	7.68m
Non-ODA	£9.957m	£2m	2.04m
Total	£40.475m	9.7m	9.72m

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	4	Amber	4	Amber	NA	Amber
Risk Rating	Med-High		Med-High		High
Notes: Output/Outcome score

## What Support Did the UK Provide in FY 23/24?
- Provided mental health and psychosocial support and dignity kits support to support resilience and independence of fleeing Gazans after the outbreak of conflict
- Reduced degradation of Palestinian land and identified and improved resilience of Palestinians through: provision of free legal aid to challenge demolition and eviction orders and counter discrimination in Area C of the West Bank and East Jerusalem; provision of humanitarian support and livelihoods assistance in collaboration with other like-minded donors; and provision of electricity services and internet provision to vulnerable Palestinians to support them to remain on their land.
- Supported the Palestinian Authority Security Forces (PASF) to improve performance and service delivery and to enhance the role of civil society in the monitoring of the security forces to drive greater accountability and transparency.
- Monitoring of the conflict, including international humanitarian law, which has been critical to His Majesty’s Government (HMG)’s contextual understanding and determination of policy positions.
## Key Results for FY 23/24
- Successfully redesigned the programme to respond to the evolving context post 7th October 2023 and be better aligned with HMG’s higher policy ambition.
- On legal aid: 97% of demolition and eviction cases supported by legal aid partners were protected; 2308 Palestinians in hard-to-reach places were provided with legal aid; 30 vulnerable households were provided with electricity and 70 with internet access to support households to remain in the homes and increase resilience against evictions.
- Under the UK chairmanship of the West Bank Protection Consortium (WBPC), two member states signed new agreements, increasing the total membership of WBPC to 12 member states. The first capital-level joint statement by all 12 WBPC member states on the situation in the West Bank was issued. A joint letter was sent to the Government of Israel on increased instability in the West Bank and settler violence. Numerous other high-profile advocacy activities, high-level briefings and Ministerial visits were undertaken effectively raising the profile of instability issues in the West Bank. The unprecedented first package of sanctions against extremist settlers by the UK and other member states were initiated building on the extensive work of WBPC.
- Most peacebuilding project implementation partners continued to create spaces for Palestinians and Israelis to come together and build connections, despite heightened tensions. Two facilitators under the Search for Common Ground religious leaders’ engagement project won the prestigious award “IIE Victor J Goldberg Prize” for their work funded by CSSF. Search for Common Ground succeeded in having Lod municipality, a mixed Jewish/Palestinian city that experiences violence and tensions, adopt their religious education curriculum, developed through CSSF funding, in the schools in Lod.
- Following the closure of their activities in Gaza since October, the adaptation plans by Physicians for Human Rights Israel (PHRI) were successfully delivered, resulting in doubling their target of people they reached in Area C of the West Bank through their mobile health clinics. Medical support was extended to affected Israeli communities in the Gaza envelope and to Thai workers and other status-less groups caught up in the hostilities, demonstrating effective adaptability based on need.
- The work delivered by Capable, Accountable, Sustainable and Inclusive Palestinian Armed Forces (CASIP) on establishing the Joint Emergency Services Interoperability Principles and Incident Command led to an effective response to a large fire outbreak in Hebron (largest in the West Bank fire in 10 years). Establishment of the Joint PASS Emergency Response Capability (ERC) to effectively utilise the World Bank donated 911 Computer Aided Dispatch System included establishing and approving the legal framework by the Council of Ministers and establishing a PA budget line dedicated to the sustainability of the 911 ERC. Activating the Central Joint Operations Centre (CJOC) to monitor, analyse, evaluate, and report on security related incidents in the West Bank (and Gaza) meant that the CJOC provided flash reports on settler violence incidents to inform USSC in a swift, efficient matter – at times allowing the US 3* General to engage with senior Israeli Defence Force personnel to resolve issues as they were happening on the ground.

## Key Lessons:
- Commissioning a strategic review promptly after the context changed dramatically in October enabled the programme to be well-positioned and help set the agenda with informed analysis.
- Importance of being alert to project work not dictating policy development.
- The usefulness of designing and having access to a flexible funding mechanism in fluid, fast moving, conflict affected environments (i.e. the new Stabilisation Response Mechanism).
## Key Recommendations for FY 23/24:
- Continue to take an adaptive, flexible approach to programming risks and opportunities. The new programme, especially the Stabilisation Response Mechanism (SRM), should enable this.
- Keep on making use of the higher risk tolerance threshold to push the programme into spaces that influence 1. HMG policy thinking and decision-making; 2. Israeli and Palestinian positions/thinking.
- Engage fully in HMG scenario planning processes to ensure programmatic options are well understood.
- In future, refrain from continuing project work which is underperforming for the sake of policy/programme requirements (i.e. on Gender Equality and Social Inclusion (GESI)-E) and engage early with relevant central advisers.
- When capacity allows, consider adopting a stability tracker to allow real-time understanding of conflict developments and opportunities.
- Given current context, continue to consider additional activity in the West Bank.
- Consider prioritising joint working and increased communications (both ways) with colleagues working on CASIP and use key personnel changes within CASIP and British Consulate General Jerusalem (BCGJ) to re-establish routines.
- CASIP: review to take place.
- With increased capacity in the team now, ensure communication with implementing partners is regular and they are kept abreast of changes to funding.
- Plan for potential departure of Programme Adviser Deployable Civilian Expert (DCE); ensure orderly handover and duties and relationships are passed over.
- Increase engagement with Taskforce in London, especially around stabilisation, security and governance in Gaza as well as responding to the deteriorating security situation in the West Bank and increased settler violence.