## GMCA
Annex A: Greater Manchester Combined Authority - £1,070m City Region Sustainable Transport Settlement	Greater Manchester Combined Authority's (GMCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. GMCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.	*Indicates schemes are retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
Electric Vehicles (EV) Buses	Delivery of Electric Vehicle buses	GM Wide	Aug-22 (assumed start of project delivery was the placement of the order as this relates to procurement of electric buses following approval from GMCA on 29/07/2022).	Mar-25
Golborne Station*	Scheme to provide new station at Golborne and necessary car park enhancements, active travel, highways interventions, public realm etc. as part of Golborne masterplan.	Wigan (Golborne)	Aug-25	Aug-26
Bury Interchange*	Delivery of a new Interchange at Bury with significantly improved passenger facilities for bus, Metrolink and active travel. It will be designed in accordance with decarbonisation and sustainability principles and deliver journey time improvements for passengers. These features along with increased safety, security and accessibility will encourage mode shift to public transport. The Interchange will accommodate future growth in public transport and as a key component in Bury's Town Centre Masterplan (March 2022), will act as a catalyst for regeneration in the area. *As agreed with DfT, the Scheme Opening date will go beyond the current CRSTS funding period with an estimated completion date in 2030, and not 31/03/27.	Bury	Aug-26	Mar-27
Next Generation Vehicles*	Procurement of up to seven new tram-train vehicles for use on the Pathfinder North tram-train scheme between Oldham and Bury via Rochdale and Heywood. *As agreed with DfT, the Scheme Opening Date will go beyond the current CRSTS funding period with an estimated completion date, subject to Network Rail programme, in 2029 and not 31/03/27.	Oldham, Rochdale, Bury and Manchester	Sep-26	Mar-27
Pathfinder - Infrastructure*	Delivery of tram-train infrastructure between Oldham, Rochdale, Heywood and Bury (26 km) to support implementation of Next Generation Vehicles. *As agreed with DfT, the Scheme Opening Date will go beyond the current CRSTS funding period with an estimated completion date, subject to Network Rail programme, in 2029 and not 31/03/27.	Oldham, Rochdale, Bury and Manchester	Apr-25	Mar-27
Future Quality Bus Transit (QBT) Corridor: Bury-Rochdale (including Rochdale: Heywood Streets for All)	Scheme to develop Quality Bus Transit Corridor between Bury and Rochdale (11km)	Bury / Rochdale	Jan-24	Mar-27
Future Quality Bus Transit (QBT) Corridor: Ashton-Stockport	Scheme to develop Quality Bus Transit Corridor between Ashton and Stockport (13km)	Tameside / Stockport	Jan-24	Mar-27
Future Quality Bus Transit (QBT) Corridor: Wigan-Leigh	Scheme to develop Quality Bus Transit Corridor between Wigan and Leigh	Wigan	Jan-24	Mar-27
Initial phased delivery of Wigan-Bolton Corridor	Scheme to develop Quality Bus Transit Corridor between Wigan and Bolton (16km)	Wigan / Bolton	Jan-24	Mar-27
Initial phased delivery of Rochdale-Oldham-Ashton Corridor	Scheme to develop Quality Bus Transit Corridor between Rochdale, Oldham and Ashton (15km)	Rochdale / Oldham / Tameside	Jan-24	Mar-27
City Centre Bus Strategy Phase 1	Provides bus priority measures in Manchester City Centre	Regional Centre	Jul-25	Mar-27
Initial phased delivery of Salford Crescent-Media City UK Corridor	Delivery of new Quality Bus Transit (QBT) corridor between Salford Crescent and Media City (4.9km) involving a range of bus priority measures and schemes to improve bus stops.	Salford (Crescent / Media City)	Jan-24	Mar-27
Sale West to Altrincham Network Improvements	Active travel and bus priority measures to support delivery of housing allocation	Trafford	Apr-24	Mar-26
City Centre Radials: A662 Ashton New Road	Delivery of new bus priority measures on the A662 Ashton New Rd corridor into and out of the Regional Centre	Regional Centre	Jul-25	Mar-27
City Centre Radials: A664 Rochdale Road	Delivery of new bus priority measures on the A664 Rochdale Rd corridor into and out of the Regional Centre	Regional Centre	Jul-25	Mar-27
City Centre Radials: A62 Oldham Road	Delivery of new bus priority measures on the A62 Oldham Rd corridor into and out of the Regional Centre	Regional Centre	Jul-25	Mar-27
City Centre Radials: A6 Stockport Road	Delivery of new bus priority measures on the A6 Stockport Rd corridor into and out of the Regional Centre	Regional Centre	Jul-25	Mar-27
City Centre Radials: B117 Wilmslow Road	Delivery of new bus priority measures on the B117 Wilmslow Rd corridor into and out of the Regional Centre	Regional Centre	Jul-25	Mar-27
Bus Pinchpoint Fund (Rolling Programme)	Range of measures to reduce delays to buses and increase bus service reliability	GM Wide	Apr-22	Mar-27
Bus priority signing and lining (Rolling Programme)	Range of measures to improving signing and lining arrangements to support use and enforcement of bus priority measures such as bus lanes	GM Wide	Apr-23	Mar-27
Bus Stop Enhancement Programme (Rolling Programme)	Range of measures to enhance level of facilities provided at bus stops	GM Wide	Oct-23	Mar-27
Intelligent Transport Systems (ITS) Enhancements (Rolling Programme)	ITS programme delivers a software platform to integrate walking, cycling, bus, tram and highway data. Scope also includes delivery of infrastructure such as ATC's, CCTV.	GM Wide	Aug-23	Mar-25
Integrated Ticketing and Information	Delivery of technology and systems to support integrated ticketing and information	GM Wide	Mar-24	Mar-26
Bus Franchise Depots	Delivery of depots to support bus franchising	GM Wide	Sep-23	Mar-25
Depot Charging Infrastructure	Delivery of electric vehicle charging infrastructure at bus depots	GM Wide	Jan-23	Mar-25
Deliver a number of the remaining Access for All (AfA) stations	Deliver improved access to stations as part of Access for All programme. Stations could include: Reddish North, Hindley, Bryn	Reddish North, Hindley, Bryn	Jan-25	Mar-26
Deliver Daisy Hill and Irlam Access for All (AfA) stations	Deliver improved access to stations as part of Access for All programme. Stations include Daisy Hill and Irlam	Bolton / Salford	Mar-24	Mar-25
Develop and deliver Swinton Access for All (AfA) scheme	For Swinton station, progress the detailed design, surveys & cost plans for submissions and approvals encompassed by the Network Rail Governance for Railway Investment Projects (GRIP) stages 3 to 8	Salford (Swinton)	Jan-25	Mar-26
Develop further Access for All (AfA) schemes (Development Only)	Progress development of further Access for All improvements at rail stations	GM Wide	Development only	Development only
Station improvement regeneration and development	Provides support for delivery of new homes near new or existing rail stations	Cheadle Hulme, Hazel Grove, Navigation Road	Jun-25	Mar-27
Tameside: Hattersley Station Improved Access	Provides new pedestrian bridge (with step free access to rail platforms) to link station with new development at Godley Green Garden Village	Tameside (Hattersley)	May-25	Mar-27
Development of new stations	Further work to develop schemes to provide new stations across Greater Manchester. Potential locations include Kenyon Junction, Slattocks, Gamesley, Stanley Green and Little Hulton	GM Wide	Development only	Development only
Stockport Station	To continue to progress design and development activity for Stockport Station to a single preferred option	Stockport	Development only	Development only
Tyldesley Travel Hub / Park & Ride (P&R)	Scheme provides for the development and delivery of a Travel Hubs / P&R facility to improve access to, and reach of, the guided busway services.	Wigan (Tyldesley)	Jan-26	Dec-26
Programme of Travel Hubs / Park & Ride (P&R) at Stations and Stops	Scheme provides for the development and delivery of a programme of Travel Hubs / P&R to improve access to, and reach of Rapid Transit (Metrolink, suburban rail, guided busway) services across Greater Manchester.	GM Wide	Apr-26	Mar-27
Develop Potential New Guided Busway Stop - Mosley Common	Development of New Guided Busway Stop and Travel Hub to support the North of Mosley Common Places for Everyone (PfE) housing allocation. As a key component of the wider Bee Network, the stop will encourage mode shift to public transport for the adjacent residential led development site. The facility will be designed in accordance with decarbonisation and sustainability principles.	Wigan	Development only	Development only
Development of Potential New Metrolink Stops: Sandhills	Development of new Metrolink stop at Manchester (Victoria North). As a key component of the wider Bee Network, the stop will encourage mode shift to public transport for the adjacent residential led development site. The stop will be designed in accordance with decarbonisation and sustainability principles and aims to act as an enabler/accelerator for the surounding regeneration scheme comprising of approx 15,000 residential units.	Manchester	Development only	Development only
Development of Potential New Metrolink Stops: Elton	Development of a new Metrolink stop and travel hub/park and ride at the Places for Everyone allocation site at Elton Reservoir (Bury). As a key component of the wider Bee Network, the stop will encourage mode shift to public transport for the adjacent residential led development site. The stop will be designed in accordance with decarbonisation and sustainability principles and aims to act as an enabler/accelerator for the Places for Everyone allocation site comprising of approx 3,500 homes, three schools and local centres.	Bury	Development only	Development only
Development of Potential New Metrolink Stops: Cop Road	Development of a new Metrolink stop and travel hub/park and ride at the Places for Everyone Broadbent Moss (Oldham) site allocation. As a key component of the wider Bee Network, the stop will encourage mode shift to public transport for Broadbent Moss (1,450 homes, local centre) and the adjacent Beal Valley (480 homes) residential led allocation sites. The stop will be designed in accordance with decarbonisation and sustainability principles and aims to act as an enabler/accelerator for the Places for Everyone allocation sites.	Oldham	Development only	Development only
Metrolink Stop Improvements	Scheme seeks to support patronage recovery on the Metrolink network, including measures to address safety, security and access issues associated with ageing ex-heavy rail infrastructure. Initial proposals will focus on Bury and Heaton Park stops.	Bury	Jan-26	Mar-27
Development of long term rapid transit options	Preparation of feasibility studies etc. to support development of, and protect routes for, long-term rapid transit options across Greater Manchester.	GM Wide	Development only	Development only
Powers for 1 scheme and development for 2 schemes	Development of a Powers application for 1 scheme and pre-Powers development for 2 schemes.	GM Wide	Development only	Development only
Stockholm Road Bridge	Scheme will provide sufficient lateral clearance to accommodate a future tram-train track to the north of the existing heavy rail tracks. The bridge will also accommodate a 6.5m carriageway and 2no. 2m footways	Stockport	Dec-24	Nov-25
Greek Street Bridge	Scheme will provide an additional twin track alignment for future capacity improvements such as the proposed Stockport to Airport tram-train/metro route.	Stockport	Oct-25	Feb-26
Design and Development work on Metrolink and High Speed Stations	Design and Development work on Metrolink and high speed stations, station integration, costing and funding, and wider connectivity Packages for stations at Piccadilly, Airport, Wigan and Stockport.	GM Wide	Development only	Development only
Deferred and further renewals 2025+	Renewals of Metrolink network from 2025 onwards	GM Wide	Apr-25	Mar-27
Prioritised renewals 2022-2025	Renewals of Metrolink network from 2022 to 2025	GM Wide	Apr-22	Mar-25
Approved but unfunded schemes in MCF programme	Programme of 13 active travel schemes to be delivered across GM to improve facilities for pedestrians and cyclists, as part of a pipeline approach to active travel capital delivery.	GM Wide	Apr-24	Mar-27
Bolton: Farnworth Street for All (S4A) Town Centre Scheme	Delivery of a Streets for All design for Farnworth Town Centre High Street, reallocating road space to improve public realm for walking and cycling in support of a wider Future High Streets funded scheme	Bolton (Farnworth)	Mar-25	Mar-26
Bolton: Town Centre Package including Topp Way / Higher Bridge Street	Improvements focus on Active and Sustainable Travel and support Master Plan proposals for improved pedestrian and cycle connectivity between Bolton University / College campus and the town centre and public transport hub	Bolton Town Centre	May-25	May-26
Bury Town Centre Scheme (over and above interchange works)	Redesign of highway measures to the south of Bury town centre to improve bus priority and pedestrian and cycle connectivity across A58 and to /from proposed new interchange	Bury Town Centre	Jan-25	Mar-27
Bury: Radcliffe Town Centre Development	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Bury (Radcliffe)	Jan-25	Mar-27
Bury: Ramsbottom Town Centre Development	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Bury (Ramsbottom)	Jan-25	Mar-27
Manchester: Ancoats Streets for All	Traffic management measures to complement delivery of Ancoats mobility hub and improve facilities for pedestrians and cyclists	Manchester (Ancoats)	Jan-25	Mar-26
Manchester: Transforming Deansgate (Streets for All)	Scheme to provide car-free Deansgate improving facilities for pedestrians and cyclists and bus services	Manchester City Centre	Dec-25	Mar-27
Oldham: Town Centre - Accessible Oldham Phase 2	Redesign of highway arrangements in town centre to improve walking and cycling facilities	Oldham Town Centre	Mar-25	Jul-26
Rochdale: Heywood Streets for All	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority - scheme subsumed into Future Quality Bus Transport Bury Rochdale (Line 9)	Rochdale (Heywood)	Scheme subsumed within the Future QBT Corridor: Bury-Rochdale	Scheme subsumed within the Future QBT Corridor: Bury-Rochdale
Rochdale: Littleborough Streets for All	Redesign of highway arrangements in town centre to improve walking and cycling facilities and to provide improved bus priority	Rochdale (Littleborough)	Sep-24	Mar-26
Rochdale: Middleton Streets for All Phase 1	Redesign of roundabout in town centre to improve walking and cycling facilities	Rochdale (Middleton)	Mar-25	Mar-26
Stockport Interchange	Cycle ramp to be provided as part of new interchange	Stockport	Jan-23	Apr-24
Stockport: Town Centre West	Active travel and bus priority measures to support delivery of housing allocation	Stockport	Jun-24	Jan-26
Stockport: Greek Street Bridge Streets for All	Scheme provides new pedestrian and cycle bridge as part of wider transport scheme	Stockport	Jul-26	Mar-27
Bolton: De Havilland Way	Scheme provides for active travel along corridor to support modal shift	Bolton	Jul-25	Mar-27
Oldham Mumps Corridor Improvements	Active travel and bus priority measures to support delivery of housing allocation	Oldham	Apr-25	Mar-27
Oldham: Beal Valley & Broadbent Moss - Greenway Corridor	Active travel and bus priority measures to support delivery of housing allocation	Oldham	Mar-25	Mar-27
Salford: Peel Green Active Travel Scheme	Scheme provides new active travel routes to development site	Salford	Nov-24	Mar-27
Salford: Quays Northern Access (Broadway/S Langworthy Road)	Scheme provides new access to development site to support active travel and bus services	Salford	Nov-24	Mar-27
Stockport: A6 / Manchester Road / School Lane	Scheme proposes active mode and bus priority measures in Key Route Network (KRN) corridor	Stockport	Mar-24	Mar-25
Stockport: Bredbury Economic Corridor Improvement (BECI) Package	Scheme proposes active mode and bus priority measures to support new employment developments	Stockport (Bredbury)	Mar-24	Mar-26
Stockport: Hempshaw Lane	Highway safety scheme for location with poor safety record (especially pedestrians)	Stockport	Jul-24	Mar-25
Tameside: A560 Stockport Road	New segregated cycle lane between Hattersley Viaduct and M67 J4	Tameside (Hattersley)	Jan-26	Mar-27
Trafford: Carrington Sustainable Transport Measures	Scheme to deliver improved bus route to/from an isolated community whilst also allowing for traffic calming and improved sustainable transport access on the existing A6144.	Trafford (Carrington)	Mar-26	Mar-27
Wigan: A577 Complementary Works	Reallocation of carriageway space at locations from Pemberton to Atherton for bus priority, cycling and walking.	Wigan	Development only	Development only
Wigan: A580 Lane Head Improvements	Scheme proposes active mode and bus priority measures to tackle the poor air quality issues within the corridor.	Wigan	Oct-25	Mar-27
Electric Vehicle Charging infrastructure (EVCI) Match funding	Support for delivery Electric Vehicle Charging Infrastructure across GM with a potential focus on employment locations	GM Wide	Oct-23	Mar-25
Consolidated Highway Maintenance (Needs, Incentive & Potholes)	Ongoing maintenance work across Greater Manchester to maintain quality of road network	GM Wide	Jul-22	Mar-27
Bolton - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Bolton	Jul-22	Mar-24
Bury - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Bury	Oct-22	Mar-27
Manchester - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Manchester	Mar-23	Mar-25
Oldham - Manchester Street Viaduct	Refurbishment of viaduct to ensure ongoing operation of road network	Oldham	Jun-24	Mar-26
Rochdale - Queens Park Bridge Refurbishment & Key Route Network (KRN) carriageway	Refurbishment of bridge to ensure ongoing operation of road network	Rochdale	Jan-24	Mar-25
Salford - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Salford	Sep-23	Mar-27
Stockport: Greek Street Bridge Streets for All	Ongoing maintenance of bridge as part of wider transport scheme for Greek Street Bridge	Stockport	Jul-26	Mar-27
Tameside - Hattersley Viaduct Refurbishment and Widening	Refurbishment of viaduct and incorporation of improved cycle facilities	Tameside	Jan-26	Jan-27
Trafford - Key Route Network (KRN) Carriageway and Structures	Ongoing maintenance to improve quality of Key Route Network + works to structures in need of refurbishment	Trafford	Jan-23	Mar-25
Wigan - Key Route Network (KRN) Carriageway	Ongoing maintenance to improve quality of Key Route Network	Wigan	Sep-22	Mar-25
Integrated Transport Block (ITB) - Minor Works	Ongoing minor works to improve quality of road network	GM Wide	Sep-22	Mar-27
Integrated Transport Block (ITB) - Public Transport	Ongoing minor works to improve the quality of public transport network	GM Wide	Sep-22	Mar-27
Transforming Cities Fund 2 (TCF2) Development	Initial scheme development.	GM Wide	Development only	Development only

## LCRCA
Annex A: Liverpool City Region Combined Authority - £710m City region Sustainable Transport Settlement	Liverpool City Region Combined Authority's (LCRCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. LCRCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.	*Indicates schemes are retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
Independently Powered Electric Multiple - Unit (IPEMU) – Network Expansion*	Expansion of the IPEMU project to fit Merseyrail trains with battery technology to enable services to run beyond the end of the existing network, enabling the new 777 Class Rolling stock to be deployed on a range of routes.	Liverpool City Region-wide	Apr-26	Mar-27
Liverpool Baltic Rail Station*	Delivery of a new rail station in the Baltic Triangle area of Liverpool with a 15-minute peak time frequency which provides direct rail access to the city centre’s growing creative and digital cluster. Scheme has been increased to include active travel improvements to the main link roads around the station.	Liverpool	Jun-24	Jun-27
Local Cycling and Walking Infrastructure Plan (LCWIP) Phase 3	Delivery of the third phase of high-quality walking and cycling network in line with the LCWIP, LTN 1/20 compliant active travel connectivity, Access for All and Green Bus Routes across the City Region.	Liverpool City Region-wide	Jun-24	Jun-26
Key Route Network (KRN) Levelling Up	Delivery of a programme of KRN upgrades to provide a high-quality highway network for travel by bus, walk and cycle and reduce negative noise and air quality issues for local communities.	Liverpool City Region-wide	Apr-22	Mar-26
Highways Maintenance	A series of maintenance packages will deliver key improvements to the city region’s highway network and transport systems.	Liverpool City Region-wide	Apr-22	Mar-27
Non-Highways Maintenance	This is a supporting maintenance programme that will improve the MCAs ferry, bus and rail assets.	Liverpool City Region-wide	Apr-22	Mar-27
Transforming Cities Fund - Headbolt Lane Station	A new rail station providing an alternative to the car for people making longer journeys to and from Kirkby local centre, with supporting active travel links to and from the station.	Liverpool City Region-wide	Mar-22	Oct-23
Transforming Cities Fund – Active Travel	Delivery of high-quality walking and cycling network in line with our LCWIP, LTN 1/20 compliant active travel connectivity across the City Region.	Liverpool City Region-wide	Jul-19	Sep-23
Transforming Cities Fund – Hydrogen Buses	Provision of 20 hydrogen buses on the Liverpool – St Helens 10A corridor, which will provide a high-quality passenger journey with significantly reduced carbon emissions.	Liverpool City Region-wide	Mar-23	Dec-23
Birkenhead Central Gateway	LTN 1/20 compliant new and upgraded walking and cycling links. Supports sustainable access to key regeneration sites in central Birkenhead.	Wirral	Feb-24	Mar-27
St George's Gateway	LTN 1/20 compliant new and upgraded walking and cycling links which will link the city centre with Childwall.	Liverpool	Jun-24	Jun-26
Cross River Connectivity	Introduction of new tolling system at Kingsway Tunnel. Removal and reconfiguration of supporting infrastructure.	Wirral	Apr-24	Mar-27
Local Cycling and Walking Infrastructure Plan (LCWIP) Phase 2 (Runcorn - Daresbury)	LTN 1/20 compliant active travel route connecting Runcorn with Sci-Tech Daresbury.	Halton	Feb-23	Sep-25
Runcorn Station Quarter Phase 2	A rebuild of Runcorn Station building with enhanced active travel links connecting to Runcorn.	Halton	Jul-24	Mar-27
Runcorn Busway Active Travel Corridor	Extension of Active travel, and creation of a new active travel route into a new housing area.	Halton	Apr-24	Mar-26
East Runcorn Connectivity	An integrated cycle network of LTN 1/20 compliant routes connecting communities, businesses and major multimodal interchanges.	Halton	Apr-25	Mar-27
Green Bus Routes (86)	A Green Bus Corridor in Liverpool with faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool	Apr-26	Mar-27
St Helens Town Centre Multimodal Interchange	Multimodal intervention in St Helens town centre. Enhancements to the bus station area. Active travel infrastructure around the town.	St Helens	Jan-25	Mar-27
Active Travel Improvements M57 J4	Delivery of high-quality walking and cycling network in line with our LCWIP, LTN 1/20 compliant. Connecting Knowsley and Liverpool across M57 J4.	Knowsley	Apr-24	Jun-25
St Helens North Housing Access	Improved LTN 1/20 compliant active travel connectivity between St Helens town centre and Cowley Hill development site.	St Helens	Feb-24	Jan-26
Huyton Active Travel Corridor	Improved LTN 1/20 compliant active travel connectivity between Huyton and local employment sites. Increased to include Active travel connections at Tarbock Island.	Knowsley	Jan-24	Mar-25
Green Bus Routes (10a)	Delivery of a new Green Bus Corridor between Liverpool and St Helens offering faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Knowsley and St Helens	Jan-22	Mar-26
Southport Eastern Access	Junction and roundabout improvements supporting active travel with segregated cycle facilities and additional crossings.	Sefton	Aug-24	Mar-27
Stanley Dock Rail Access (Sandhills)	Expansion of station capacity at Sandhills to support the development of Liverpool Waters.	Liverpool	Jul-24	Jul-25
Maritime Corridor	Enhanced multimodal connectivity along the Maritime Corridor in Sefton.	Sefton	Apr-24	Dec-26
Green Bus Routes (53)	Delivery of a new Green Bus Corridor between Liverpool and Sefton providing faster and more reliable journey times, enhanced journey quality and ticketing.	Liverpool, Sefton	Apr-25	Mar-27
Smart Ticketing	Proposal to fund a tap and go ticketing solution for use across the Merseyrail rail network, acting as a single operator, single mode ticketing solution. Aims to achieve the wider vision for a multi modal, multi operator tap and go ticketing solution, which is being considered at a national level.	Liverpool City Region-wide	Jul-23	Mar-26
Inaccessible Stations	To install new fully accessible lifts at a number of LCRCA Rail Stations	Liverpool, Wiral, Halton, St Helens	Apr-24	Mar-27
Reinstatement of LCC Bus Lanes	To reintroduce Bus Lanes on key strategic routes in the city to support the Green Bus programme of works	Liverpool	Sep-24	Sep-25

## SYMCA
Annex A: / South Yorkshire Mayoral Combined Authority - / £570m City Region Sustainable Transport Settlement	South Yorkshire Mayoral Combined Authority's (SYMCA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. SYMCA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.	*Indicates schemes are retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
CRSTS 22/1 Zero Emission Buses - Phase 1	Complementary to the submission for DfT Zero Emission Bus Regional Areas (ZEBRA) funding and earmarked gainshare funding, this allocation will enable the procurement of electric, zero-emission buses, including Community Transport and provision of charging infrastructure at Interchanges, on street and at depots to facilitate the goal of operating a zero emission fleet.	Across South Yorkshire	Apr-23	Nov-23
CRSTS48 Gateway East*	Stage 1 of Gateway East rail will see the construction of a railway station that would consist of: / Two platforms each 100m long with passive provision for extension to 150m long; / Lifts, stairs and overbridge; / Station building; / Station forecourt including: / *Bus stops for terminal shuttle buses and local services; / *Set-down and pick-up areas; / *Taxi rank; / *Cycle parking; and / Station car park notionally at 50 spaces	DSA airport, DN9 3XA	TBC	Full scheme (i.e. not just stage 1) post 2027
CRSTS51 Railway reinstatement: North Barnsley to Wakefield via Royston - Phase 1*	The restoration proposal for the North Midland Line is to run passenger services from Barnsley to Wakefield Kirkgate via the semi-operational freight route from Wakefield to Lundwood. This could form the first phase of a more fundamental reinstatement between Lundwood and Barnsley and / or Lundwood and Swinton on disused tracks. Currently, the route is a single track, infrequently used freight line, which runs parallel to parts of the National Cycle Network. (funding for development only) / *Scheme retained by DfT and subject to business case approval by HMG	Barnsley, Royston, Wakefield	Development Only	Development Only
CRSTS52 Rotherham Mainline Station: tram-train development*	The CRSTS contribution is for the initial Outline Business Case development work for the integrated tram-train and mainline station project. Funding for further development of this scheme is subject to HMG approval. (funding for development only)	Rotherham, S60 1SD	Development only	Development only
CRSTS 54-58 Mass Transit	Existing DfT retained scheme consisting of 5 elements: / 1. Replacement of tram slab, rails, points and strengthening of key structures and improvement of turnback facilities. 2. Additional and refurbished sub stations / Floating Earth System 3. Refurbishment and/or replacement of vehicles subject to the results of imminent assessment of existing fleet including new Vehicle Information System and Automatic Vehicle Location System. 4. Includes new shelters; CCTV, Passenger Information Points; seating; passenger information improvements, plus improvements to pedestrian crossing points to ensure they meet current LRSSB Guidance. 5. Improve existing layout and systems where required, look to increase sustainability (solar, grey water recycling etc) Includes improvements to Paint Shed.	Sheffield / Rotherham	Jul-25	Mar-27
CRSTS01 A61 Active Travel - Barnsley – Royston via Smithies - Phase 1	An active travel scheme which provides 7.5km of new on and off road cycle routes. Full scheme is sequenced in two phases with phase 2 currently within the over-programming list and includes new pedestrian / cycle crossings at key junctions and decking of an existing disused rail bridge providing better connectivity. Also ties into the A61 Royston Bus Priority measures scheme being delivered by SYMCA.	Barnsley (S70) and Royston (S71)	Feb-25	Aug-25
CRSTS02 Active Travel Cross city connections Sheffield	A series of scalable active travel network improvements which will plug the gaps within Sheffield City Centre to the radial cycle links. Maximise connections with existing schemes and consider options to connect other key destinations within the city centre.	Sheffield City Centre	Oct-25	Mar-27
CRSTS03/2 Elsecar Active Travel Hub	The scheme will convert a unit at the council owned Elsecar Heritage Centre into an Active Travel Hub. The heritage centre is located just off of the B6097 (Wentworth Rd.) and has many buildings on its site. The scheme will refurbish an existing building, make it DDA compliant, provide safe and secure storage for cyclists using the rail station and provide bike loan / hire for local residents.	Elsecar (S74)	Apr-25	Jul-25
CRSTS03/3 Bikeworks Active Travel Hub	The scheme will increase / improve the offer in the existing Active Travel hub at the Interchange by expanding into adjacent vacant units, reconfiguring the space, taking the running of the Hub in house and undertaking a refurbishment / rebranding exercise with new stock and facilities	Barnsley Town Centre (S70)	Jun-24	Aug-24
CRSTS04/14 Northern Communities	The Northern Communities schemes will provide active travel and public transport improvements along the A6135 corridor and surrounding northern communities in Sheffield. The schemes intend to improve bus and active travel routes and infrastructure along the A6135 corridor and surrounding communities. / The bus priority element includes scalable improvement along the A6135 corridor from Sheffield City Centre to the northern communities of Chapeltown, Ecclesfield and Firth Park via the Northern General Hospital (NGH). There will also be an opportunity to improve connecting infrastructure such as bus stops, waiting restrictions and other traffic management opportunities. / The active travel element includes a series of scalable network improvements connecting Sheffield city centre with the Northern General Hospital (NHG), and onward to surrounding communities. The project seeks to integrate active travel with the bus corridor to provide a sustainable transport route to NGH and improved local access to district centres as well as strategic connections into the city and area of high employment.	Sheffield City Centre to Northern General Hospital	Jul-25	Mar-27
CRSTS05 - Worsbrough - Wombwell TPT Links	This project will deliver active travel infrastructure improvements to a 5km section of the Trans Pennine Trail between Haverlands Lane, Worsbrough and the TPT junction at the north of the principal town, Wombwell. Currently the routes infrastructure is inconsistent and unsuitable for some users, with irregular surfacing, widths and drainage issues.	Wombwell (S73) Worsbrough (S70)	Aug-24	Nov-24
CRSTS08/1 Darton Active Travel Link	The Darton Active Travel Route (DATR) is a package of measures which seeks to promote walking and cycling connectivity between ‘The Yorkshire Sculpture Park’ located at J38 M1 and the proposed A61 Active Travel Route. The scheme will deliver: / • 4.8km route which consists predominantly of 4.5km off-road and approximately 300m of shared use footway built towards LTN 1/20 standards where possible / • Improvements to pedestrian crossing locations / • Improvements to two footbridges / • Wayfinding signage / • Improvements to public realm / • Resurfacing of existing sections of the routes / • Provision and improvements to lighting	Barnsley (S70) Darton (S75) Mapplewell (S71)	Apr-25	Aug-25
CRSTS08/2 Dearne Valley Active Travel Link	The proposed ‘River Dearne Long Route’ scheme consists of a package of measures which seeks to improve walking and cycling connectivity between A61 Gyratory at Old Mill Lane and A633 Grange Lane via A628 Pontefract Road. The proposal will also incorporate a spur which will improve connectivity to Old Tannery Road	Barnsley – S71. Area between A61 Old Mill Lane and A628 Pontefract Road	Aug-25	Nov-25
CRSTS06/30/39 Rotherham East Cycle and Bus Priority Package	The scope of the project covers the study area along Fitzwilliam Road, at St. Ann’s Roundabout and the neighbourhoods of Eastwood and Herringthorpe.A description of the scope of works for each of these locations is provided below: /  A630 Fitzwilliam Road - provision of 2x bilateral unidirectional cycleways along Fitzwilliam Road between St. Ann’s Roundabout to Mushroom Roundabout and a bus lane on the approach to St Ann’s Roundabout as well as associated improvements to crossings and junctions. /  St Ann’s Roundabout - the improvements specific to St. Ann’s roundabout include visible priority for buses to improve actual and perceived speed and reliability of bus services. Further to this, pedestrian and cyclist shared-use paths and crossings will be improved in aspects regarding social safety, particularly those paths associated with subways. /  Eastwood and Herringthorpe – implementation of traffic calming measures to reduce traffic levels, speeds and on street parking in areas that are served by Fitzwilliam Road and Broom Road cycleways.	Rotherham, S65 2	Jan-25	Mar-27
CRSTS7/28(2)/40/43 Broom Rd Wickersley Extension Corridor	The scope of the project covers the study area along Broom Road, Wickersley Road, at Stag Roundabout and the neighbourhood of Moorgate. A description of the scope of works for each of these locations is provided below: /  A6021 Broom Road Cycleways (extension) – provision of 2x bilateral unidirectional cycleways and bus priority measures along Broom Road between the Broom Road / Fraser Road priority junction and Wickersley Road, as well as associated improvements to crossings and junctions. /  Wickersley Road Sustainable Travel Corridor – provision of 2x bilateral unidirectional cycleways and bus priority measures along Wickersley Road between where Broom Road changes into Wickersley Road and Brecks Roundabout, as well as associated improvements to crossings and junctions. /  Stag Roundabout Improvement – provision of segregated cycle routes and controlled crossing facilities on each arm of the roundabout. These facilities will connect into the new cycle routes that are proposed on the A6021 Wickersley Road arms of the junction whereas transitions onto the carriageway will be provided onto the northern and southern A6123 arms. /  Moorgate Active Travel Neighbourhoods – implementation of traffic calming measures on Broom Lane, Brunswick Road, Beaconsfield Road and Broom Valley Road to reduce traffic levels, speeds and manage on-street parking in areas that are served by Broom Road cycleways.	Rotherham, S60 3	Oct-25	Mar-27
CRSTS09 Barnsley Town End Roundabout	The focus of the Town End Roundabout (TER) scheme is to reconfigure the existing roundabout which is a major junction and gateway into Barnsley Town Centre on the A628. It is envisaged that the existing roundabout will be upgraded and priority for pedestrians and cyclists will be provided at key crossing points.	Barnsley (S70)	Oct-25	01/02/2027
CRSTS10/1 TPT Improvements York Road to Melton Road	The project will see the installation of a sealed surface and widening along a much used section of Trans Pennine Trail (National Cycle Network) connecting users between York Road and Melton Road. The improvements will enable greater levels of active travel along an already busy corridor for people accessing employment, education and leisure. The section of the trail also connects pedestrians’ cyclists and equestrian users to Cusworth Hall and is a popular recreation route which can get extremely muddy over the winter months.	City of Doncaster Council, Roman Ridge/Bentley/Sprotborough and Cusworth	Oct-23	Dec-23
CRSTS10/2 TPT Improvements - Melton Road to Riverside and Riverside to Boat Inn	Ensuring the National Cycle Network is fully accessible and has an appropriate sealed surface to enable more journeys by foot or by cycle. Improving local connections to the Trans Pennine Trail which passes through a number of deprived communities where car ownership levels are lower than other parts of the Borough. This scheme will see improvements between Melton Road to Riverside and Boat Inn		Apr-25	Mar-26
CRSTS 10/3 Northern Local Centres Improvements	Improvements to Northern Local Centres- Adwick, Skellow, Carcroft, Askern	Adwick, Skellow, Carcroft, Askern	Apr-25	Mar-26
CRSTS11 A61 Chesterfield Road Bus Priority	A scalable bus improvement project which will deliver bus priority along the A61 corridor from Meadowhead roundabout in the South to Sheffield city centre in the north. Bus priority measures will include signal technology, bus lane reviews and enforcement measures via red routes. There will also be a series of bus stop enhancements and pedestrian access improvements.	A61 Sheffield	May-26	Mar-27
CRSTS12 Bus Service Improvement Plan (BSIP) Bus Improvements	Improvements to the bus network and facilities delivering the objectives defined in the BSIP to improve bus journey times, reliability, punctuality and customer satisfaction. This could include improvements to customer facilities on street and in interchanges and highway improvements to reduce delays to buses. CRSTS investment in BSIP objectives is not limited to this dedicated allocation, the other bus and multi-modal schemes within the programme will be monitored to ensure contribution to the region's BSIP.	South Yorkshire wide, with specific sites to be informed by the BSIP.	01/10/2025	Mar-27
CRSTS13 Bus Lane Review Implementation	A review has been carried out of existing bus priority across the region to assess the performance of existing bus priority and recommend improvements to improve the performance of each site in order to maximise the benefits to buses in the face of changing traffic patterns. Improvements would include: / Lengthening bus lanes / Widening bus lanes / Changes to operating times / Improvements to signing and lining	Multiple locations in Barnsley, Doncaster, Rotherham and Sheffield.	Apr-25	Mar-27
CRSTS15 Bus Priority - Upper Don Valley	A scalable bus improvement project to deliver bus priority along the A61 corridor from Sheffield City Centre to northern communities of Stannington, Wisewood and Grenoside. The scheme will include the investigation of the major junctions on Penistone Road and Halifax Road. There will also be an opportunity to improve connecting infrastructure such as bus stops, waiting restrictions and other traffic management opportunities which positively present themselves through consultation.	Sheffield	Jun-25	Oct-26
CRSTS16/21 Cleveland Street Sustainable Transport Improvements	The project will provide: / • A redesign of Cleveland Street Roundabout. / • An off road, segregated cycleway and footway along the A6182 White Rose Way. / • A toucan crossing across A6182 White Rose Way. / Revision of junction, replacing a roundabout where no bus prioritisation is possible and where congestion is an issue with a Microprocessor Optimised Vehicle Actuation (MOVA) controlled signalised junction prioritising bus movement.	Doncaster DN1	Apr-25	Mar-26
CRSTS17 Meadowhall Interchange Mobility Hub	Increased park and ride capacity with supporting amenities including electric charging points for vehicles, family and disabled parking bays, waiting facilities, cycle stands, cycle lockers, and potentially mobility scooter lockers.	Meadowhall Interchange	Jan-25	Dec-26
CRSTS18 Mexborough - Transport Network Sustainable Improvements	The scheme will reallocate space within the existing highway layout along Greens Way to provide a new active travel corridor and provide a sustainable active transport alternative to the private car. The transformation of Greens Way from ‘bypass’ to ‘town street’, will provide a more attractive journey for pedestrians and cyclists giving each mode segregated space. The route will be lined with street trees and give active modes a much safer environment for vulnerable road users providing a buffer between active travellers and the carriageway. / The existing dual carriageway will be converted to a standard 7.3m carriageway and a new signalised junction created to provide vehicular access onto Station Road (North) and Bank Street, to allow bus services to access the town centre. The signalised junction will include traffic signal bus priority measures which will allow the buses to enter the town centre more efficiently. Toucan crossing facilities will also be incorporated to provide safe crossing provisions for both pedestrians and cyclists across Greens Way.	Doncaster, Mexborough	Jan-25	Feb-26
CRSTS19/1 Realtime Detection Priority	Expansion and roll out of bus priority through signalised junctions across the whole county with the aid of virtual triggers, new signal infrastructure and real-time detection including Urban Traffic Control (UTC) improvements where needed and links to operators. Outputs will include: / Upgrades to traffic signals to enable bus priority / Upgrades TO Urban Traffic Management and Control (UTMC) systems as appropriate	Primarily Sheffield and Rotherham.	Feb-25	Mar-27
CRSTS19/2 Realtime Detection Priority	Expansion and roll out of bus priority through signalised junctions across Barnsley, with the aid of virtual triggers, new signal infrastructure and real-time detection including Urban Traffic Control (UTC) improvements where needed and links to operators.	Barnsley	Aug-24	Dec-24
CRSTS20/29 Shaw Lane Bus Lane & East Doncaster Passenger Transport Connectivity	Widening of highway to create a new bus lane and resolve a significant bus and congestion pinchpoint. Identified by Operators as a significant issue for service quality and reliability. / This scheme is for phase 2 of the West Moor Link A18-A630, to deliver essential connectivity improvements along the A630 between junction 4 of the M18 motorway to the A18 (Thorne Road) and between the A19 and A630 Wheatley Hall Road, providing active travel routes, bus priority measures and road capacity improvements.	Doncaster, DN2	Aug-25	Aug-26
CRSTS23 Network Asset Maintenance - Barnsley, Doncaster & Rotherham	Development of the approach to asset management maintenance taking the fundamental requirements of the Highway Capacity Manual (HCM) regime (surfacing, potholes, footway and cycleway management, lighting and structures), and aligning these with the region’s strategic priorities, including the draft Key Route Network and supporting increased adoption of sustainable modes and the re-allocation of road space. Opportunities to use the maintenance regime to add further value to other CRSTS interventions will be developed.	Barnsley	Apr-22	Mar-27
CRSTS26 A628 Bus and Active Travel priority corridor	Bus / Active Travel (AT) priority scheme; also mitigation for Local Plan developments . Will also include Active Travel routes to tie into existing routes delivered through Transforming Cities Fund (TCF) / AT funding. Direct Outputs / * Bus and Active Travel priority measures; / * Active travel routes which feed directly into existing TCF active travel and bus priority. / * Bus stop improvements to include new shelters / real time information / * Junction improvements to deliver journey time benefits	Barnsley (S70 & S72)	Jan-26	Mar-27
CRSTS27 A635 Quality Bus Corridor - BRT	Support economic growth through investments at key junctions reducing current and forecast congestion, improving bus journey time reliability and widening sustainable travel opportunities. A corridor length of approximately 7.2km. / Enlarge footprint of roundabout, provide 2 new foot / ped / Equestrian Bridges / Provide One-Way gyratory system at junction / Upgrade Bus Stop infrastructure with new shelters providing real time information / Widen Grange Lane for inbound and outbound traffic flows / Dedicated bus lane along Wombwell Lane to industrial estate junction	Barnsley (S70) Stairfoot (S70), Cundy Cross (S71)	Jun-25	Mar-27
CRSTS28 Broom Lane Cycleways Phase 1	Provision of new cycleways alongside the B.6410 Broom Lane between Broom Road and Worrygoose Roundabout. Total affected length 1.4km	Rotherham, S60 4	Apr-26	Jan-27
CRSTS31 Ickles Roundabout improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S60 1DS	Aug-25	Aug-26
CRSTS32 Integrated Strategic Public Transport	A programme of public transport led infrastructure interventions to enhance the service efficiency and provide the facilities that travellers and communities require. Focussing on a higher volume of smaller scale investments to complement the CRSTS scheme investments and manage the detailed needs including community transport vehicle fleet upgrade, shelter replacements, and bus hotspot rectification.	Region wide	Apr-22	Mar-27
CRSTS33 Local and Neighbourhood Transport Complementary Programme - all four local authority areas	Broad range of the smaller scale interventions required to complement the CRSTS scheme allocations and provide efficiency and effectiveness across the network upon which the regional strategic objectives and investments can be delivered. Also delivering localised investments within communities to open up the network to all users and encourage sustainable access to leisure, facilities and employment.	Barnsley	Apr-22	Mar-27
CRSTS38 Royston Active Travel and Bus Priority Measure infrastructure	Provision of infrastructure mitigation required to deliver 2 major Mixed Use (employment / residential) sites allocated in the Local Plan. MU3 and MU5 – which have been approved in the Royston Masterplan. The scheme will provide mitigation at several local junctions; provide active travel routes and an alternative bus priority route into the town centre	Barnsley	Development Only	Development Only
CRSTS44 Worrygoose Roundabout improvement	Replacement of roundabout with subways with a new junction with bus priority and improved pedestrian and cycle crossing. Delivering bus passenger journey time savings, improved bus journey reliability, better walking & cycling journey ambiance and mode shift.	Rotherham, S60 4LD	Jan-25	Dec-25
CRSTS45 Accessibility Improvements – Thorne North Rail Station	Provision of fully accessible footbridge, stairs and lifts access to the platforms at the station. Current facilities only enable access while the station is staffed and is therefore only available part time.	Thorne North Station, Doncaster	Sep-25	Mar-26
CRSTS47 Conisbrough Rail Station Park & Ride	Increase capacity by enlarging car park encouraging modal shift and improving improved access to opportunities. Facility regularly over-subsbribed resulting in local road side parking.	Conisborough Station, Doncaster	Mar-25	Mar-26
CRSTS49 Park & Ride - Penistone Rail Station	Extension of existing car parking facilities by provision of a new car park on the eastern side of the existing station, providing an additional 99 spaces. Complementary to Barnsley Metropolitan Borough Council (BMBC) Penistone Station Accessibility Improvements / Scheme also includes alterations to existing car park and provision of a new footbridge to replace a barrow (at grade / across track) crossing.	Penistone Station	Jan-25	Dec-25
CRSTS50 Penistone Station Accessibility Improvements	The scheme will improve accessibility to the proposed Park and Ride scheme at the Penistone station. The creation of a Park and Ride site at Penistone station is a priority of SYMCA and will also complement Kirklees Council Levelling Up Fund (LUF) submission to increase the number of trains on the Penistone Line, which connects Huddersfield with Sheffield via Barnsley. Services at Penistone are currently restricted to 2 trains per hour.	Penistone (S36)	Apr-25	Mar-27
CRSTS53 Waverley Station	Provision of new railway station on the Sheffield to Lincoln line at Waverley, providing rail connectivity to the Advanced Manufacturing Park and Waverley new community, as well as to potential housing allocations in Sheffield. / The CRSTS contribution would be for business case development work up to 2026.	Rotherham, S60	Development Only	Development Only
CRSTS59 Maltby Active Travel Neighbourhood (overprogramming)	Provision of measures to manage traffic volumes, traffic speeds and parking in the Maltby area, linking to the Maltby to Hellaby cycleway. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output.	Maltby, ROTHERHAM. S66.	Jan-26	Dec-26
CRSTS46 Wickersley & Brecks Active Travel Neighbourhoods (overprogramming)	Provision of measures to manage traffic volumes, traffic speeds and parking in areas served by Wickersley Road and Bawtry Road cycleways. Scheme to be designed in collaboration with the community it serves to enable specific local needs to inform the output	Wickersley, Rotherham.	Jan-25	Dec-26

Transforming Cities Fund (TCF) Final Year - BRT (T0011) / BMBC	The proposed schemes focus on investment along 3 Key Growth Corridors - / • A61 Barnsley to Wakefield / • A635 Barnsley to Doncaster / • A633 Barnsley to Doncaster via Rotherham / The scheme starts at the Barnsley Interchange in the town centre, follows the Schwabisch Gmund Way to the A61 which connects to the Alhambra Roundabout, the route then continues east to the roundabout at Stairfoot; the route then connects into the A633 Wombwell Lane continuing south and ends at the roundabout junction of the A633 / A6195, a corridor length of approximately 10.6km.	Barnsley (S70) Royston (S71), Cundy Cross (S71)	Jun-25	Mar-27
Transforming Cities Fund (TCF) Final Year - A631 Maltby (T0005) / RMBC	Two sections of bus lane are proposed, all along the A.631 Bawtry Road – / • Between Addison Road, Maltby and Denby Way, Hellaby (1.2 km length). This bus lane consists of an additional lane; / • In the vicinity of Wickersley School and Sports College (0.2 km length). This bus lane consists of a combination of additional lanes, and repurposing existing acceleration / deceleration tapers, in the Rotherham-bound direction; and, / • Improvements to the bus stop at Brecks Crescent to ease the passage of buses pulling away.	Wickersley, Bramley, Hellaby and Maltby. / ROTHERHAM. S66.	Jul-23	Jul-24
Transforming Cities Fund (TCF) Final Year - Sheffield Rd Cycleways (T0026/3) / RMBC	Comprising walking and cycling routes, supporting housing delivery in the Westgate Riverside area. Pedestrian improvements are to be focused on enabling journeys to the town centre and onward via public transport, and making this more attractive so as to support both housing delivery and the vitality of the town centre. The scheme on Westgate will also reduce traffic volumes and so improve the local environment for existing and future residents. For cyclists, the scheme will include LTN 1/20 compliant cycle lanes to support onward connectivity by bicycle. Additional cycle tracks will be constructed along the remainder of Sheffield Road to the Borough boundary, to provide access to employment areas in Ickles and Templeborough, and with proposals in development by Sheffield City Council and SYPTE providing further connectivity to Meadowhall and to tram-train services respectively. / Parts of this scheme in the Templeborough area are proposed to be co-delivered with highways and drainage maintenance works delivered through the Department for Transport’s Local Highways Maintenance Challenge Fund.	Rotherham, S60.	May-23	Jul-24
AMID via Darnall/Sheffield to AMID Buss Corridor (T0008 1 & 3) / SCC	The proposals will deliver a step change in active travel infrastructure to support the development of employment sites at the Advanced Manufacturing Innovation District (AMID) in north east Sheffield. The active travel improvements are to be complemented by public transport connectivity enhancements.	Burngreave S4 / Attercliffe, Brightside, Darnall, Meadowhall, S9 / Handsworth, Woodhouse S13	Jan-25	Jan-27
Transforming Cities Fund (TCF) Final Year - City Centre Cycling/Cross City Bus (T0015) / SCC	Sheffield City Council are seeking to enhance the city centre, by improving the legibility of active travel routes, improving the public transport network and enhancing the city’s public realm. The scheme will include the relocation of public transport from Pinstone Street, with the creation of high quality transport hubs on Rockingham Street and Arundel Gate to reflect the changing nature of the city centre. The relocation of buses and general traffic from Pinstone Street will create a pedestrian friendly environment and allow the introduction of cycle lanes to the economic and leisure core whilst providing important cross city links to other radial routes.	S1 – Sheffield City Centre	01/11/2024	01/05/2026
Transforming Cities Fund (TCF) Final Year - Kelham (T0019) / SCC	The Project will consist of the following Works - / a) A segregated cycle route along Tenter Street and West Bar with sustainable urban drainage / systems. / b) West Bar roundabout will be reconfigured to prioritise pedestrians and cyclists. / c) Traffic management measures in Kelham and Neepsend to reduce through traffic including / localised junction improvements for pedestrians and cyclists. / d) Bus priority interventions in Kelham and Neepsend.	Kelham Island, Sheffield, S3	May-23	01/01/2025
Transforming Cities Fund (TCF) Final Year - Magna-Tinsley (T0008/2a) / SCC	The project will deliver: / a) a new toucan crossing at the Sheffield Road/Raby Street junction to provide a safe / crossing point from the Tinsley Village across Sheffield Road; / b) enabling works on Sheffield Road ahead of the delivery of the Phase 2 project which / will provide improved footways and physically separated cycle tracks on Sheffield / Road; / c) rationalisation and resurfacing of parking bays alongside Sheffield Road which is required to deliver the Phase 2 project; and / d) a new gated access onto Sheffield Road.	S9 – Tinsley	Feb-24	01/06/2024
Transforming Cities Fund (TCF) Final Year - Magna-Tinsley (T0008/2b) / SCC	A package of measures to facilitate walking and cycling within the Magna, Tinsley and Meadowhall area. This includes Sheffield Road cycle tracks, upgradge of exisitng and shared use infrastructure at Blackburn Meadows Way and provision of new toucan crossings (delivered as part of Phase 1).	S9 – Tinsley, Meadowhall area	Aug-24	Mar-25
Transforming Cities Fund (TCF) Final Year - Nether Edge Wedge (T0023) / SCC	Development of core route connecting city centre to Nether Edge involving construction of separate cycle tracks along Wostenholme Road corridor, with feeder route from adjacent residential areas (measures likely to include traffic calming and/or separating cyclists from it to fit site circumstances).	Sheffield City Centre S1 Nether Edge S7 Sharrow S11	Nov-24	May-26
Transforming Cities Fund (TCF) Final Year - South West Bus Corridors (T0006) / SCC	The South West Bus Corridors scheme forms an important part of Connecting Sheffield’s plans for supporting the shift towards sustainable transport in and around the city. The proposals aim to improve public transport connectivity within the Abbeydale Road and Ecclesall Road corridors in South West Sheffield both to and from the city centre.	•S1 –City Centre / •S2 – Little Sheffield / •S3 – Broomhall / •S7 – Abbeydale, Millhouses, and Carter Knowle, Nether Edge, and Sharrow / •S8 – Beauchief, and Norton Hammer / •S10 – Broomhall / •S11 – Sharrow Vale, Brincliffe, Banner Cross, Ecclesall, Parkhead, and Little Common	May-24	May-25
Transforming Cities Fund (TCF) Final Year - A61 Wakefield Bus Corridor (T0002) / SYMCA	The scheme will feature improvements to bus detection which will give buses priority at junctions to beat congestion, and red routes to allow enhanced enforcement of illegal parking along with infrastructure improvements at junctions and bus stops which will deliver increased accessibility to the city centre as well as to local centres and other destinations along the route from large residential areas including Millhouses, Brincliffe and Parkhead.	Stretch of the A61 in Barnsley between Carlton Road and the Old Mill Lane Gyratory.	May-22	Oct-25
Transforming Cities Fund (TCF) Final Year - Rotherham Parkgate Package (T0024) / SYMCA	The scheme is to provide road widening at two key locations along the A61 Corridor in Barnsley. The aim of the road widening scheme is to reduce congestion and improve bus journey: / widen the existing Old Mill Bridge to provide a new five-lane arrangement, including a designated southbound bus lane. The widening will increase the traffic capacity on the bridge as well as providing an opportunity for future active travel provisions; / Widen Wakefield Road (A61) from the existing two-lane configuration to a new four lane configuration, to provide greater capacity, between existing signalised junctions at Smithies Ln and Carlton Road / The scheme delivers key interventions on, or adjacent to the A633 corridor which when combined are designed to relieve congestion on this key arterial public transport route.	A633 Rotherham Road and A6123 Aldwarke Lane	Feb-23	Mar-25

Overprogramming - Meadowhall Interchange Mobility Hub	This is the balance of allocation required based on the original forecast costs. This scheme spanned the £570m programme cut off point so this value currently sits below the line. Increased park and ride capacity with supporting amenities including electric charging points for vehicles, family and disabled parking bays, waiting facilities, cycle stands, cycle lockers, and potentially mobility scooter lockers.	Meadowhall Interchange
Overprogramming - Rotherham Mainline Station	Provision of new railway station on the Sheffield – East Coast Main Line route at Forge Way, Rotherham, allowing long distance services on the Cross Country, South Trans Pennine and Yorkshire Coast lines to call in Rotherham and ultimately allowing for local stopping services to be removed from the mainline between Sheffield and Holmes Junction, and between Aldwarke and Mexborough Junctions – releasing capacity for improved regional services and shorter journey times regionally. / The station will include new station infrastructure to service long distance services on the Tapton Junction to Gascoine Wood via Sheffield line (i.e. the mainline Sheffield to East Coast Mainline route), and new station infrastructure to provide for existing tram-train services on the Aldwarke Junction to Woodburn Junction Route (i.e. the Rotherham branch & freight line), which would ultimately be extended to Doncaster. / The CRSTS contribution is for development of the OBC only with the wider masterplan and tram-train elements to be reconsidered following completion of the OBC and of the DfT led Leeds area Masterplan / In respect of tram-train services, it is assumed that existing services between Cathedral and Parkgate would call at Rotherham Mainline. Whilst potential for stopping heavy rail services between Sheffield, Rotherham Central and Doncaster to be converted to tram-train in future may allow additional services to call at the Mainline tram-train stop – this is not assumed to be delivered within this project.
Overprogramming - A61 Active Travel - Barnsley – Royston via Smithies - Phase 2	Continuation of work currently sequenced within the main programme. An active travel scheme which provides 7.5km of new on and off road cycle routes. Full scheme includes new pedestrian / cycle crossings at key junctions and decking of an existing disused rail bridge providing better connectivity. Also ties into the A61 Royston Bus Priority measures scheme being delivered by SYMCA.	Barnsley (S70) and Royston (S71)
Overprogramming - Accessibility Improvements – Chapeltown Station	Provision of lifts to the platforms at the station. Making the station accessible to all travellers and thereby enabling mode shift from cars to public transport, walking and cycling.	Chapeltown Rail Station,
Overprogramming - Active Travel Schemes Barnsley Phase 2	A scalable schemes comprising / Provision of on and off-road sections; / Improvements to pedestrian crossings into Toucans / Pegasus; / Monitoring Equipment; / Wayfinding signage; / Improvements to public realm / Re-surfacing of existing routes	Barnsley (multiple)
Overprogramming - A.633 Rotherham to Dearne Valley sustainable transport corridor	Public transport priority and supporting active travel infrastructure along the A.633 corridor between Rotherham and the Dearne Valley employment area. Main intervention will be 1km of bus lane along the A.633 Warren Vale, to be supported with additional measures to provide bus priority and active travel between Wath, Manvers and Brampton.	A633 Warren Vale Rotherham
Overprogramming - Maltby to Hellaby Cycleways	Development work for provision of cycleways along the A.631 between Grange Lane, Maltby and Denby Way, Hellaby, total affected length of 3.4km	Bawtry Road, Hellaby.
Overprogramming - Active Travel Mosborough Townships	A series of scalable active travel network improvements connecting the Mosborough Communities with schools, local businesses, recreational greenspace (including Rother Valley Country Park), the Park and Ride at Halfway and a number of crossing facilities to enhance pedestrian permeability.	Sheffield
Overprogramming - Improvements to Trans-Pennine Trail Barnsley	This phaseable package of interventions includes: / * Provision of new active routes / * Improving the condition of the Trans-Pennine Trail (TPT) / * New Pegasus / toucan crossings in locations where the trail connects with the highway / * Providing circular links / * New Wayfinding / * Data Collection / Monitoring Equipment	Barnsley
Overprogramming - A635 Quality Bus Corridor - BRT - Phase 2
Overprogramming - Railway reinstatement: North Barnsley to Wakefield via Royston - Phase 2	The restoration proposal for the North Midland Line is to run passenger services from Barnsley to Wakefield Kirkgate via the semi-operational freight route from Wakefield to Lundwood. This could form the first phase of a more fundamental reinstatement between Lundwood and Barnsley and / or Lundwood and Swinton on disused tracks. Currently, the route is a single track, infrequently used freight line, which runs parallel to parts of the National Cycle Network	Barnsley, Royston, Wakefield
Overprogramming - Zero Emission Buses - additional scope opportunity	Complementary to the submission for DfT Zero Emission Bus Regional Areas (ZEBRA) funding and earmarked gainshare funding, this allocation will further enable the procurement of electric, zero-emission buses, including Community Transport and provision of charging infrastructure at Interchanges, on street and at depots to facilitate the goal of operating a zero emission fleet.	Across South Yorkshire
Overprogramming - Active Travel Northern Communities Phase 2	A series of scalable active travel network improvements connecting Sheffield City Centre with the Northern General Hospital (NGH), and onward to the surrounding communities. The project will seek to integrate with the bus corridors to provide a sustainable transport route to NGH and improved local access to district centres as well as strategic connections into the City and areas of high employment.	Sheffield

## TVCA
Annex A: / Tees Valley Combined Authority £310m - City Region Sustainable Transport Settlement	Tees Valley Combined Authority's (TVCA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. TVCA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.	*Scheme retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
Linthorpe Road Phase 2	Provision of safe facilities for pedestrians and cyclists along Linthorpe Road between Ayresome Street and Cumberland Road. This will complement the existing Phase 1 scheme between Borough Road and Ayresome Street and together will provide a continuous link between Linthorpe Village and Middlesbrough Town Centre. In addition to CRSTS funding this scheme has also attracted Active Travel Fund - tranche 3 money to support delivery.	Middlesbrough	Mar-23	Mar-24
Woodland Road Phase 2	The Woodland Road Phase 2 scheme will provide safe facilities for pedestrians and cyclists along Woodland Road (A68) between Hollyhurst Road and Deneside. This will complement the existing Phase 1 scheme between Hollyhurst Road and Skinnergate and together will provide a continuous link between Cockerton and Darlington Town Centre. In addition to CRSTS funding this scheme has also attracted Active Travel Fund - tranche 3 money to support delivery.	Darlington	Mar-23	Mar-24
Nunthorpe to Guisborough	The Nunthorpe to Guisborough Cycleway Phase 1 Scheme will provide a continuous off-road walking and cycling link between Nunthorpe, at the southern edge of Middlesbrough and the town of Guisborough.	Middlebrough / Redcar and Cleveland	Mar-23	Mar-24
A68 to Cockerton and Faverdale	This scheme will continue the route from Woodland Road Corridor phases 1 & 2 and extend existing cycling and walking provision to link Darlington Town Centre and Cockerton with the economic development site at Faverdale.	Darlington	Mar-24	Mar-25
Town Centre to Acklam and Hemlington	This scheme will continue the route from Linthorpe Road Corridor phases 1 & 2 and extend existing cycling and walking provision to link Middlesbrough Town Centre and Linthorpe with the residential areas of Acklam and Hemlington.	Middlesbrough	Mar-25	Mar-26
Norton to Stockton Town Centre	This scheme will provide safe facilities for pedestrians and cyclists along the Norton Road Corridor between Stockton Town Centre and Norton. The scheme will be delivered in two phases and onward links to Billingham will also be developed in phase 3.	Stockton	Mar-24	Mar-25
Redcar town centre to South Bank / Teesworks	This scheme will provide safe facilities for pedestrians and cyclists between Redcar Town Centre and South Bank, via the Teesworks site. It is a key access corridor to the major employment site from Redcar and Middlesbrough. The scheme will be delivered in phases	Redcar	Mar-24	Mar-25
A689 Hartlepool Town Centre to Wolviston	This scheme will provide safe, largely off road facilities for pedestrians and cyclists along the A689 between Hartlepool Town Centre / Transport Interchange, and Wynyard and Billingham to the south. It will link a number of new housing developments in the southwest of Hartlepool with employment sites in Hartlepool and seal sands. This scheme will be delivered in phases. In addition to CRSTS funding delivering all phases of this scheme is dependent upon securing funding from the DfT's Major Road Network programme for the A689 Corridor Improvements bid.	Hartlepool	Mar-24	Mar-26
Yarm Road to Teesside International Airport Business Park	This scheme will provide safe facilities for pedestrians and cyclists along the A67 between Darlington Town Centre/Darlington Railway Station and heading towards the Teesside International Airport and nearby villages. In addition to linking a number of residential areas with employment sites in Darlington Town Centre and on the outskirts of Darlington, it will also link with the growing demand at the airport.	Darlington	Mar-24	Mar-25
Marton Road to Nunthorpe	This scheme will provide safe facilities for pedestrians and cyclists along Marton Road between Middlesbrough Town Centre and James Cook University Hospital and Nunthorpe. This will link a number of residential areas with employment sites in Middlesbrough Town Centre and at the hospital. This scheme will be delivered in phases.	Middlesbrough	Mar-24	Mar-26
Thornaby to Stockton Town Centre	This scheme will provide safe facilities for pedestrians and cyclists between Thornaby Town Centre and Stockton Town Centre. This will link a number of residential areas with employment sites and Thornaby station.	Stockton	Mar-24	Mar-26
Hartlepool Town Centre to the Headland	This scheme will provide safe facilities for pedestrians and cyclists between Hartlepool Headland and Hartlepool Town Centre/Transport Interchange. This will link a number of residential areas with employment sites.	Hartlepool	Mar-24	Mar-25
Development of active travel hubs and cycle storage	Capital investment in the establishment of new active travel hubs aross the Tees Valley to provide a focal point for behaviour change activity to encourage walking and cycling. On-going operation of the Active Travel Hubs dependent upon securing Capability Fund revenue.	Tees Valley wide	Mar-23	Mar-24
Darlington Station*	Darlington Station is the largest rail investment project taking place in Tees Valley and is fundamental to the delivery of the Tees Valley Combined Authority's vision for rail service improvements. Located on the East Coast Main Line (ECML), the Darlington Station project is a fundamental part of the investment programme north of York, as outlined in the Government's Integrated Rail Plan. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline / *Scheme retained by DfT and subject to business case approval by HMG	Darlington	Sep-22	Nov-24
Eaglescliffe Station	Eaglescliffe Station is currently only accessible from the eastern side of the railway lines. In terms of vehicular access, the station car park is at or near capacity and there is no scope for expansion due to the site constraints. Hence, this scheme involves the construction of a new access road and car park on the west side, a new fully accessible footbridge and station enhancements.	Eaglescliffe Station	Oct-22	Mar-24
Middlesbrough Station	This is the third phase of improvements at Middlesbrough Station. The current operational layout means that there are a number of performance and reliability issues and a capacity constraint, which acts as a barrier to the delivery of new services and extends journey times. This proposal comprises rail infrastructure, including the construction of a new platform to improve capacity, reduce journey times and provide resilience. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline	Middlesbrough	Dec-23	Nov-24
Redcar Central Station Project	The CRSTS proposal at Redcar Central Station comprises the construction of a new footbridge, building repair work and improving walking, cycling and bus connectivity.	Redcar	Apr-24	Mar-25
Hartlepool Station Platform Reinstatement	Hartlepool Station is currently a key constraint on the Durham Coast Line on account of it having only one operational platform for through trains, despite there being two tracks through the station. The proposal at Hartlepool Station comprises re-opening the disused platform and constructing a new footbridge / lifts.	Hartlepool	Aug-22	Jun-23
Billingham Station Accessibility	Billingham Station is an island platform and is currently the only station on the Tees Valley rail network which doesn't have step free access to either of its platforms. The proposal at Billingham Station includes installing a new footbridge to replace the previous life-expired one and lifts, along with reconfiguring current car parking.	Billingham	Jul-22	Jun-23
Teesworks Stations and Transport hubs (South Bank Station and British Steel Redcar Station Improvements)*	Teesworks is the UK's largest regeneration site and is critical to the transformation of the Tees Valley economy. A railway line from Middlesbrough and Redcar runs through the site with Redcar British Steel Station providing good access to the east of the site and South Bank Station provide good access to the west of the site and the adjacent residential community. The proposal involves refurbishing the stations, enhancing facilities and seeking to improve accessibility.	South Bank	Mar-24	Mar-26
Station Accessibility and Modal Integration Enhancements	Programme involves a number of improvements across stations in the Tees Valley. Proposals across the 16 identified stations include improved cycling and parking infrastructure, pedestrian accessibility, bus connectivity, car parking facilities and working with the rail industry to secure additional funding to deliver passenger enhancements at the stations.	Tees Valley wide	Mar-23	Mar-25
Line Speed and Capacity Improvements	The purpose of this project is to: / * review and prioritise the pinchpoint locations where infrastructure improvements are needed; and / * work with Network Rail to identify where line speed improvements can be delivered to speed up journey times.	Tees Valley wide	Mar-24	Mar-26
Eaglescliffe to Northallerton W12 Gauge Clearance*	This project will provide a more direct W12 gauge cleared route to the East Coast Main Line (ECML) to enable more freight to be moved efficiently by rail, particularly between the Northallerton and Stockton Cut Junction. In addition to CRSTS funding this scheme is seeking funding from DfT's Rail Network Enhancements Pipeline.* / *Scheme retained by DfT and subject to business case approval by HMG	Yarm Town / Northallerton	Sep-23	Mar-25
Bus priority improvements: Darlington Branksome to Red Hall corridor	This corridor provides connectivity into Darlington town centre and offers links to employment and leisure opportunities along with an interchange to rail at Darlington station. This corridor serves local communities where car ownership is less than 50%, alongside providing access to local employment sites. Future developments have been identified along the corridor.	Darlington	Jan-23	Mar-25
Redcar to Middlesbrough bus corridor	This corridor provides an important connection to the major trauma centre and district general hospital at James Cook and Redcar Primary Care Hospital. The corridor offers links to employment opportunities by serving communities across the region, several of which have low car ownership and rely on bus services to access employment and education opportunities.	Redcar / Middlebrough	Jan-23	Mar-25
Middlesbrough to Hartlepool bus corridor	This corridor provides connectivity between three key centres: Middlesbrough, Stockton and Hartlepool and offers an interchange with the rail network at Hartlepool and Thornaby, alongside serving various local communities. The corridor provides Hartlepool residents with a public transport link to employment attractors located in town centres and industrial parks along the A689.	Middlebrough / Hartlepool	Jan-23	Mar-25
Middlesbrough to Ingleby Barwick bus corridor	This corridor provides an important link into Middlesbrough town centre and offers links to employment, education and leisure facilities together with an interchange with the rail network at Allens West. The corridor serves many communities in Stockton district who rely on bus journeys due to low car ownership.	Middlebrough / Ingleby Barwick	Jan-23	Mar-25
Middlesbrough to Coulby Newham bus corridor	This corridor offers an important connection between an area of development south of Middlesbrough and Middlesbrough town centre. The corridor offers a public transport link for various communities in the region, providing accessibility to employment, educational and leisure facilities.	Middlebrough / Coulby Newham	Jan-23	Mar-25
Middlesbrough to East Cleveland Hospital bus corridor	This corridor serves both Middlesbrough and Redcar & Cleveland residents, offering connectivity from Middlesbrough to Teesport and the development area of Teesworks / Tees Valley Freeport. The corridor connects various local communities to employment, leisure, education and healthcare facilities.	Middlebrough / Redcar	Jan-23	Mar-25
Middlesbrough to Netherfields / Overfields bus corridor	This corridor provides connectivity into Middlesbrough town centre for various local communities where car ownership is below 50%, allowing them to access employment, educational and leisure opportunities.	Middlebrough	Jan-23	Mar-25
Darlington to Middlesbrough (via Stockton) bus corridor	This corridor provides connectivity between three key centres: Darlington, Stockton and Middlesbrough and interchanges with the rail network at Thornaby. The corridor offers a public transport link to employment attractors both in the town centres and at industrial estates out of town, meaning that employees can travel across districts to access employment.	Darlington / Middlebrough	Jan-23	Mar-25
Darlington to Durham bus corridor	This corridor serves various communities in both Tees Valley and Durham County Council, offering connectivity into Darlington and Durham centres and links to employment, leisure and education opportunities. The corridor requires a collaboration between the neighbouring authorities to ensure that aspirations and proposals along the corridor are aligned between neighbouring authorities and bus operators.	Darlington	Jan-23	Mar-25
Tees Valley wide Bus Shelter Improvements	Tees Valley wide project to complement the bus corridor work by developing a hierarchy of bus shelter provision and specifying the expected level of provision / facilities for each category. It is envisaged that the level of provision / facilities will be of a higher specification on the key bus corridors.	Tees Valley wide	Jan-23	Mar-24
Electric vehicle programme	TVCA is committed to delivering a step-change in the provision of electric vehicle charging infrastructure, which is one of the main deterrents for people considering a transition to electric vehicles. The Combined Authority has already started to create a comprehensive network of charge points to kickstart the transition to electric vehicles. This project will build upon the initial phase of roll-out.	Tees Valley wide	Mar-24	Mar-25
Digital transport programme - Data Platform	A data platform will form the foundational digital infrastructure for TVCA, allowing for data analytics capabilities. It will enable data to be collected, aggregated, analysed and shared. It will provide convenient access for TVCA and third parties to work with data to gain insights and identify trends.	Tees Valley wide	Mar-23	Mar-24
Digital transport programme - Digital Services	Digital services are the customer-facing offering that will enable TVCA to communicate, engage and interact with users. Digital services can take many forms, from web-based, to mobile applications, or voice activated services and interactive installations, offering a range of services such as real-time data, integrated parking services and customer services.	Tees Valley wide	Mar-23	Mar-24
Digital transport programme - Digital Twin	A Digital twin is a virtual digital replica of an asset or system that incorporates associated real-time data during operation, allowing for greater understanding and network performance of the asset. Digital twins enable modern digital analysis techniques, such as condition-based monitoring and predictive analysis, to plan for the continued functioning of the infrastructure. A Digital twin will enable TVCA to better envision, design, build, operate, maintain and manage virtually everything in the built environment.	Tees Valley wide	Mar-23	Mar-24
Wheels to work (Capital) April 2024 - March 2027	The project leases electric motorcycles to working age people at a subsidised rate for a short period enabling individuals to access to employment, training or education where public transport is not a viable option. Extension of the current scheme beyond 2023/24 is subject to evaluation. CRSTS will be used to fund the replacement of the vehicle fleet. In addition to CRSTS capital funding the extension of this scheme will need revenue funding to support the operational costs.	Tees Valley wide	Apr-24	Mar-27
Tees Flex On-Demand Service	Tees Flex is an on-demand bus service currently in operation as a 3-year pilot project. Extension of this project is subject to evaluation of the pilot. CRSTS will be used to fund the provision of new vehicles. In addition to CRSTS capital funding the extension of this scheme will need revenue funding to support the operational costs.	Parts of Tees Valley where there is limited commercially operated public transport	Mar-23	Mar-27
Local Highway Authority Consolidated Funding	This is an allocation of funding for each of the five local authorities and is a 5-year settlement based upon the level awarded for 2020/21	Tees Valley wide	Started	Mar-27
Transforming Town Centre Accessibility	Ensuring that transformational transport interventions can be implemented to help meet the ambition and support the delivery of the proposed Hartlepool and Middlesbrough Mayoral Development Corporations and other town centre major regeneration projects. Masterplanning work is to commence later in 2022/23, following designation of the Mayoral Development Corporations and will help to define the specific investment proposals	Hartlepool / Middlesbrough / Other major town centre regeneration projects	Mar-24	Mar-27
Over-programming	Additional scope on Transforming Town Centre accessibility	TBC	TBC	TBC
Over-programming	Additional scope on: / * Wheels to work (Capital) April 2024 - March 2027, or / * Tees Flex On-Demand Service	TBC	TBC	TBC
Over-programming	Additional scope on Digital Transport Programme packages	TBC	TBC	TBC
Over-programming	Additional scope on Electric Vehicle Programme	TBC	TBC	TBC
Over-programming	Either additional scope on identified schemes which may have to be value engineered if inflation continues to exert pressure on the identified scheme costs / Or / Delivery of additional interventions identified during further project development work on each of the 9 corridors	TBC	TBC	TBC
Over-programming	Additional scope on: / * Station Accessibility and Modal Integration Enhancements, or / * Line Speed and Capacity Improvements	TBC	TBC	TBC
Over-programming	Either additional scope on identified schemes which may have to be value engineered if inflation continues to exert pressure on costs, or delivery of other phases of active travel corridors identified in the Tees Valley Local Cycling and Walking Improvement Plan.	TBC	TBC	TBC

## WECA
Annex A: / West of England Combined Authority £540m - City Region Sustainable Transport Settlement	The West of England Combined Authority's (WECA) delivery plan includes an additional reserve list of schemes as part on an approach to overprogramming. WECA has flexibility to manage their programme in line with the approach to change control, but remain responsible for sourcing any additional funding required to deliver the agreed schemes.	*Scheme retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
M32 Sustainable Transport Corridor and Hub*	Providing a new transport hub, improvements to bus priority and improved active travel offer. This scheme removes substantial traffic entering the centre of Bristol that at present is generated from the M4. It includes a new junction off the M32, a new transport hub and parking, improvements to bus priority into the centre of Bristol and walking and cycling connections.	Bristol (M32 is in Bristol)	Sep-25	Jun-27
Charfield Railway Station*	This activity is focused on the construction of a new station at Charfield, between Gloucester and Yate. This will enable additional development and sustainable transport for new and existing residents of the village, including a transport hub.	Charfield	Feb-25	Mar-27
Bristol City Centre Sustainable Transport Corridor Inc. Long Ashton metrobus improvements	Improving the appeal and effectiveness of public transport offer in Bristol City Centre, this project includes upgrading cycling and walking infrastructure, implementing Bus Priority and creating effective transport hubs/interchange across the city centre. This will deliver significant multi-modal transport benefits across the city.	Bristol	Aug-25	Mar-27
Bath City Centre Sustainable Transport Corridor	Improving the appeal and effectiveness of public transport offer in Bath City Centre, this project includes upgrading cycling and walking infrastructure, improvements to the Bus Station and links across the river. This will deliver significant multi-modal transport benefits across the city.	Bath City Centre	Nov-25	Dec-26
Bristol to Bath Sustainable Transport Corridor - Bristol to Emery Road	Improving public transport services along the A4 Strategic Corridor from Bristol Temple Meads to the existing Park and Ride at Emery Road (5km). This already popular public transport service is hampered by a lack of continuous bus priority. This project would address much of the challenges to enable a more reliable and faster service. Walking and cycling infrastructure along the route is also being significantly improved.	A4 Corridor	Dec-25	Mar-27
Bristol to Bath Sustainable Transport Corridor - Keynsham to Bath	There is no bus priority at present along this 12.5km route that connects Bath to it's largest town - Keynsham. Therefore, Improving public transport offer along this section of the A4 is a priority. Walking and cycling infrastructure along the route is also being significantly improved.	A4 Corridor	Sep-25	Mar-27
Bristol to Bath Sustainable Transport Corridor - Transport Hub	Proposed location for new hub and P&R is within the Green Belt (Hicks Gate) and will not come forwards for development within the CRSTS timescales as it will need to be re-designated through the local plan process. The site would replace existing Brislington P&R (currently has spare capacity). / It is proposed the Hub is phased as a later part of the corridor programme, with some CRSTS1 funding used to develop the full business case for the Hub. / A hub is proposed at Keynsham. / Improvements to the corridor between Emery Road and Keynsham will also be delivered within this project. This was missing from the scope descriptors within the CRSTS1 bid, although included within the overall narrative and the SOC. The scope is now defined.	A4 Corridor	Sep-25	Mar-27
Portway Sustainable Transport Corridor and Hub	Focused on enhancing the corridor between central Bristol, employment sites in Avonmouth and connections to the M5. These initiatives consist of upgrading the existing P&R site, bus segregation measures and improved cycling infrastructure.	Bristol	Oct-25	Mar-27
Stockwood to Cribbs Causeway Sustainable Transport Corridor Work Package 1 Victoria Street/Colston Avenue	These are a number of activities related to infrastructure improvement regarding public transport offer in the A37/A4018 corridor. These upgrades include the provision of bus priority measures, road design and enhancement of cycling and walking routes across the covered area.	Bristol city	May-25	Dec-26
Stockwood to Cribbs Causeway Sustainable Transport Corridor Work Package 2 Southern section	These are a number of activities related to infrastructure improvement regarding public transport offer in the A37/A4018 corridor. These upgrades include the provision of bus priority measures, road design and enhancement of cycling and walking routes across the covered area.	Bristol city	Dec-24	Apr-26
Stockwood to Cribbs Causway Sustainable Transport Corridor Work Package 3 Revised Outline Business Case and northern section	These are a number of activities related to infrastructure improvement regarding public transport offer in the A37/A4018 corridor. These upgrades include the provision of bus priority measures, road design and enhancement of cycling and walking routes across the covered area.	Bristol city	Oct-25	Mar-27
Stockwood to Cribbs Causeway Sustainable Transport Corridor - A4018 corridor improvements	These are a number of activities related to infrastructure improvement regarding public transport offer in the A37/A4018 corridor. These upgrades include the provision of bus priority measures, road design and enhancement of cycling and walking routes across the covered area.	Bristol city	Jul-24	Nov-25
Thornbury to North Bristol Sustainable Transport Corridor	This is about a series of interventions focused on improving transport links and public transport services along the A38 connections from Thornbury to the M32.	A38 Thornbury to M32	Nov-24	Dec-26
A38 south Bristol to Hengrove Metrobus extension - Extension to Hartcliffe	This consist of a series of upgrades to the existing metrobus route to Hengrove, in combination with bus stop upgrades and bus priority measures throughout the corridor.	Thornbury and Charfield (Bristol and South Gloucestershire)	Jul-25	Dec-26
A38 south Bristol to Hengrove Metrobus extension - Bedminster Green	This consist of a series of upgrades to the existing metrobus route to Hengrove, in combination with bus stop upgrades and bus priority measures throughout the corridor.	Thornbury and Charfield (Bristol and South Gloucestershire)	Nov-22	Dec-25
Somer Valley to Bath Sustainable Transport Corridor	This activity is focused on improving links from the Somer Valley to Bath, including connections to rural communities. Interventions include better bus priority measures, creation of transport hubs and provision of new cycling infrastructure to connect those rural communities with Bath.	Somer Valley to Bath	Sep-25	Nov-26
Chipping Sodbury to Hambrook Sustainable Transport Corridor	These are a number of interventions focused on improving Active Travel links and public transport services in from University of the West of England (Frenchay) to Yate and Chipping Sodbury. Activities include enhancement of cycling infrastructure, creation of new transport hubs and road design.	Frenchay, Yate, Chipping Sodbury	Jan-25	Mar-27
Regional Station Accessibility	This activity aims to bring Lawrence Hill railway station up to a MetroWest standard regarding accessibility. Enhancements include full step free access, and where required improvements to wayfinding, easy walking and cycling access, improvements to security, CCTV and lighting.	Lawrence Hill	Jul-25	May-26
Bath Sustainable W&C links: / 1) Royal United Hospitals / 2) Sydney Gardens / 3) Scholars Way / 4) Weston to Bath City Centre	We will invest in walking and cycling facilities across Bath and Midsomer Norton area to improve the attractiveness of active travel, including new modes. The facilities include increased provision of cycle parking spaces and off-road and segregated walking and cycling routes.	Bath City Centre	Mar-25	May-26
Midsomer Norton Package: / 1) Silver Street Fosse Way / 2) Midsomer Norton to Westfield / 3) Midsomer Norton to Norton Hill School	We will invest in walking and cycling facilities across Bath and Midsomer Norton area to improve the attractiveness of active travel, including new modes. The facilities include increased provision of cycle parking spaces and off-road and segregated walking and cycling routes.	Midomser Norton	Jan-25	Jun-25
Fieldings Bridge	We will invest in walking and cycling facilities across Bath and Midsomer Norton area to improve the attractiveness of active travel, including new modes. The facilities include increased provision of cycle parking spaces and off-road and segregated walking and cycling routes.	Fieldings Bridge	Mar-27	Beyond March 2027
Bristol to Bath Railway Path improvements	This activity aims to deliver enhancement to the Bristol Bath Railway Path in the South Gloucestershire area. Upgrading of lighting and access to the path is required. To achieve year round model shift improved lighting and access is essential. This will enable commuters to access employment sites in Bristol, Bath and north fringe sustainably year round.	South Gloucestershire	Nov-24	Mar-25
Bath and North East Somerset Liveable Neighbourhoods	Proposed liveable neighbourhood scheme in Bath which will engage with local residents and business through the 'co-design' process to understand the barriers to walking, cycling, public transport and wider 'liveability'. The project will see improvements to 5 Local Cycling and Walking Improvement Plan (LCWIP) routes and 5 Core Walking Zones alongside enhancements to local connections, and ecological assets (e.g. Sustainable Drainage Systems, tree planting and parklets)	Bath and North East Somerset	Sep-24	May-26
Bristol City Liveable Neighbourhoods - CRSTS Streetspace 1 - Princess Victoria Street, Overton Road and Cotham Hill	Proposed liveable neighbourhood scheme in Bristol focused on delivering 4 LCWIP routes and one Core Walking Zone alongside enhancements to local connections and ecological assets (e.g. SUDS, Tree planting and Parklets). The scheme will interface with the regeneration of the Temple Quarter Enterprise Zone, St Phillips Marsh and Temple Meads.	Central Bristol	Jan-25	May-25
Bristol City Liveable Neighbourhoods - CRSTS Streetspace 2 - Chandos Road, Rosemary Lane, Denmark Street	Proposed liveable neighbourhood scheme in Bristol focused on delivering 4 LCWIP routes and one Core Walking Zone alongside enhancements to local connections and ecological assets (e.g. SUDS, Tree planting and Parklets). The scheme will interface with the regeneration of the Temple Quarter Enterprise Zone, St Phillips Marsh and Temple Meads.	Central Bristol	Sep-25	Jan-26
Bristol City Liveable Neighbourhoods - South Bristol Liveable Neighbourhood	Proposed liveable neighbourhood scheme in Bristol focused on delivering 4 LCWIP routes and one Core Walking Zone alongside enhancements to local connections and ecological assets (e.g. SUDS, Tree planting and Parklets). The scheme will interface with the regeneration of the Temple Quarter Enterprise Zone, St Phillips Marsh and Temple Meads.	Central Bristol	Mar-26	Feb-27
Bristol City Liveable Neighbourhoods - East Bristol Liveable Neighbourhood	Proposed liveable neighbourhood scheme in Bristol focused on delivering 4 LCWIP routes and one Core Walking Zone alongside enhancements to local connections and ecological assets (e.g. SUDS, Tree planting and Parklets). The scheme will interface with the regeneration of the Temple Quarter Enterprise Zone, St Phillips Marsh and Temple Meads.	Central Bristol	Apr-25	Jun-26
SGC Liveable Neighbourhoods (Thornbury)	Introducing through co-design a Liveable Neighbourhood approach to Yate and Thornbury	Thornbury	Mar-26	Oct-26
SGC Liveable Neighbourhood (Yate)	Introducing through co-design a Liveable Neighbourhood approach to Yate and Thornbury	Yate	Jan-26	Oct-26
Integrated Smart Ticketing	Development of new and simplified bus ticketing options across all buses in the West of England Combined Authority and North Somerset Council. It will deliver tap-on, tap-off contactless ticketing. It will allow the introduction of fare capping, faster boarding processes and the removal of the need for prior network knowledge across users.	West of England and North Somerset	Jun-22	Mar-25
Regional Transport Branding	This activity is focused on the delivery of a Regional Transport Branding. This aims to drive higher patronage across public transport and active travel modes in the West of England.	Regional	Jul-24	Mar-27
Maintenance - ITB/Maintenance Funding	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	Sep-22	Jun-27
Maintenance Challenge Fund	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	Sep-22	Jun-27
Non-highways Maintenance	The Combined Authority (CA) will dedicate a section of the highway maintenance funding to cater for localised safety and highway management improvements at locations which are outside the main proposals in the submission. This portion of funding will allow the CA to address any safety or traffic management issues which arise, in a timely fashion.	Regional	Sep-22	Jun-27
Overprogramming - Sustainable Transport Corridor Additional Value pot	This is the opportunity for all strategic corridors to enhance their existing offer through further walking and cycling provision, Enhancing connections to rural communities, first and last mile journey improvements and transport hubs	Regional
Overprogramming - Liveable Neighbourhoods Additional Value pot	This is the opportunity to enhance the liveable neighbourhood programme once trials are completed.	Regional
Overprogramming - Bus stop upgrades outside of Sustainable Transport Corridor routes	Further bus stops outside of the CRSTS sustainable transport corridors also require upgrade and standardisation.	Regional
Overprogramming - Bath City Centre sustainable transport corridor enhancements	This is the opportunity to enhance the Bath City Centre Sustainable Transport Corridor offer including further walking and cycling provision and further improvement for buses accessing the bus station.	Bath
Overprogramming - Concorde Way/ Dovercourt Depot	Off-road extension to cycling & walking strategic cycle route in North Bristol section, replacing current on-road section from Muller Road to Constable Road with high-quality walking and cycling path.	Lockleaze, Bristol
Overprogramming - Filton to MoD	Improvements to W&C routes alongside the A4174 Ring Road in Filton, from Great Stoke Way (GSW) roundabout to the Ministry of Defence facility.	Filton, North Fringe
Overprogramming - Keynsham Road	Creation of a high quality protected cycle and walking route between Bitton Station on the BBRP and Keynsham Station, along the Keynsham Road.	Bitton, SGC and Keynsham, B&NES
Overprogramming - Grovesend to Gillingstool	Stage 2 of the Thornbury Link, providing a segregated cycle route linking Thornbury to the A38 SC.	Thornbury

## WMCA
West Midlands Combined Authority - £1,050m City Region Sustainable Transport Settlement	West Midlands Combined Authority's (WMCA) delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. WMCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.	*Scheme retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
Very Light Rail Regional Programme*	Funding now split between research and development (R&D) and delivery of a demonstration project only. Demonstration project is a 220m section on Greyfriars Road/ Queen Victoria and a 600m route between Coventry Railway Station and Coventry University Technology Park (latter is subject to change control). The concept design will be completed for a potential route 1 during the SOBC phase for Coventry.	Coventry, Dudley, Birmingham, Solihull	Dec-25	Oct-26
Aldridge Station*	New station at Aldridge and reintroduction of passenger services to the station along a short section of the existing Sutton Park rail line. Development only.	Walsall	Development Only	Development Only
Wednesbury to Brierley Hill Metro Extension (Phase 2)*	Second phase of extension from Dudley	Sandwell/Dudley	Jan-25	Mar-28
Wednesbury to Brierley Hill Metro Extension (Phase 1)	First phase of extension of the Metro from Wednesbury to Dudley. Final year of Transforming Cities Fund project incorporated into CRSTS	Sandwell/Dudley	Mar-20	Nov-25
Highways maintenance and structures	Five year programme of maintenance and renewals.	West Midlands	Apr-22	Mar-27
Bus Priority Cross-city Routes	Greater priority for buses through a step-change in road space re-allocation to provide better journeys through the expansion of more bus priority across the region to speed up buses and improve reliability on new cross-city and cross-regional services as part of the core bus network	Birmingham	Jan-26	Dec-26
Metro Depot	Expansion of depot	Sandwell	Oct-22	Dec-25
Sprint A34 Phase 2	Phase 2 enables completion of the full project include priority measures in Birmingham.	Birmingham	Sep-23	Dec-25
Metro Line 1 Renovation costs	Asset renewal of Line 1 to enable continued reliable and safe operation	Wolverhampton / Sandwell / Birmingham	Nov-22	Mar-27
A4123 Walk, Cycle and Bus Corridor	Multi-modal corridor improvements, including LTN 1/20 compliant cycleway and bus priority measures.	Dudley/Sandwell/Walsall	Jan-25	Mar-27
Sprint A45 Phase 2	Phase 2 enables completion of the full project including priority measures in Solihull.	Solihull/Birmingham	Sep-24	Dec-25
East Birmingham to Solihull Corridor	Enhancements in the East Birmingham to Solihull (EBS) Corridor including bus priority measures and improved access to employment sites at UKC Hub via A45 / Damson Parkway improvements, as well as active travel improvements within the Bordesley Green area, providing improved legibility to public transport corridors with key destinations and trip attractors.	East Birmingham/Solihull	Jan-25	Mar-27
Hagley Road Rapid Transit	Investigation and development of a rapid transit route, along the Hagley Road corridor between Birmingham and the Black Country, which would serve areas without access to a heavy rail network.	Birmingham/Sandwell	Development Only	Development Only
Sutton Gateway	Sutton Gateway is an exciting package of investment to transform access to Sutton Coldfield Town Centre by bus and active travel modes.	Birmingham	Oct-25	Mar-27
Inclusive growth Local Network Improvement Plan	Five year programme of minor schemes to support inclusive growth across the seven local authorities and TfWM. Schemes could include minor junction improvements to support active travel, safety upgrades or public transport information provision on the inclusive growth corridors.	West Midlands	Apr-22	Mar-27
Connecting our places Local Network Improvement Plan	Five year programme of minor schemes to support Connecting our Places Theme across the seven local authorities and TfWM. Schemes could include public transport information provision, park and ride improvements or bus reliability improvements on key corridors.	West Midlands	Apr-22	Mar-27
Healthy Streets and Spaces Local Network Improvement Plan	Five year programme of minor schemes to support Healthy Streets theme across the seven local authorities and TfWM. Schemes could include highway safety improvements to benefit cyclists or public realm improvements to support place making initiatives.	West Midlands	Apr-22	Mar-27
Resilient Networks and Communities Local Network Improvement Plan	Five year programme of minor schemes to support Resilient Network Theme across the seven local authorities and TfWM. Schemes could include minor junction improvements, safety upgrades or bus reliability improvements on key corridors.	West Midlands	Apr-22	Mar-27
Making behaviour change easy Local Network Improvement Plan	Five year programme of minor schemes and behaviour change programmes to support Making Behaviour Change Easy Theme across the seven local authorities and TfWM. Schemes could include minor junction improvements, safety upgrades or travel demand management support.	West Midlands	Apr-22	Mar-27
City Centre Active Travel Connections to Interchange	This scheme seeks to improve walking and cycling routes across Birmingham City Centre connecting public transport interchanges with key destinations. Reducing vehicle volumes on Colmore Row is a key objective. Scheme also seeks to improve quality of existing connections between interchanges within the city centre	Birmingham	Apr-25	Mar-27
Smethwick - Birmingham Inclusive Growth Corridor Transport Package	Corridor improvements to support connectivity between deprived areas of Smethwick and West Birmingham including segregated cycling facilities. Estimated 1km of cycle interventions.	Sandwell and Birmingham	Mar-25	Mar-27
A41 Moxley Iron Park to Walsall Town Centre Walk, Cycle and Bus Corridor Phase 1	This corridor (A41/A4038) provides a key strategic link between Darlaston and Walsall town centre. The scheme extends from Moxley Junction to Walsall Rd, Darlaston Rd and Wednesbury Rd leading into Walsall town centre. It also supports access to/from the Black Country Enterprise Zone sites in the Darlaston and Pleck areas of Walsall, located immediately off the Darlaston Rd. NB. The scheme is envisaged to be delivered in two discrete (stand-alone) project phases. Phasing has been devised to maximise active travel benefits in Phase 1 in line with CRSTS objectives, and is focused on LTN1/20 cycle improvements and integration with bus and rail (Darlaston Rail Station opening late 2025).	Walsall	Mar-25	Mar-27
A454 Walk, Cycle and Bus Corridor	Corridor scheme which reallocates space to ensure that the highway suitably caters for all modes, particularly improving conditions for active travel in line with LTN 1/20 and bus priority.	Walsall/Wolverhampton	Jan-23	Mar-27
Swift contactless payment (cEMV) broker	To deliver a broker that will enable integrated cEMV contactless payment transactions with best value capping across operators and modes removing the current issue where customers are overcharged when using their bank card to travel on multiple operators services.	West Midlands	Oct-25	Dec-26
Coventry South Sustainable Transport (inc access to proposed GIGA Factory site)	The South of Coventry is an area experiencing substantial economic growth, with the establishment of a Battery Innovation Centre (BIC), the expansion of Jaguar Land Rover’s global HQ and plans to build the UK’s largest Gigafactory. This scheme will deliver sustainable transport links between the centre of Coventry and these locations	Coventry	Aug-23	Mar-26
Wednesbury to Brierley Hill Extension Sustainable Access Measures	Improve active travel connectivity to WBHE stops to reduce reliance on private cars and the possibility for informal park and ride. The scheme will also consider public transport interchange between metro and other public transport infrastructure. Aspiration to deliver 9.1km of segregated active travel infrastruture through this scheme.	WBHE corridor (Sandwell / Dudley)	Oct-24	Mar-27
Selly Oak to Longbridge Segregated Cycling Route	The scheme will extend the segregated cycle route that has already been delivered on the A38 between the city centre and the northern end of Selly Oak. The extension will be approximately 6km between Selly Oak and Longbridge. Focuses on reducing private car trips; increasing travel via active modes; creating an integrated and coherent active mode network along the study area; creating a safe environment for all road users with an emphasis on cyclists; and improving access to transport infrastructure which can improve access to skills, jobs and education.	Birmingham	Oct-26	Mar-27
Active Travel - A45 Segregated Cycleway	The A45 Active Travel Route provides a continuous, LTN 1/20 compliant link from Birmingham City Centre through East Birmingham along the A45.	Birmingham	Jan-26	Mar-27
Ultra Rapid Charging Transit Stations	The project will see the development of 9 Transit Stations located on or in close proximity to the Key Route Network/MRN/SRN for the West Midlands and hinterland.	West Midlands	Jul-25	Mar-27
Metro Traction power	The power supply that provides the backbone of the wider network is over 20 years old and increasingly unreliable and obsolete. In order to accommodate the increased service levels and numbers of trams , traction power upgrades to Line One are required.	West Midlands	May-23	Oct-26
A461 Dudley Walk, Cycle and Bus Corridor	Multi-modal LTN 1/20 compliant infrastructure improvements for active travel and bus priority for various bus routes identified in the WM BSIP.	Dudley	Jun-25	Mar-27
A461 Sandwell Walk, Cycle and Bus Corridor	Multi-modal LTN 1/20 compliant infrastructure improvements for active travel and bus priority for various bus routes identified in the WM BSIP.	Sandwell/Walsall	Jun-25	Mar-27
Ultra Low Emission Vehicles	Delivery of on-street residential chargepoints in areas with no off-street parking, as well as other EV charging facilities around the West Midlands.	West Midlands	Oct-23	Dec-26
Dickens Heath to Solihull Town Centre LCWIP Scheme	Segregated cycleway connecting the large residential area of Dickens Heath to the south of the borough with the town centre.	Solihull	May-26	Mar-27
One Station and Smallbrook Queensway	Upgrade of strategic walking routes between Birmingham New Street, Birmingham Moor Street, Birmingham Curzon Street and Birmingham Snow Hill. Upgrade and provision of new cycle routes connecting A34 and A38	Birmingham	Jan-26	Mar-27
Demand Responsive Bus (inc diversification of Ring & Ride)	New assets and improved IT systems to support wider Demand Responsive Transport deployment across the region.	West Midlands	Mar-26	Mar-27
Wolverhampton City Centre Movement - Walk, Cycle and Bus Package	LTN 1/20 compliant continuous cycle route and additional walking infrastructure will be created through the city, creating a high quality walking and cycling environment in the heart of Wolverhampton City Centre	Wolverhampton	Jan-25	Jan-27
Mobility Hubs	Mobility Hubs & E Bikes	West Midlands	Jul-25	Nov-26
Black Country Walking and Cycling Package	Delivery funding for various LTN 1/20 compliant walk and cycle corridors within the Black Country, as identified in the WM LCWIP.	Dudley/Sandwell/Walsall/Wolverhampton	Nov-25	Mar-27
Knowle to Solihull Town Centre LCWIP Scheme.	Segragated cycleway connecting Solihull town centre to Knowle, a key settlement in the rural east of Solihull.	Solihull	Mar-26	Mar-27
A449 Walk, Cycle and Bus Corridor	Walking and cycling infastructure to encourage modal shift from private car to more sustainable modes between Bushbury and Gorsebrook Roundabouts.	Wolverhampton	Aug-24	Aug-26
Dudley Town Centre Interchange Sustainable Connectivity Package	Walk, cycle, bus & general highway improvements to help unlock regeneration/jobs/homes	Dudley	Feb-26	Feb-27
Data to support scheme development plus M&E	Funding to collect, interpret and analyse data to determine the outcomes and impacts of the CRSTS projects and overall programme.	West Midlands	N/A	N/A
Chester Road Corridor – Segregated Cycleway and Capacity Enhancement.	Delivery of LTN 1/20 compliant cycle infrastructure and a modest increase of highway capacity on a heavily congested section of the A452 Chester Road through Chelmunds Cross, just north of the HS2 Interchange station.	Solihull	Jan-26	Dec-26
Solihull Rail Station	Development (only) of a multi-modal interchange incorporating increased capacity at the station, alongside significantly improved bus interchange facilities and enhanced public realm and provision / facilities for cyclists and pedestrians.	Solihull	Development Only	Development Only
UK Central - Solihull - Dorridge Bus Priority	Cross Solihull bus route, with priority infrastructure to connect the UKC Hub area with Solihull Town Centre, Cranmore and Blythe Valley Business Parks and Knowle / Dorridge.	Solihull	Mar-26	Mar-27
Snow Hill Growth Strategy	Development (only) of improvements to the Snow Hill area of Birmingham city centre including the A4540 ring road and improved active travel links across the A38, as mitigation for the potential future closure/downgrading fo the A38 Tunnels. Project is intended to enable expansion of development areas for residential and employments sites.	Birmingham	Development Only	Development Only
Multi-modal Access to HS2 Enhancement.	Development of interventions at key junctions on the highways network to improve upon the schemes proposed by HS2 including provision of LTN 1/20 compliant infrastructure.	Solihull	Development Only	Development Only
West Coast Mainline and M42 Public Transport and Active Travel bridge links to HS2 Hub.	Development of a bridge over the M42 to provide sustainable access to the HS2 Interchange site. (WCML Bridge delivery to follow with subsequent funding).	Solihull	Development Only	Development Only
Park & Ride Estate Development (Tile Hill & Whitlocks End)	At Tile Hill, delivery of bus interchange and walking, cycling and multimodal integration measures. At Whitlocks End, development of proposals for a multimodal interchange and car park expansion.	Coventry/Solihull	Feb-26	Dec-26
Foleshill Transport Package	Junction improvements, PT priority measures and walking & cycling infrastructure.	Coventry	Nov-22	Mar-27
Walk, Cycle and Bus Access: Darlaston and Willenhall Train Stations	Walk, cycle, bus & general highway improvements to help unlock regeneration/jobs/homes	Walsall	Sep-25	May-26
Rail Development	Funding for the development of a number of new stations in anticipation of subsequent delivery funding.	West Midlands	Development Only	Development Only
Stourbridge Town Centre Sustainable Connectivity Package	Walk / cycle connectivity project within Stourbridge town centre, improving perceptions of safety and making permananent changes made for EATF.	Dudley	Jan-26	Feb-27
BSIP Retrofit Programme (120 buses to Euro 6)	Retrofitting of ~50 older buses to get them to Euro 6 emissions standards.	West Midlands	Jan-25	Mar-26
Dudley Port ITH - Phase 1 and Phase 2 Development	Delivery of infrastructure at Dudley Port to improve integration and interchange between bus, rail and metro.	Sandwell	Feb-24	Mar-27
Walk, Cycle and Bus Access: Walsall Town Centre Interchange	Development funding for Walsall Town Centre Interchange, which involves reconfigured access to St Paul's Bus Station and delivery of town centre masterplan.	Walsall	Development Only	Development Only
CAF Battery / Viaduct / Metro Improvements	Onboard Energy Storage System (OESS) Service Agreement to renew batteries on 2GT and 3GT trams and support for improvements to Metro Lines.	West Midlands	Dec-23	Mar-27
Dudley Interchange	Re-build of Dudley Bus station to incorporate DIRO operations and provide better interchange with Wednesbury to Brierley Hill Metro which has a stop adjacent to the site.	Dudley	Mar-24	Jan-26
Rail Package 1 (Willenhall & Darlaston)	Construction of two new rail stations at Darlaston and Willenhall and provision of a rail service on an existing rail line which currently has no local passenger service	Walsall (Willenhall & Darlaston)	Jan-21	Feb-26
Rail Package 2 (Camp Hill Line: Moseley, Kings Heath and Pineapple Road)	Construction of three new rail stations at Moseley, Kings Heath and Pineapple Road and provision of a rail service on an existing rail line which currently has no local passenger service	Birmingham (Moseley, Kings Heath & Pineapple Road)	Mar-22	Oct-25
Retained by TfWM for critical / unavoidable cost escalations (e.g. Package 1)	Additional funding needed for Rail Package 1 - scope not yet known. Whilst actions are being taken by WMCA to limit financial exposure as a result of the administration, there will be an impact on both cost and schedule. It is too early to know the full extent of the financial implications, but every effort will be made to contain these within the budget parameters previously set out to the DfT and all options for other compensatory funding are being explored.	Walsall (Willenhall & Darlaston)	Sep-23	Mar-27
Midland Metro Birmingham Eastside Extension Interim Scheme	The full scheme involves 1.7km construction of both on street and off-street twin-tracked tramway and includes a major urban realm scheme, designed and delivered focusing upon Digbeth High Street via HS2 Curzon Street station. There will be four additional tram stops and sections of the route that will run without overhead line equipment. / This interim scheme includes the construction and operation of the first two sections and delivery of the final section.	Birmingham	Apr-21	Mar-27

## WYCA
Annex A: / West Yorkshire Mayoral Combined Authority - £830m City Region Sustainable Transport Settlement	West Yorkshire Combined Authority's delivery plan incorporates a proportion of overprogramming, additional to their agreed settlement. WYCA has flexibility to manage their programme in line with the approach to change control, but is responsible for sourcing any additional funding required to deliver the agreed schemes.	*Scheme retained by DfT and subject to business case approval by HMG
Name of Scheme	Description	Location	Start of project delivery	Completion date
West Bradford - Cycle Superhighway Extension	Delivering a direct, segregated cycle route to provide cyclists with a safe, secure space to travel easily and conveniently between Bradford city centre and areas to the west of the city.	Bradford	Nov-23	Feb-25
Bradford Interchange Station Access	Improving Bradford Interchange and access to it, including a new station approach and entrance for pedestrians giving a direct, safe and legible route from the civic quarter and City Park through to the interchange.	Bradford	Dec-23	Jun-25
Bradford City Centre Cycling and Walking Improvements	Removing through traffic from key civic areas, create corridors for cycling and walking including the introduction of new green spaces. Create a new bus priority corridor around Bradford city centre for more efficient movement of buses, with new bus hubs serving key locations in the city centre.	Bradford	Jul-23	Mar-25
South Bradford Park & Ride and Bus Expressway	Deliver a high-quality, high frequency dedicated bus service between Bradford city centre and the M606 motorway, via Manchester Road by providing a bus expressway. This scheme will be complemented by introducing segregated cycle routes, new bus hub locations, bus priority measures and linking to a park and ride site.	Bradford	Oct-24	Mar-26
West Halifax Improved Streets for People	Provide improvements for walking and cycling in West Halifax, one of the most deprived wards in Calderdale and create safer connections to Halifax town centre for those walking and cycling providing new cycle routes and footpaths, crossing facilities, changes to parking and measures to address inappropriate speeds.	Halifax	Feb-24	Dec-24
North Halifax Improved Streets for People	Create a new cycleway from North Halifax to Halifax town centre, improve pavements and crossing points for walking and cycling and improve street lighting.	Halifax	Feb-24	Dec-24
Elland Rail Station Walking and Cycling Access	Improve walking and cycling routes to the proposed new Elland railway station, this includes two new pedestrian/cycle bridges across the River Calder/Calder Hebble Navigation/West Vale., providing connections to existing cycleways and future development areas to help connect the Town Centre/station with the wider housing and employment catchment.	Elland	Sep-24	Mar-26
Heckmondwike Bus Hub	A new bus station facility in the centre of Heckmondwike, increasing bus capacity, improving passenger waiting facilities, including new toilet facilities and better bus information along with improved access arrangements to the station for buses, reducing journey times, boarding arrangements and measures to improve associated bus movements and journey times within the town.	Heckmondwike,	Nov-23	Nov-24
Dewsbury - Cleckheaton Bus, cycling and walking corridor	New bus priority measures, new/widened footways and crossings along the length of the A638 corridor, from the outskirts of Dewsbury town centre, through Heckmondwike and Cleckheaton, to Chain Bar roundabout on the M62. The scheme will also deliver sections of new segregated cycle route between Cleckheaton and Heckmondwike.	Dewsbury/Cleckheaton	Mar-24	Jun-25
Dewsbury - Batley - Chidswell Bus, cycling and walking corridor	Provide a series of bus, cycle and footway improvements along routes between Dewsbury, Batley and Chidswell. These include new cycle links, widened footways, new crossing points, bus priority at junctions and enhanced waiting facilities and bus information at stops.	Dewsbury/Batley/Cleckheaton	Jun-24	Jun-25
Dewsbury Town Centre Walking & Cycling Improvements	Improve the provision and safety of walking and cycling in and to/from Dewsbury town centre through the delivery of new and upgraded footways, crossing facilities, cycle routes and improved connectivity between the rail/bus stations and reduce severance of residential areas on the periphery of the town.	Dewsbury	Jul-24	Jul-25
Huddersfield Rail Station walking and cycling connections	Deliver more attractive and safer walking and cycling routes on key approaches to Huddersfield town centre and to its key rail and bus sites, education sites and across the ring road to reduce segregation from using more sustainable modes of transport.	Huddersfield	Aug-24	Mar-26
A64 Bus, Cycle and Walking Improvements and bus P&R	Improve bus journey times through creation of bus priority measures along the A64 and provide enhancements to existing cycle infrastructure, with additional connections to the existing cycle superhighway. The scheme will also link to a future park and ride site to provide more attractive bus journeys.	Leeds	Aug-24	Oct-25
Leeds Station - Sustainable Travel Gateway	Create a multi-modal gateway at Leeds Rail Station, including pedestrian priority areas, improved accessibility to the station, create step-free access for passengers, installation of segregated cycle lanes and widened footways, enhanced lighting within these areas and the provision of a 700 space cycle hub and infrastructure for e-bikes.	Leeds	Jul-23	Oct-25
Leeds City Centre Cycle Improvements	Consolidating and fully connecting cycle infrastructure in Leeds city centre, creating a fully segregated cycle network across the city.	Leeds	Apr-22	Mar-24
Leeds Public E- Bike Cycle Share	Provide and maintain a network of electric bikes for hire by the public within the centre of Leeds, this will complement a range of current and future cycling initiatives and infrastructure, enabling people to make journeys by bike across the city, whatever their ability.	Leeds	Aug-23	Mar-24
Wakefield City Centre Bus, Cycle and Walking Improvements	Remove elements of through traffic from parts of Wakefield city centre and provide walking and segregated cycle links from/to key locations as well as links to wider cycle provision outside of the city. New bus priority measures around the bus station will also improve bus journey times and reliability.	Wakefield	Mar-25	Mar-26
A61 Bus, Cycle and Walking Improvements	Enhanced bus priority and new, targeted, high quality cycle infrastructure. New and improved crossings for pedestrians and cyclists at key locations. New bus lanes / priority at locations in Leeds and Wakefield to improve bus journey times.	Leeds and Wakefield	Mar-25	Mar-26
A639 Bus, Cycle and Walking Improvements	New bus priority at signalised junctions to improve bus journey times alongside new or improved, targeted, high quality cycle infrastructure. The scheme will also deliver new and improved crossings for pedestrians and cyclists at key locations to improves access to bus stops and existing /new cycle routes.	Pontefract	Mar-25	Mar-26
Halifax Bus Station	Deliver a modern, fit for purpose bus station, creates a public transport gateway into the town centre, a key place of interchange for bus services, and includes a fully enclosed and level concourse facility , cycle parking and improved access for pedestrians.	Halifax	Sep-21	Dec-23
White Rose Station	Deliver a new train station which aims to provide enhanced connectivity for local people and businesses to Leeds, as well as providing improved access to Dewsbury, Huddersfield and improving accessibility to the existing White Rose site, a key employment, retail and educational hub.	Leeds	Mar-22	Nov-23
Dewsbury Bus Station	Transform Dewsbury Bus Station, improving both operational and passenger facilities, including improvements to bus flow, pedestrian access, passenger concourse and waiting areas, journey information and facilities for customers. This will significantly improve passenger experience and support the drive to encourage increased bus travel in the town.	Dewsbury	Sep-24	Feb-26
Huddersfield Bus Station	Transform Huddersfield Bus Station, improve both operational and passenger facilities, including improvements to bus flow, pedestrian access, waiting areas, journey information and facilities for customers as well as a new cycle hub. This will significantly improve passenger experience and encourage increased bus travel into the town.	Huddersfield	Dec-24	Aug-26
Public transport Network Navigation	Making it easier for bus passengers to navigate the bus network by improving legibility and improving accessibility expanding the existing Leeds Network Navigation project across the core bus network in West Yorkshire, through real-time information, bus stop information, access improvements, and journey/route planning tools.	West Yorkshire-wide	Nov-23	Jan-26
Castleford Wheldon Road Pedestrian and Cycle Bridge	New bridge for cyclists and pedestrians, to address safety issues on existing road bridge that has no provision. Links to wider Castleford growth corridor scheme that provides new cycle lanes, pedestrian facilities to the north of the town centre.	Castleford	Jan-25	Mar-26
Leeds Creating Healthier Streets, Spaces and Communities	Delivering safer streets across Leeds district through reducing through traffic and modal filters supporting mode shift from car and reduced carbon emissions. Package of measures to deliver walking and cycling improvements, through active travel neighbourhoods, school streets, improved cycle parking, District Centre enhancements and traffic signal upgrades to give greater priority for pedestrians and cyclists.	Leeds District	Dec-24	Jan-27
Wakefield Road, Bradford transformational bus priority and cycle corridor	Provision of high quality segregated bus corridor with bi-directional cycle lane from Dudley Hill roundabout to Bradford city centre. The scheme will act as a continuation of the Tong Street MRN project in terms of enhancing sustainable transport connectivity.	Bradford	Mar-26	Mar-27
Calderdale Bus hotspots and priority incl. bus lane camera enforcement	A package of interventions to improve bus journey times and reliability, including camera enforcement of bus lanes along main bus corridors and bus gates within Halifax and other district centres alongside other potential measures e.g., traffic regulation measures particularly focusing on pinch points on popular routes.	Calderdale District	Jul-25	Mar-27
North-East Calderdale Bus Priority and Cycle corridor – phase 1	Development and initial delivery of a major scheme to improve bus and active travel in north east Calderdale, reducing the impact of through traffic on local communities. The scheme enables development work on the major scheme as well as delivering bus priority between Halifax and Stump Cross. Delivery will be for the construction of the bus priority element.	Halifax and NE Calderdale	Mar-26	Mar-27
A62 – A644 Bus priority corridors- Huddersfield – Cooper Bridge – Ravensthorpe – Dewsbury	Bus infrastructure enhancements to improve bus journey times and reliability, along two main corridors within Kirklees, A62 Leeds Road / A644 Huddersfield Road. This project sits alongside several transport schemes already in progression in order to provide continuity and additionality to provide sustainable transport enhancements over a wider area.	Cooper Bridge/Mirfield	Jan-26	Jan-27
Beckett Street, Leeds – transformational bus priority scheme	Planned improvements located over two sections of carriageway north and south of the junction with Lincoln Green Road to accommodate a new section of bus lane outbound. The northern section is to be widened to accommodate new bus lanes both outbound and inbound. A bi-directional segregated cycleway will be built and improved bus stop facilities and an improved pedestrian environment will also be part of this key scheme.	Leeds	Jan-25	Mar-26
Leeds City Centre Bus Priority	A package of measures that builds on the success of Leeds city centres schemes being delivered through other funding programmes to enhance the sustainable transport offer in Leeds city centre by re-allocating existing carriageway to more sustainable modes, in accordance with LTN 1/20 and the National Bus Strategy.	Leeds	Jan-23	Nov-23
Bus Priority Active Travel Cycle Loops	Package of schemes that builds on the success of city centres schemes being delivered through other funding programmes (TCF, LP TIP , and the Transport Fund) to enhance the sustainable transport offer in the core city centre by re-allocating existing carriageway to more sustainable modes, in accordance with LTN 1/20 and the National Bus Strategy.	Leeds	Aug-24	Aug-25
A639 Park Road, Pontefract – on and off highways improvements	Enhanced bus priority and new, targeted, high quality cycle infrastructure. New and improved crossings for pedestrians and cyclists at key locations. New bus lanes / priority at locations in Leeds and Wakefield to improve bus journey times.	Leeds and Wakefield	Jun-25	Feb-26
Heath Common to Knottingley Bus Priority	This scheme aims to improve public transport offer along the ~22km route between Wakefield and Knottingley, linking key conurbations such as Pontefract and Featherstone along the way. Detailed options will be considered at a later stage but will include infrastructure changes that prioritise bus travel along the route, improve accessibility for public transport users, and ultimately encourage modal shift for the journeys that use this link. At its core, this scheme aims to improve transport options for residents of all backgrounds and income brackets and provide a more sustainable link for the Five Towns and Wakefield.	Wakefield, Featherstone, Pontefract and Knottingley	Jan-26	Jul-26
Horbury to Wakefield / Ossett to Wakefield bus priority	This scheme will focus on bus infrastructure enhancements to improve bus journey times and reliability along the corridors, which will contribute to improved air quality in the surrounding areas. The scheme will identify bus enhancements along the corridors and also identify opportunities for improvements to cycling and pedestrian infrastructure where appropriate. Especially concerning accessibility to bus stops to facilitate the integration of active travel and public transport journeys.	Wakefield, Horbury and Ossett	Jan-26	Jul-26
West Yorkshire Rail Accessibility Package - Small Scale Station Improvements	Improve the accessibility and inclusivity of West Yorkshire rail stations, reducing the barriers to travel and improving passengers’ travel experience especially for those with disabilities and other disadvantaged groups. Contribute towards making a fully accessible transport system	Various Stations across West Yorkshire	Apr-24	Dec-24
West Yorkshire Rail Accessibility Package - Large Scale Station Improvements	Improve the accessibility and inclusivity of West Yorkshire rail stations through targeted improvements to improve the user experience of persons with restricted mobility, reducing the barriers to travel especially those with mobility impairments and other disadvantaged groups. Contribute towards making a fully accessible transport system	West Yorkshire wide	Feb-25	Mar-27
Kirklees enhanced Electric Vehicle programme - residential charging and support programme	Developing Kirklees as a national demonstrator for larger scale Electric Vehicle Charging deployment, including the provision of charging on residential streets without impinging on the walking or cycling experience. This package includes a “try before you buy” Electric Vehicle scheme and delivery of on-street charging points.	Kirklees district wide	Oct-24	Mar-27
Kirklees district wide speed limit review	The scheme will lower speed limits where appropriate to 20mph in built up areas and 40mph and 50mph on some busy rural routes, improving safety, reducing pollution and carbon emissions, on roads where traffic speeds are dangerous and reduce the ability of the network to support walking, cycling or accommodate bus.	Kirklees district wide	Jun-24	Mar-27
CoSa	The project will procure the systems/software that will replace the functionality currently provided by the Combined Services and Assets system to enable the Combined Authority to meet its statutory obligation in the provision of public transport information and network management. The project also includes the selection of an implementation partner to lead on gathering requirements, analysis of potential solutions, and creation of procurement documentations of any off-the-shelf solutions.	West Yorkshire wide	Jul-23	Mar-25
Integrated ticketing and Payment	A range of initiatives, complemented with BSIP revenue funding, that support improved ticketing and information including:	West Yorkshire wide	Oct-23	Mar-27
Car club network electrification	Electrification of the existing car club network within West Yorkshire. This will include delivery of EV charge points, replacement of some existing charging infrastructure that is no longer fit for purpose and creation of a fund for operators to bid into in order to gap fund EV car club vehicles. Delivery of the charge points will be aligned with the mobility hubs and wider EV charge point delivery programme in West Yorkshire.	West Yorkshire wide	Mar-24	Oct-25
Integration - Mobility Hubs Ph2	Delivery of mobility hubs in locations across West Yorkshire. These hubs will increase local transport accessibility by providing access to demand responsive transport services, shared bikes, car club and EV charging facilities to complement existing public transport networks. Facilities delivered at the hubs include – cycle parking, cycle hire, EV charging points, passenger information and improved waiting facilities.	Specific locations within West Yorkshire	Jun-24	Mar-27
Community Transport Vehicle renewal and upgrade to electric vehicles	Access Bus community transport vehicle fleet replacement and upgrade to electric vehicles.	West Yorkshire wide	Oct-24	Jul-26
Integrated Information	A range of initiatives that support improved ticketing and information including: / • Installation of tap-out card readers and electronic ticketing machines (to enable pay-asyou-go capping) / • Retrofitting of vehicles with onboard audiovisual information technology / • Further development of the MCard mobile app / • Enhanced disruption messaging / • Information accessibility enhancements	West Yorkshire wide	Mar-25	Mar-27
Demand Responsive Travel	Delivery of demand responsive bus schemes across West Yorkshire. Based on the lessons learned from the East Leeds Flexibus scheme DRT schemes will be developed to address specific areas of need where public transport access is currently poor.	Specific locations within West Yorkshire	Apr-25	Dec-25
Highways Safer Roads programme	CoSA enables WYCA to create and manage bus routes and on-street assets and receive data from several sources including bus service registrations, including by electronic means; Operator; Contractor; Pupil; Parent and School information.	West Yorkshire wide	Apr-22	31/04/27
Steeton and Silsden cycling and walking Improvements	An active travel corridor including a pedestrian and cycle bridge over the A629 dual carriageway reducing the severance between two communities, provide protected cycleways and wider footways connecting to the bridge creating a safe and attractive route between the two settlements	Steeton and Silsden	Feb-26	Feb-27
West Yorkshire EV Charging and Local Place/ Neighbourhood Package	Improvements within local neighbourhoods to create safer, more economically active local areas and high streets. Delivering improvements to walking and cycling provision alongside other potential measures improvements such as electric vehicle charging points, bus gates, car club spaces, cycle parking, sustainable urban drainage and the creation of informal/formal mobility hubs.	West Yorkshire wide	Apr-25	Mar-27
Dalton Deighton Active Travel Route	Quality, off-road walking and cycling route, complementing future on-road infrastructure by improving access to settlements and new development by active modes. Benefits include less congestion, reduced journey times, improved air quality, improved safety, reduced noise, and better social and economic outcomes in local communities.	Dalton/Deighton	Jan-26	Jan-27
A660 bus priority & cycle corridor incl. Lawnswood roundabout	Bus priority and cycle provision along key corridor in north Leeds, providing bus priority and segregated cycle provision on the corridor, including improvements to Lawnswood roundabout to address cycling safety issues	Leeds	Sep-24	Sep-25
Zero Emission Buses	Introducing Zero Emission Buses and related infrastructure, building on current zero emission bus programmes to help achieve our targets in the Bus Service Improvement Plan to raise the total proportion of the fleet to 50% by 2030	West Yorkshire wide	May-24	Oct-26
Leeds Station - Platform 13/17 extension - allowing longer trains and better rail services to the Five Towns/Wakefield district	Extension of platform 17 to improve capacity by facilitating longer trains, plus changes to platform access from the overbridge to allieviate crowding issues.	Leeds	Nov-24	Apr-26
Highways Asset Management and Enhancement	The programme will implement renewal and improvement of highway assets, including roads, structures, cycleways, footways, lighting and drainage across West Yorkshire. Asset enhancement will also benefit sustainable modes of travel by introducing elements of bus, cycle and walking improvements into traditional asset renewal projects.	West Yorkshire wide	Apr-22	Mar-27
Highways Network Management and Enhancement	The programme will replace out-of-date and high-risk signal infrastructure as well as introduce modern network management systems that allow opportunities for detection and priority of pedestrians, cyclists and buses at junctions, including smart traffic control that can automatically respond to congestion and air quality information.	West Yorkshire wide	Apr-22	Mar-27
Bradford Interchange – bus station refurbishment and renewal	Re-waterproofing of the concrete deck, plus resurfacing of the carriageway. Includes any repairs to the surface of the concrete deck as required	Bradford	Sep-22	Apr-24
Bus shelter refurbishment and renewal	Shelter refurbishment, renewal and improvement package, delivering renewal of life expired shelters and new features and facilities to create greener and more innovative shelters. These could include intelligent shelters, phone charging, Real Time I information screens, advertising, and solar panels	West Yorkshire wide	Dec-24	Mar-27
Bus Infrastructure works	The scheme will deliver improvements at bus stations and stops to make public transport more accessible to everyone, developing solutions through engagement with disabled people. It will also deliver an Invest to Save programme to reduce consumption and waste, leading to carbon reductions across the public transport estate. Phase 1 of this project is currently underway , CRSTS will fund Phase 2.	West Yorkshire wide	Dec-24	Mar-26
Highway works	The scheme will deliver improvements at bus stations and stops to make public transport more accessible to everyone, developing solutions through engagement with disabled people. It will also deliver an Invest to Save programme to reduce consumption and waste, leading to carbon reductions across the public transport estate.	West Yorkshire wide	Dec-24	Mar-26
Bus Station refurbishment- additional priorities	Improvements to bus stations across the region to improve customer experience and make bus journeys a more attractive and competitive option	Bradford	Apr-25	Dec-26
Off Highway walking and cycling routes	Improvements to the Public Rights of Way Network to support active travel and place improvements within the CRSTS programme, delivering measures to support accessible, active travel modes and links to public transport facilities on existing rights of way and cycle routes.	West Yorkshire wide	Apr-22	Apr-24
Kings Road sustainable travel corridor improvements	Provision of a segregated cycle lane on both sides of Kings Road . A bus priority corridor including combination of bus lanes, bus gates and bus priority features. Delivery of a high quality walking and cycling corridor with associated public realm improvements	Bradford	Mar-26	Mar-27
A660 - Northern/University Gateway inclusive of the Headrow to St Marks Road.	Addressing bus delay through improvements in Leeds city centre up to the Inner Ring Road. From there, the scheme will remove general traffic from Blenheim Terrace in both directions, creating a bus, cycle and walking only environment, facilitated through the provision of bus gates and complementing the proposed A660 protected cycle lane.	Leeds	Apr-25	Sep-26
South Wakefield Bus Package	Targeted bus priority at key locations in Wakefield district. This is expected to include new bus lanes and priority provision at junctions along the bus corridor to improve bus journey times.	Wakefield	Jan-26	Jul-26
North Wakefield Bus Package	This scheme will focus on bus infrastructure enhancements to improve bus journey times and reliability along the corridors, which will contribute to improved air quality in the surrounding areas. Since more than 91% of transport emissions in the UK originate from road transport, 78% of which are from private vehicles, enabling more journeys by active and public transport will be integral to achieving our ambition to tackle the climate emergency. Whilst the main objective of the scheme is to identify bus enhancements along the corridors, the scheme will also identify opportunities for improvements to cycling and pedestrian infrastructure where appropriate. Especially concerning accessibility to bus stops to facilitate the integration of active travel and public transport journeys.	Wakefield	Jan-26	Jul-26
Bradford Bus Hotspots	This scheme will focus on bus infrastructure enhancements to improve bus journey times and reliability along the corridors, which will contribute to improved air quality in the surrounding areas. Since more than 91% of transport emissions in the UK originate from road transport, 78% of which are from private vehicles, enabling more journeys by active and public transport will be integral to achieving our ambition to tackle the climate emergency. Whilst the main objective of the scheme is to identify bus enhancements along the corridors, the scheme will also identify opportunities for improvements to cycling and pedestrian infrastructure where appropriate. Especially concerning accessibility to bus stops to facilitate the integration of active travel and public transport journeys.	Bradford	Jan-26	Jul-26
Elland Road South/Churwell Hill	Project involves a range of interventions to reduce congestion on Bradfords bus network by reducing delays to customer journeys, removing overall congestion from busy roads such as Leeds Road gyratory and improving road safety with the aim to promote a move towards sustainable transport.	Leeds	Mar-25	Jan-26
Thirsk Row/King Street- bus gate/access road	Enable an existing one-way street to be two-way for buses along with a new bus gate enabling buses to avoid unnecessary and highly congested movement in the city centre. It will also enable a wider footway and an extension of the existing bi-directional cycle track.	Leeds	Nov-22	Dec-23
Mass transit development and delivery*	Development and initial delivery of a new form of public transport system for West Yorkshire, to increases capacity and provide an alternative to car travel for the region, linked to bus, rail, cycling and walking networks across the region as part of an integrated transport system.	West Yorkshire	Mar-28	Dec-31