Public Service Delivery Review Board minutes of meeting

Meeting date: 12 March 2024, hosted remotely via Microsoft Teams.
Attendees: Sue Bateman (CDDO), Rhian Jones (CDDO), Patrick Kiernan (CDDO) Sulaiman Saeed (CDDO), Ebru Yilmaz (CDDO), Sadia Siema (CDDO), Jack Ramsden (DESNZ), Ross Young (UKSA), Jenny McEneaney (LGA), Stephen Mak (DLUHC), Alison Dewar (Scottish Government), Anna Bartlett-Avery (Welsh Government)

Observers: Debra Heaton (ICO)
Speakers: (Scottish Government) Joanna MacKenzie (Scottish Government), Peter Grant (Scottish Government), Louise Anderson (Scottish Government)

Apologies: Alessia Morris (Scottish Government), Edgar Whitley (PCAG), Darrell McCullough (Northern Ireland Government), Louise Bennett (PCAG), Louise Greenrod (NHSX/DHSC), Andy Gregory (Home Office), Glyn Jones (Welsh Government), Emma Wharram (DfE), Mark Brewin (HMRC), Helen Walker (DWP).

1	Welcome and introduction from the Chair
1.1	The Chair welcomed Members to the meeting
2	Conflicts of interest, action points and minutes from the last meeting
2.1	The following action points were closed: / Action point 69: Secretariat to publish minutes from 13 June 2023 / Action point 72: Secretariat to liaise with Review Members on suggestions raised [in relation to the way the quarterly analysis is conducted / The following action points are covered in the update paper. / Action point 70: Secretariat to update on the progress scoping the emergency planning and recovery and early help proposals. / Action point 71: Secretariat to check the impact of the Data Protection and Digital Information Bill on timings with relaying a revised Code of Practice.
2.2	Minutes from the last meeting on 12 December 2023 were approved / Action point 73: secretariat to publish minutes from 12 December 2023 on GOV.UK
3	Work programme update
3.1	The secretariat informs members that the Identity Verification Services objective was enacted on 8 February 2024 and the first IVS has been added to the register of information sharing agreements.
3.2	The secretariat are continuing to work with the Scottish Government to promote the use of the ELC objective.
3.3	Members are informed that the Secretariat has worked with DSIT to assess changes to the DEA Code of Practice following the passage of the DPBI Bill through Parliament. / Action point 74: UKSA requested to discuss aligning the updates to the Research and Statistics Codes.
3.4	Members were informed of work being carried out to assess how the PSD power could be used to provide support for individuals living in fuel poverty.
3.5	Members were updated on work carrying out to triage objectives that have been presented to the Review Board previously in order to prioritise efforts to advance these objectives as formal proposals as soon as possible: / Dormant Assets: work is underway for HMRC to share the outcomes of the pilot with HMT. / Free School Meals: the Secretariat is working with colleagues in HMRC, DWP and the Scottish government to collate the information needed to progress the objective to a formal proposal. / The Secretariat has resumed conversations with colleagues in the Civil Contingencies secretariat to progress the Emergency planning and recovery objective - colleagues from the Devolved Administrations to be included in due course / The Secretariat has also engaged colleagues in DLUHC/DfE in evaluation of the early help and prevention objective / Action Point 75 to include SM when meeting with the resilience and recovery directorate (RED) / Action Point 76 Secretariat to follow up with JM on early help and prevention objective
3.6	Members are informed that the Secretariat has worked with DSIT to assess changes to the DEA Code of Practice following the passage of the DPBI Bill through Parliament.
4	Presentation: public register analysis and quality review
4.1	The secretariat gave an update on the use of the public service delivery, civil registration, debt and fraud powers.
5	Presentation: Early learning and childcare
5.1	Colleagues from the Scottish government gave a presentation on the use of the early learning and childcare objective which included an overview of the data sharing process and how some councils in Scotland are using the data. / Members discussed the benefits that the data sharing has enabled, and the Chair welcomes Scottish colleagues to provide further insight into Scottish Government’s use of the ELC power at Data Connect
7	Risk Register
7.1	Members were informed that there have been no updates to the risk register at this time.
8	AOB
8.1	A potential use of the PSD power raised by correspondence which the Secretariat committed to explore further. / Action Point 77: Secretariat to meet with HMRC to discuss further how the PSD power could support the sharing of VAT data
8	DONM 13 June 2024