Public Service Delivery Review Board minutes of meeting

Meeting date: 26 September 2024, hosted remotely via Microsoft Teams.

Attendees: Craig Suckling (CDDO), Rhian Jones (CDDO), Michaela Freeland (CDDO), Ebru Yilmaz (CDDO), Sadia Siema (CDDO), Sulaiman Saeed (CDDO), Patrick Kiernan (CDDO), Glyn Jones (Welsh Government), Edgar Whitley (PCAG), Louise Bennett (PCAG), Alessia Morris (Scottish Government), Helen Walker (DWP), Mark Brewin (HMRC), Sue Wharram (DfE), Louise Greenrod (DHSC), Lucy Maguire (MHCLG), Mark Williams (LGA).

Speakers: Rachel Wallce and Stuart Pescodd (Scottish Government)
Observers: Daniel Barnett and Sara Lawrence (ICO)
Apologies: Andy Gregory (Home Office), Ross Young (UKSA), Stephen Mak (MHCLG), Ruth Richmond (DESNZ).

1	Welcome and introduction from the Government Chief Data Officer, Craig Suckling
1.1	Craig Suckling welcomed members to the meeting and highlighted the critical nature of the Board’s role in delivering key government data priorities. He then introduced the Board’s new chair, Michaela Freeland. / Michaela Freeland thanked members for joining the meeting and welcomed new Board members, Sue Wharam (DfE) and Ruth Richmond (DESNZ).
2	Conflicts of interest, action points and minutes from the last meeting
2.1	The following action points were closed: / Action point 73: Secretariat to publish minutes from 12 December 2023 on GOV.UK. / Action point 76: Secretariat to follow up with Jenny McEneaney on the early help and prevention objective. / The following action points were covered in the update paper: / Action point 74: UKSA requested to discuss aligning the updates to the Research and Statistics Codes. / Action point 75: Secretariat to include Stephen Mak when meeting with the resilience and recovery directorates. / Action point 77: Secretariat to review how the PSD power could support the sharing of VAT data as part of the work programme.
2.2	Minutes from the last meeting on 12 March 2024 were approved. / Action point: secretariat to publish the minutes from 12 March 2024
2.3	Sue Walker and Mark Brewin raised potential conflicts of interest as agenda item 3 (the passported benefits proposal) seeks to share data held by DWP and HMRC.
3	Scottish passported benefits proposal
3.1	The Secretariat presented a proposal seeking to streamline access to Scottish passported benefits for individuals and households. / Members discussed the proposal, querying its territorial extent, particularly on whether the objective should be UK wide, including England and Wales. / In response, the Welsh Government (WG) confirmed support for the proposed initiative and expressed interest in expanding it to Wales. DfE agreed to seek a view from Ministers on the objective’s application in England. / Members queried the process for the objective being expanded to include Northern Ireland once the PSD power was commenced. / The Secretariat confirmed that it would explore expanding the territorial application of the proposal. / Members discussed further details of the proposal, focusing on the frequency of means tested assessments and clarification of applicant duties regarding a change of circumstances. / Scottish Government representatives explained that it would be the applicant's responsibility to report circumstantial changes but agreed that this, as well as the frequency of means tested assessments, should be further clarified in the proposal and relevant documents. / Action point: Secretariat to liaise with the Department for Education and Welsh Government to explore expanding the territorial application of the proposal to include England and Wales. / Action point: Secretariat to issue the proposal form via email
4	Work programme update
4.1	The Secretariat provided an overview of the work programme update paper of which the key priorities included: / Commencing the DEA powers in Northern Ireland / Amending s35 of the DEA to include business via the Data Usage and Access (DUA) bill (which is expected to enter Parliament during first session) / Exploring data sharing to support vulnerabilities / Revising the Code of Practice in line with the DUA bill timeline / Updating the DEA register entry process / Members queried the process for users to differentiate between debt/fraud pilot data shares and business as usual data shares. / Action: Secretariat to review comments raised and consider amendments to the register or supplementary guidance.
5	Risk Register
5.1	Members were informed that there had been no new updates to the risk register.
6	AOB
6.1	The Secretariat highlighted the new Government's ambition to improve public services and suggested that there could be proposals submitted to the Board outside of the regular scheduled meetings.
7	DONM: 12 December 2024