## Guidance
Second Hydrogen Allocation Round (HAR2) Request for Information (RFI) template
This document forms part of the due diligence phase and should be completed alongside the Project Datasheet and the Financial Statement Form. It will be used by DESNZ and its advisers to confirm and verify any aspects of the application and to seek an update on all technical, financial and commercial compliance matters. Please complete and return this document in .xlsx format provided.
Applicant Details
Project Name | [Project name]
Lead Project Developer | [Project developer]
Is your project a HAR1 expansion project? | [Yes/No]
Applicant RFI Response Guidance
Please read before completing this template.
Questions The aim of this document is to check the progress made on the HAR2 project application since the original submission in April 2024, and gather more information to address any areas of concern highlighted during the assessment. The questions in this template have been categorised into three types: 1) Technical 2) Financial and Commercial 3) Additional questions Responses A response should be provided to all questions asked in the relevant sections on each tab. Delays or refusals to provide necessary information requested could lead to engagement with projects through the due diligence process being discontinued. For Technical questions, applicants should provide minimum expected evidence where requested, which represents the ambition of maturity for projects in the HAR2 process and are not a fail/pass criteria for technical due diligence assessments. Projects should provide quality evidence (Column J and K) and be clear where minimum expectations are not fully met in the 'Applicant Narrative' (Column M). The narrative should set out clearly how applicants are on track to meet these expectations and that their deliverability risk remains low. For Financial and Commercial questions, applicants should provide evidence as listed in Column H, where relevant, and use the 'Applicant Response' in Column J to provide any necessary supporting information. Applicants should also complete the 'Financial Statement Form', alongside providing the information requested in question F3.1 'Financial Health - Company-level'. Projects should provide quality evidence and be clear where evidence hasn’t been provided, including rationale for evidence not being provided, demonstrating that their deliverability risk remains low. For Additional questions, please answer the question in full and provide any supporting evidence requested. The applicant should keep to the word count, but may request to provide additional details to DESNZ, where relevant. Applicants should contact HAR2@energysecurity.gov.uk as soon as possible with this request. Project Datasheet Data provided through the Project Datasheet, which is a separate spreadsheet that must be populated, needs to align and be substantiated by the relevant written response within this document. For example, the completed production facility data must align with the FEED study provided. Evidence Please resubmit all evidence relevant to this RFI return, even if it remains unchanged from application stage. Any evidence that has been updated and resubmitted since application stage, should clearly highlight all changes since the original submission, for example, tracked changes on a Project Execution Plan. Please note that in order to ensure a thorough review of all submitted evidence, it is required that all evidence be accompanied by clear and concise identification of relevant pages or sections as they relate to the question at hand. DESNZ reserves the right to not review any submitted evidence if relevant sections are not clearly referenced. All evidence submitted must be added to the evidence register tab, please add additional rows if required. If any submitted evidence is not part of the suggested or minimum expected evidence list requested by DESNZ, you must provide a justification as to why it has been submitted. DESNZ reserves the right to not review a submitted document if the justification is blank.

## Technical
Request for Information Questions: Technical
RFI ID | Assessment criteria | Question | Minimum expected evidence | Minimum expected evidence shall include, where relevant | Self-declaration that the evidence provided meets all the requirements set out in column I. (If unable to provide min. evidence, please select no and complete narrative in Column M and reference supporting evidence in Column P) | Minimum expected evidence references | Applicant Narrative (where required if minimum evidence cannot be met in Column J) | Word Limit | Word Count | Narrative supporting evidence references
T1.1 | Schedule and Risk Management | Schedule Delivery Please provide a Level 3 project schedule which clearly shows all key changes and progress made since the original submission, as well as all remaining planned activities. This should substantiate the evidence, and responses provided to all other RFI questions and should show how key risks have been considered. All milestone/activity changes since last submission should be easily comparable to the previous submission. Assessing and Managing Project Risks Alongside the schedule, please provide an updated project risk register. (Note, this criteria is to be assessed based on the evidence provided. No narrative is required for this criteria). | Project Schedule (>Level 3) | ● Expected timescales and milestones for completion of activities related to: • Planning, consents and land agreements, • Grid connection, • Offtaker agreements and enabling works required, • Feedstock, water supply and waste management arrangements, • Financial Investment Decision, • Procurement, including long lead time items and services, • Design, construction and commissioning. ● Critical path ● Progress made to date ● Planned float |  |  | This criteria is to be assessed based on the evidence provided. No narrative is required for this criteria
T1.2 |  |  | Updated risk register | ● At least a qualitative assessment of project risks ● Planned actions being taken to mitigate risks ● Identification of risk owners |  |  | This criteria is to be assessed based on the evidence provided. No narrative is required for this criteria
T2.1 | Planning, Consents and Land (including all aspects of the project, including, where relevant, the production facility, utilities, and hydrogen distribution and storage infrastructure) | Understanding Planning & Consenting Requirements Please provide evidence of a site-specific planning appraisal which details considerations made with regards to all consents and permits required for the construction and operation of the facility. If a PLANC register (or similar) has not been provided, please provide narrative in Column M with supporting evidence in Column P to justify how the evidence provided demonstrates that all planning requirements are understood and being managed. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Site-specific planning appraisal / statement | ● PLANC register or similar demonstrating all site-specific pre-requisites are understood and being managed |  |  |  | 200 | 1
T2.2 |  | Achieving Planning Approval Please provide a copy of your submitted planning application. If a submitted planning application, or approval has not been provided, please provide narrative in Column M with supporting evidence in Column P to justify how the evidence provided demonstrates that securing planning permission is low risk to deliverability and the project will be able to submit a planning application ahead of a potential contract award. This should include evidence that an EIA is not required, or if required, is progressed in addition to engagement with the local authority. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Planning application submission, or approval notice | ● Confirmation that a planning application has been submitted including: • Planning application reference number • Copy of submitted planning application and/or ● Approval notice |  |  |  | 200 | 1
T2.3 |  | Obtaining an Environmental Permit Please provide evidence of engagement with the UK environmental regulator for the proposed location of your project (e.g. Environment Agency if your project is in England, SEPA in Scotland and NRW in Wales) to demonstrate that obtaining the required environmental permits presents low risk to delivery. If evidence of engagement with the Environmental Agency has not been submitted, please provide narrative in Column M with supporting evidence in Column P to justify how the evidence provided demonstrates that either an environmental permit will be secured in time to take FID within HAR2 windows or securing an environmental permit will not prevent FID being taken and will be in place to allow COD within HAR2 windows. The narrative must demonstrate that securing an environmental permit is low risk to deliverability and the project. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Engagement with the UK environmental regulator for the proposed location of your project with regards to environmental permits | ● Evidence of engagement with the UK environmental regulator for the proposed location of your project to demonstrate that obtaining the required environmental permits presents low risk to delivery |  |  |  | 200 | 1
T2.4 |  | Existing Environmental Permits Please detail any existing sites connected with the proposed HAR2 project (e.g. offtaker) area currently holding an Environmental Permit for another activity, and whether this permit is regulated by a UK Environmental Regulator (EA, SEPA, NRW), or the local authority, if known. | N/A | N/A | NA | N/A |  | 200 | 1
T2.5 |  | Understanding Planning Updates to HAR1 Projects For those HAR2 projects that are expansions of HAR1 projects, please provide narrative in Column M with supporting evidence in Column P to explain how any changes to the design and planning status of the HAR1 project has subsequently affected the planning status of the HAR2 project and how this is being managed e.g. if an offtaker has changed or distribution method has changed from pipeline to tube trailers. (Note, if your project is not an expansion of a HAR1 project, there is no need to provide a narrative for this question) | Narrative only | Narrative only |  |  |  | 200 | 1
T2.6 |  | Securing Land Agreements Please provide signed heads of terms (HoT) with the landowner. If providing signed HoTs with the landowner is not possible, please provide narrative in Column M with supporting evidence in Column P, explaining when you will obtain this and justify how obtaining this is considered low risk. This should include written confirmation from the landowner demonstrating their intent to reach an agreement by FID. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Signed land agreement (HoT) with the landowner. | ● All HoTs between the current landowner and the project developer, including copies of the title deeds proving ownership and any HoTs between intermediary or group organisations. |  |  |  | 200 | 1
T3.1 | Supply Chain - Equipment | Progress and Approach to Procuring Key Equipment Please provide the necessary minimum evidence to demonstrate that milestone commitments stated within the application relating to the procurement of critical equipment have been achieved (such as tendering for and selection of key equipment) and that tendering process are ensuring a balance of value for money, low delivery risk and equipment performance/reliability. Where milestones have not been achieved, please provide a narrative in Column M with supporting evidence in Column P justifying why any have been missed and the risk to deliverability is low. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Project procurement strategy setting out approach to procurement of equipment. Decision summary and firm quotation (not budget estimate) with each key equipment manufacturer or submitted purchase orders, this could include but is not limited to the electrolyser, compression, storage, transformers and other high voltage equipment. | ● Procurement strategy ● Example decision paper(s) or matrix for key supplier choices (e.g. electrolyser). ● Quatlity Assurance/ Control plan. ● Quotes for all key equipment (e.g. electrolyser) and all other long lead items (e.g. transformers, HV equipment, storage equipment and compressors) ● Project specific quotes i.e. quotes that align with design ● Quotes including delivery timescales |  |  |  | 200 | 1
T3.2 |  | Plan to Secure Outstanding Equipment Provide narrative in Column M to justify how any outstanding activities to place orders for equipment (e.g. electrolysers, compressors, storage) will be completed in time to avoid any delays to COD and that sufficient lead-in times and float have been included within the schedule. | Narrative only. | Narrative only. |  |  |  | 200 | 1
T4.1 | Supply Chain - Key Delivery Services | Progress and Plan to Secure FEED Services Please provide your FEED contract and tender documents or evidence of internal capability, where relevant. Where this is not possible, please provide narrative in Column M with supporting evidence in Column P to evidence progression towards securing FEED services and justify why the risk to deliverability is low. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | FEED contract and tender documents or evidence of internal capability, where relevant. | ● For FEED supplier: • Invitation to tender • Scope • Selection criteria • Decision summary • Draft and/or final contracts or ● or evidence of internal capability including a Project Execution Plan (PEP) or equivalent including: • A RACI matrix or equivalent for FEED • Management processes/procedures which will be applied to enable the successful delivery of FEED e.g. risk management plan, communications plan • Quality assurance processes/procedures which will be applied to enable the successful delivery of FEED |  |  |  | 200 | 1
T4.2 |  | Progress and Plan to Secure Engineering Delivery (e.g. EPC) Services Provide evidence to demonstrate how any outstanding activities to award delivery contracts will be completed in time to avoid any delays to COD and that sufficient lead in times (and float) have been included within the schedule. Where this is not possible, please provide narrative in Column M with supporting evidence in Column P to show progression towards securing delivery services and justify why the risk to deliverability is low. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Project contracting strategy setting out breakdown of responsibility, and approach to managing different phases of the project. Procurement documents to demonstrate sufficient progress towards selecting and securing an EPC contractor. | ● Contracting strategy ● Quality assurance processes which will be applied to project execution. ● For EPC supplier: • Invitation to tender • Scope • Selection criteria or ● or evidence of internal capability including a Project Execution Plan (PEP) or equivalent including: • A RACI matrix or equivalent for EPC • Management processes/procedures which will be applied to enable the successful delivery of EPC e.g. risk management plan, communications plan |  |  |  | 200 | 1
T5.1 | Design Development | Design Viability and Development Please provide your FEED study for all aspects of the project including, hydrogen production, storage, distribution, offtaker connections, electricity/water/waste infrastructure. If a FEED cannot be provided, provide evidence of pre-FEED work done to date and provide narrative in Column M with supporting evidence in Column P to justify how the remaining design work can be completed to allow COD within the HAR2 window. This narrative should include detail on how sufficient design progress will be completed to enable accurate costs to be developed, should the project be taken through to the next stage beyond due diligence. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Full project-specific FEED study detailed to a level to produce an AACE Class 3 cost estimate. Complete documents are required. | ●For all aspects of the project including, hydrogen production, storage, distribution, offtaker connections, electricity/water/waste infrastructure please include: • Sizing • P&ID • PFD /UFDs • Electrical SLD • Electrical Load List • Mass and energy balance • Layouts • RAMs • Operating Philosophy • Process/ Technical Safety Documentation (e.g. Philosophy, HAZID, ENVID) • Plans for laying and operating any required hydrogen pipeline ● Hydrogen production, offtaker demand and electricity supply half hourly profiles. Referencing actual meter readings or similar data sets to indicate how the profile has been developed. Including evidence of the electricity generation mix which aligns with production (e.g. production plan for when wind/solar assets are not generating). This should align with planned storage requirements. ● Manufacturer guarantee offers or similar for key equipment to demonstrate reliability e.g. guarantees, a reliability and maintenance study |  |  |  | 200 | 1
T5.2 |  | Hydrogen Pipeline Requirements Where applicable, provide narrative to justify the project's plans for laying and operating any hydrogen pipeline (i.e. will it be managed by the project organisation as an unlicensed operator or will a local GDNO manage it as a permitted development), conversion requirements and logistics. | Narrative only. | Narrative only. |  |  |  | 200 | 1
T6.1 | Offtaker Arrangements | Progress in Securing Offtaker Agreements Please provide signed HoTs covering 100% of hydrogen volumes intended to be produced by the project. Where signed HoTs aren’t available for all offtakers, please provide narrative in Column M with supporting evidence in Column P to demonstrate confidence that: a) There is a robust plan for completing all outstanding work required to reach a draft agreement ahead of a potential contract award. b) There is commitment (evidence directly from each offtaker) from all offtakers to reach an agreement. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Signed HoTs for all offtakers | Key supply information including: • Volumes • Durations • Pressures • Quality • Failure to supply notice requirements • Intended hydrogen sale price |  |  |  | 200 | 1
T6.2 |  | Progress of Offtaker Physical Development Please provide evidence for the requirements, feasibility and physical development progress for all offtakers. If this information is not available, provide narrative in Column M with supporting evidence in Column P to justify how the remaining design work can be completed to allow COD within the HAR2 window. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Design study showing technical feasibility and physical design requirements (including supply arrangements) for all offtakers, and evidence of physical development progress in line with project schedule. | • Feasibility/design summaries • Evidence of procurement progress • Evidence of securing necessary consents and permits required • Results of any trials or progress made towards demonstrating the feasibility of the site to accept hydrogen |  |  |  | 200 | 1
T7.1 | Electricity Supply | Securing an Electrical Connection Please provide evidence that an electricity connection offer has been made and accepted. Where there are transmission system impacts, this should also include evidence from the TSO confirming project requirements can be met within the HAR2 timeframe. If a connection offer has not been accepted, or provided by the network operator, which provides a firm connection date/timescales, then please provide narrative in Column M with supporting evidence in Column P to detail why securing a connection of sufficient capacity within the HAR2 window is considered low risk to achieving COD by the end of the HAR2 delivery window. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Evidence of a connection offer AND acceptance or evidence of an existing connection, where relevant. Where there are transmission system impacts, evidence from the TSO confirming project requirements can be met within the HAR2 timeframe. | • Demonstration of sufficient capacity to meet project needs • Formal offer from DNO • Evidence of signature/acceptance and payment • Evidence demonstrating timelines, capacity, and nature of connection (i.e. firm/non-firm etc) • Where required, evidence from the TSO confirming project requirements can be met within the HAR2 timeframe |  |  |  | 200 | 1
T7.2 |  | Securing Electrical Power Supply Agreements Please provide evidence that a PPA quote or equivalent for all electricity volumes required for the project has been secured. If providing a PPA quotation is not possible then please provide narrative in Column M with supporting evidence in Column P to detail why securing a PPA is considered low risk with respect to delivering the project within the HAR2 window. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Where required, a PPA quotation for the full electrical demand required. | • Specific generation assets listed that are linked to the project’s temporal requirements, where these are new assets please answer T7.3 • Indicative pricing • Anticipated contract length |  |  |  | 200 | 1
T7.3 |  | Progress and Plan for Development of New Generation Assets Where new build generation assets are required to meet the project's electricity supply needs (either behind-the-meter, or via grid PPA), please evidence development progress and justify that the assets will be operational by the hydrogen production facility's intended COD. If this information is not available, provide narrative in Column M with supporting evidence in Column P to justify how the development of new generation assets, within timeframes required to meet the stated COD, is considered low risk. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Where required, evidence of development of new generation asset/s | For the new generation assets: • Project schedule • Design documents • Land permissions • Planning approval & consents • Equipment supply arrangements |  |  |  | 200 | 1
T8.1 | Water Supply | Securing Water Supply Arrangements Please provide evidence that there is a sufficient water capacity on the site to supply the production facility. If the minimum evidence cannot be provided, provide narrative in Column M with supporting evidence in Column P to justify how the evidence provided demonstrates that all water supply requirements are well understood and being managed and that securing a water supply (technical, physical and commercial, statutory) is low risk to deliverability. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Evidence of requirements and supply agreement(s)/budgetary quote from the water supplier. | ● Evidence of Water System Design basis (if separate to overall BoD) including: • Electrolyser Feedstock Water, required rates and quality specification. • Raw Water, required rates and quality specification. ● Connection offer and/or development agreement from the water company, confirming there is capacity to supply the hydrogen production facility for the duration of the project. ● If not using a water supplier please provide: • HoTs with landowner detailing permission to bring utilities onto site • Extraction licence from the Environmental Agency • Borehole feasibility study If the supply is through a third party e.g. offtaker, direct evidence of capacity and intent to reach an agreement needs to be provided directly from the third party. |  |  |  | 200 | 1
T9.1 | Waste material arrangements | Waste Material Arrangements Please provide evidence that arrangements for managing waste on site are in hand. If providing a formal offer (evidencing capacity to receive waste) from the relevant body has not been possible, provide narrative in Column M with supporting evidence in Column P to justify how the evidence provided demonstrates that all waste management requirements are well understood and being managed and that securing a waste management arrangement (technical, physical, commercial and statutory) is low risk to deliverability. (Note, if the minimum evidence listed in Column I has been provided, there is no need to provide a narrative for this question) | Evidence of waste management agreements and licenses with the appropriate supplier/s. | • Development agreement from the waste company, confirming there is capacity to handle the hydrogen production facilities waste • HoTs with landowner detailing permission to manage waste on site • Discharge licence from the Environmental Agency If the supply is through a third party e.g. offtaker, direct evidence of capacity and intent to reach an agreement needs to be provided directly from the third party |  |  |  | 200 | 1

## Financial and Commercial
Request for Information Questions: Financial and Commercial
RFI ID | Assessment criteria | Question | Evidence, where applicable | Applicant Response | Word limit | Supporting Evidence References
F1.1 | Organisational structure company level | Please provide any updates and additional details to the response submitted in the Project Application Form in respect of the group structure, including a chart which positions the Project vehicle within any wider company structure highlighting the following information for each entity within the structure: 1. Full company name and number, where available; 2. Primary activity and location; 3. Responsibilities in relation to the Project: i. Project Company: The company or companies that will own / operate the Project: ii. Project Sponsor: The company or companies financing the Project; iii. Applicant Company: The company or companies that has applied for support and will be taken through to the next stage beyond due diligence if successful; and iv. the entity where key investment decisions will be taken. 4. Ownership (including details of any stock market listings); and 5. If a new legal entity is to be created for the purpose of this Project, where in the company/group structure this will sit and the expected timing of its incorporation. (where possible please provide evidence of incorporation e.g. Companies House number / extract from Companies House Website) Please provide details of the ultimate beneficial owner of the corporate group, as well as the details of any shareholder (or group of related shareholders) owning more than 5% of the group’s equity capital. | New or updated evidence could include the following updated documentation: • Organisational Structure (including details specified above) • New Entity creation agreements / details • Company Capability Statement • Internal Governance and Approvals Process |  | 400
| Organisational structure project level | In this section, please provide any updates to the response submitted in the Project Application Form in respect of the: | N/A | Please put n/a in the response boxes below if there is no material update to the evidence and response submitted at the Application Stage for RFI ID 2.1-2.4
F2.1 |  | Relevant organisational and Project delivery skills and competencies within the organisation that are essential for delivering the Project (specific employees and where developer side professional services will be appointed to bolster delivery skills and competencies). | Evidence could include the following updated documentation: • CVs for key personnel • Project Capability Statement (Project case studies) |  | 150 (excluding evidence)
F2.2 |  | The Project organisational structure that will build, own, and operate the hydrogen production facility; and | Evidence could include the following updated documentation: • Project organogram |  | N/A
F2.3 |  | Relevant previous delivery experience and track record (including developer side professional services, if applicable); | Evidence could include the following updated documentation: • Project Capability Statement (Project case studies) |  | 150 (excluding evidence)
F2.4 |  | Additionally, where not previously provided as part of your response submitted in the Project Application Form, please provide a description of how the delivery of the Project will be managed (including Project setup and governance arrangements). | N/A |  | 150
F3.1 | Financial health - company level | Please complete the 'Financial Statement Form' in line with the instructions included in the template, and provide supporting copies of the latest three sets of audited accounts, any accompanying reports, management accounts covering the remainder of the current financial year for: 1. Project Company: The company or companies that will own / operate the Project; 2. Project Sponsor: The company or companies financing the Project; and 3. Applicant Company: The company or companies that has applied for support and will be taken through to the next stage beyond due diligence if successful. These companies should clearly map to the company structure chart submitted in response to F1.1 (above). It is acknowledged that the above company / companies may not all be separate entities. Please confirm that accounts for the above entities have not received a qualified audit report in any of the previous three years. Highlight any areas of material uncertainty raised by auditors in this period. If the accounts have not been audited please also state this. | Evidence should include the following documentation: • Statutory financial statements • Management accounts • Completed version of the Financial Statement Form |  | N/A - Please fill out the template as specified
F3.2 |  | Please confirm if the corporate group currently has any financial obligation to HMG and provide details where applicable? e.g. a Government Loan, a Government Grant Repayment, a Penalty or Fines. Where relevant, please detail the department the obligations are owed to and the amount payable. | Obligations and amount payable |  | 250
F4.1 | Funding plan - project level | Please describe the proposed financing arrangements for progressing the Project. Your response should distinguish between different stages of the Project and explain what is needed to achieve a final investment decision. In the event of multiple entities in a project, we would expect to see a single overarching financing plan and for it to be clear how each entity fits into that. To support your response, please provide a finance plan in a timeline format (e.g. Gantt) detailing the financing activities that need to take place to achieve a final investment decision, to evidence the proposed sources of funds for the Project along with the current status and proposed timings for receiving those funds, in order to demonstrate that the Project will be fully funded. This timeline should: 1. Be a clear and detailed timeline to FID setting out key financing activities and commentary on how management propose to execute each activity; 2. Clearly link to the funding tabs in the Financial Statement Form showing the nature and breakdown of each of the proposed sources of funding to show that the Project will be fully funded; 3. Include dependencies, key risks and mitigations for the financing process / each activity; 4. Detail the assumptions underpinning the financing plan including key metrics or ratios (e.g. gearing ratios at each stage); and 5. Cross-refer to evidence of funding arrangements where relevant. Responses to the other questions in the 'Financing Plan' section should cross refer to the timeline provided. | A financing plan including the following: •Timeline to FID (Gantt Chart format) •Funding structure break down • Key risks, dependencies, risks & mitigations •List of funding plan assumptions |  | 500
F4.2 |  | Where relevant, please detail the nature of any internal sources of funding being deployed (funding from within the group structure). Please include the following in your response; 1. The nature of the arrangements (including the company or companies involved in providing finance for the Project and the amount required); 2. The amount and sources of the funds, split between equity and debt, which should map to clearly link to the funding tabs in the FInancial Statement Form; and 3. A letter of support from the relevant party to evidence that the intragroup funding is being allocated to the Project documents and evidence of the nature of the arrangements where they exist (e.g. key terms of the shareholder loan facilities etc.) | A letter of support for intragroup funding and evidence of the nature of the arrangements where they exist (e.g. key terms of the shareholder loan facilities etc.) including: •The nature of the arrangements •Amount, source & split of funds •Letter of support to evidence intragroup funding |  | 300 (excluding evidence)
F4.3 |  | Where additional debt will be raised to fund the Project, please detail the nature of the proposed funding arrangement, including; 1. Type (e.g. Project Finance) and amount of debt finance anticipated; 2. Whether the debt is project level, company level or group level debt, 3. The status of securing the debt, with evidence to support this. This evidence might include: i. Key terms of the debt and evidence of an agreement if the debt arrangements already exist (heads of terms); ii. Letters of support / intent from debt providers to evidence commitment for the funding of the Project; and, or iii. Latest communications with debt providers where organising arrangements is ongoing. 4. Key remaining activities and timescale needed to secure the debt financing with reference to the timeline provided in F4.1. | Third party evidence to support the status of securing debt and the key terms, including: •Type & amount of debt finance •Debt level •Status of arrangements (letters of support, latest communications) |  | 300 (excluding evidence)
F4.4 |  | If new capital needs to be raised in the form of equity in the applicant entity or in a wider group company to fund the Project, please detail the nature of the proposed funding arrangement including; 1. Type and amount of equity finance anticipated; 2. The nature of investor groups that have or will be targeted (i.e. strategic or financial investors etc.), with names of potential investors where possible; 3. The level of market engagement that has taken place, with evidence where possible. This might include: i. Letters of support / intent from investors to evidence commitment for the funding of the Project; and, or ii. Feedback received to date from potential investors. 4. Key activities that need to take place to finalise the equity raise process with reference to the timeline provided in F4.1. | Third party evidence to support the status of raising equity and the key terms, including: •Type & amount of equity finance •Nature of investor groups •Evidence of market engagement (Letters of support, feedback received to date) |  | 300 (excluding evidence)
F4.5 |  | Please explain why you are unable to raise further funding from the sources identified and therefore why HPBM subsidy is required in order to make the Project viable. This would typically include reference to your standard investment appraisal methodology (e.g. internal rate of return, net present value, payback period). | Investment appraisal methodology |  | 300 (excluding evidence)

## Additional questions
Request for Information Questions: Additional questions
RFI ID | Question | Applicant Response | Proposed word count | Supporting Evidence References
A1.1 | Diversity and Inclusion: Please detail how you have considered how you can ensure diversity and inclusivity of your workforce, and if diversity and inclusivity will form part of your hiring practices and in what way. Please detail how your supply chain have considered how they can ensure diversity and inclusivity of their workforce, and if diversity and inclusivity will form part of their hiring practices and in what way. |  | 300
A1.2 | Long-term plans for scale-up: Please summarise any long-term plans to scale up hydrogen production beyond the initial capacity and provide an update on any material changes to these plans since your application. |  | 250
A1.3 | Offtake: Have your offtaker(s) considered any other decarbonisation routes and what is their rationale for using hydrogen? |  | 100 words per offtaker
A1.4 | Offtake: Where offtaker(s) are switching existing operations to use hydrogen, please detail the key process equipment that will be required, and whether the offtaker intends to have access to a back-up fuel supply (e..g, through storage or maintaining the ability to switch back to its incumbent fuel) (up to 100 words per offtaker) |  | 100 words per offtaker
A1.5 | Offtake: Based on current thinking, will your offtaker(s) be scaling up demand for hydrogen in the future, beyond what is currently proposed? If so, please describe: a) the extent of demand increase (e.g., will the offtaker switch to 100% hyodrogen)? b) how this additional demand will be met, including any further storage or transport infrastructure requirements. c) how security of fuel supply will be maintained (e.g., through storage or maintaining a gas connection). |  | 100 words per offtaker
A1.6 | Offtake: Where the proposed use of hydrogen is as a chemical feedstock (e.g. to produce ammonia, methanol, sustainable aviation fuel), where is the intended market and how will the hydrogen derivative or product be used? |  | 200

## Evidence Register
Evidence Register
RFI Question ID | Document Title | File name | File format | Part of Required Evidence (Y/N) | Justification | Confidential and Commercially Sensitive - FOI exempt (Confidential/Public)
e.g T.1 | Project Unicorn Front End Engineering Design Report | FEED Study January 23 V2 Approved | pdf | Y/N | Necessary to evidence xyz | Confidential/Public