## External Plan Format
NRS Ltd Procurement Plan as at end of March 2025
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded
C16013 | Decommissioning | Hinkley | Hinkley R1 & R2 Pipe Bridges | Decommissioning, Demolition & Deplant | rachel.thompson@nrservices.uk | Direct Award F/W | £1m to £5m | n/a | 2024-06-04 | (a) | 2025-02-09 | (a) | NSG Environmental Ltd
C21790 | Decommissioning | Oldbury | Oldbury - Demolition of Redundant Timber Buildings | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2024-12-01 | (a) | 2025-04-10 | (f) | Tend: Erith Contractors Ltd,Turnbull Infrastructure & Utilities Ltd,Central Roofing and Building Services Ltd,AJ Rail & Civil Engineering LTD,O B R Construction,Wring Group Ltd,Pennys Group Limited,N&R Demolitions and Industrial Dismantlers Limited,L A MOORE LIMITED,SMITH'S (GLOUCESTER) LIMITED,Bath Demolition Ltd
C24066 | Decommissioning | Hinkley | Hinkley Pipe Bridge Removal (Phase 2) | Decommissioning, Demolition & Deplant | rachel.thompson@nrservices.uk | Direct Award F/W | £1m to £5m | n/a | 2025-09-07 | (f) | 2026-03-06 | (f) | Not yet confirmed
C5672 | Decommissioning | Sizewell | Install Modify Vent - Splitter Vane Store (SVS) | Construction | sarah.j.deeble@nrservices.uk | Non-FTS Competition | <£100K | 2026-02-01 | 2026-04-05 | (f) | 2026-06-04 | (f) | Not yet confirmed
C5678 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@nrservices.uk | Mini Competition F/W | £1m to £5m | n/a | 2026-08-13 | (f) | 2027-02-09 | (f) | Not yet confirmed
C5690 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | fiona.pearse@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-10-08 | (a) | 2025-08-08 | (f) | Not yet confirmed
C5693 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | FTS Open | <£100K | n/a | 2025-10-07 | (f) | 2026-02-04 | (f) | Not yet confirmed
C5706 | Decommissioning | Trawsfynydd | Ponds Complex Demolition - Execution | Decommissioning, Demolition & Deplant | Shelley.Lawrence@nrservices.uk | FTS Comp Proc with Negotiation | £5m to £10m | n/a | 2025-05-10 | (f) | 2026-09-12 | (f) | Not yet confirmed
C5737 | Decommissioning | Trawsfynydd | Traws Reactor Retrievals - Scheme Design 5 - Building Modifications | Design services/support | claire.scott@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2024-09-02 | (a) | 2025-03-11 | (a) | AtkinsRealis
C8911 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Divers | Engineering | Shelley.Lawrence@nrservices.uk | FTS Open | £1m to £5m | n/a | 2026-03-06 | (f) | 2026-09-12 | (f) | Not yet confirmed
C8950 | Decommissioning | Dungeness | Package 1 Demolition, Boiler & ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2023-02-07 | 2025-02-01 | (a) | 2026-09-12 | (f) | Not yet confirmed
C9092 | Decommissioning | Oldbury | Oldbury Turbine Hall Demolition | Decommissioning, Demolition & Deplant | danielle.staples@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2025-12-06 | (f) | 2026-12-11 | (f) | Not yet confirmed
C9924 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | paul.phillips@nrservices.uk | PA23 Open | £1m to £5m | n/a | 2025-06-09 | (f) | 2025-11-06 | (f) | Tend: TBC
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health (excl D&A Testing) 26+ | Support Services | Amy.Vale@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-05-10 | (f) | 2025-12-06 | (f) | Not yet confirmed
C13038 | Ops & Enablers | Enablers/Not Location Specific | Drawing Management System - 2026 | IT hardware/software | jayne.chalmers@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-09-07 | (f) | 2026-03-06 | (f) | Not yet confirmed
C13774 | Ops & Enablers | Enablers/Not Location Specific | Fleet Management and provision of Lease Cars 2025-29 | Support Services | holly.griffith@nrservices.uk | CCS F/W Call off | £5m to £10m | n/a | 2024-10-02 | (a) | 2025-05-10 | (f) | Tend: Fleet Solutions c/o Northumbria NHS Foundation Trust,Northumbria Healthcare NHS Foundation Trust t/a NHS Fleet Solutions,GMP Drivercare Limited,Wessex Fleet Solutions Limited,Fraikin Limited,Fleetcare (Public Sector Car Scheme Management) Limited,Knowles Fleet,Adept Vehicle Management,NTW Solutions Limited,Rivus Group
C16731 | Ops & Enablers | Enablers/Not Location Specific | Consolidated Testing Services - 2025 | Manpower | jayne.chalmers@nrservices.uk | CCS F/W Call off | £5m to £10m | n/a | 2025-05-10 | (f) | 2025-05-10 | (f) | Not yet confirmed
C17087 | Ops & Enablers | Enablers/Not Location Specific | Supply of Metrology Instruments (Installed and Portable) | Engineering | caroline.j.milner@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification
C17366 | Ops & Enablers | Enablers/Not Location Specific | Office Supplies 2025 onwards | Support Services | Amy.Vale@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2024-06-04 | (a) | 2025-03-11 | (a) | ACS Group
C17387 | Ops & Enablers | Bradwell; Dungeness; Sizewell | Civils Support DPS - South East Region | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C17423 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - System | IT hardware/software | james.hiller@nrservices.uk | PA23 Competitive Flexible | £10m to £25m | n/a | 2025-07-09 | (f) | 2026-03-06 | (f) | Not yet confirmed
C17426 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - Data Management | Manpower | james.hiller@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2025-12-06 | (f) | 2026-09-12 | (f) | Not yet confirmed
C19724 | Ops & Enablers | Enablers/Not Location Specific | Asbestos Analytical Services 2025 | Design services/support | matt.p.eeley@nrservices.uk | DPS Call-Off | £25m to £50m | n/a | 2025-06-09 | (f) | 2026-03-06 | (f) | Not yet confirmed
C19793 | Ops & Enablers | Chapelcross; Hunterston | Civils Support DPS (Scottish Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20508 | Ops & Enablers | Berkeley; Hinkley; Oldbury | Civils Support DPS (South West Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20831 | Ops & Enablers | Maentwrog; Trawsfynydd; Wylfa | Civils Support DPS (Welsh Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C21710 | Ops & Enablers | Enablers/Not Location Specific | Access & Insulation Services 2025-2029 | Construction | michelle.newcombe@nrservices.uk | FTS Restricted | £50m to £100m | 2024-10-17 | 2025-01-10 | (a) | 2025-09-07 | (f) | Not yet confirmed
C21822 | Ops & Enablers | Harwell; Winfrith | Civils Support DPS - South Region - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £1m to £5m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C24227 | Ops & Enablers | Enablers/Not Location Specific | Pension Trustee Services | Manpower | alwena.owen@nrservices.uk | PA23 Competitive Flexible | £500k to £1m | n/a | 2025-09-07 | (f) | 2026-06-04 | (f) | Not yet confirmed
C5824 | Ops & Enablers | Enablers/Not Location Specific | Statutory Examination Services 2026+ | Design services/support | caroline.j.milner@nrservices.uk | FTS Open | £5m to £10m | n/a | 2025-09-07 | (f) | 2026-07-14 | (f) | Not yet confirmed
C22477 | Ops & Enablers | Enablers/Not Location Specific | IT Hardware Refresh 2025-26 | IT hardware/software | debbie.collin@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-03-11 | (a) | 2025-03-11 | (a) | Insight Direct (UK) Ltd
C24235 | Ops & Enablers | Berkeley; Bradwell; Chapelcross; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Sizewell; Trawsfynydd; Winfrith; Wylfa | Category 2 - Health Physics Monitoring Resource | Design services/support | sukyee.hermon@nrservices.uk | DPS Call-Off | £25m to £50m | n/a | 2026-04-05 | (f) | 2027-05-10 | (f) | Not yet confirmed
C24237 | Ops & Enablers | Berkeley; Bradwell; Carlisle; Chapelcross; Crewe; Dounreay; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Preston; Sizewell; Trawsfynydd; Winfrith; Wylfa | Security Personnel Services 2027 | Support Services | steven.j.lock@nrservices.uk | CCS F/W Call off | £50m to £100m | n/a | 2026-03-06 | (f) | 2027-01-10 | (f) | Not yet confirmed
C24410 | Ops & Enablers | Enablers/Not Location Specific | 2025/26 - Legal advice to trustees | Support Services | alwena.owen@nrservices.uk | Direct Award - Below Threshold | £100k to £500k | n/a | 2025-05-10 | (f) | 2025-05-10 | (f) | Not yet confirmed
C24524 | Ops & Enablers | Enablers/Not Location Specific | Indeed direct award | Support Services | alwena.owen@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-03-11 | (a) | 2025-05-10 | (f) | Not yet confirmed
C25013 | Ops & Enablers | Enablers/Not Location Specific | Legal Advice Services July 25 - Nov 27 | Support Services | gissela.m.hughes@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-06-09 | (f) | 2025-08-08 | (f) | Not yet confirmed
C17610 | Waste | Hinkley | Hinkley - Design, supply and installation of 415V Switchboard | Consumables | karen.maguire@nrservices.uk | Non-FTS Competition | £500k to £1m | n/a | 2025-06-09 | (f) | 2025-12-06 | (f) | Not yet confirmed
C20416 | Waste | Enablers/Not Location Specific | Characterisation Services | Design services/support | Liz.Gilbert@nrservices.uk | New Framework set up | £10m to £25m | 2025-02-22 | 2025-05-10 | (f) | 2025-07-09 | (f) | Not yet confirmed
C21538 | Waste | Oldbury | Oldbury - Detailed Design & Construction of AVDS Building | Construction | danielle.staples@nrservices.uk | Non-FTS Competition | £1m to £5m | n/a | 2026-04-05 | (f) | 2026-10-12 | (f) | Not yet confirmed
C23009 | Waste | Oldbury | Supply and installation of 1MVA transformer | Construction | karen.maguire@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-07-14 | (f) | 2026-07-14 | (f) | Not yet confirmed
C23141 | Waste | Oldbury | Oldbury - Waste Facility (AVDS) Mechanical & Electrical fit out | Construction | karen.maguire@nrservices.uk | Non-FTS Competition | £500k to £1m | n/a | 2026-08-13 | (f) | 2027-02-09 | (f) | Not yet confirmed
C23142 | Waste | Dungeness | Overhead Gantry Cranes (Wet Waste Transfer Facility) | Engineering | karen.maguire@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2024-12-01 | (a) | 2025-04-10 | (f) | Tend: Penny Hydraulics Ltd,SCX Special Projects Ltd,Mona Lifting Ltd,Swann Engineering Group Ltd.,CORE Nuclear Solutions Ltd,RHC Lifting Limited,Wellman Booth a trading division of The Clarke Chapman Group,Osprey Shipping Limited
C23538 | Waste | Dungeness | DCIC Lifting Assembly | Consumables | louise.x.brown@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-01-10 | (a) | 2025-03-11 | (a) | Tend: CeeVee Engineering Ltd,Penny Hydraulics Ltd,N-ERGISE Ltd.,Norris Engineering Designs
C23875 | Waste | Chapelcross | Manufacture of Stainless Steel 500L Drums, Stillages & Sleeves | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-02-09 | (a) | 2025-05-10 | (f) | Tend: More than 10
C24146 | Waste | Berkeley | 2 Forklifts 5 year hire for Berkeley site | Support Services | julie.a.jones@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-05-10 | (f) | 2025-06-09 | (f) | Not yet confirmed
C5763 | Waste | Hinkley | Package 03 - SPF9f Waste Characterisation | Waste management, disposal & storage | danielle.staples@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-12-06 | (f) | 2026-04-05 | (f) | Not yet confirmed
C24391 | Waste | Chapelcross | Special Waste Management – Provisions of Containers, Carriage and Disposal of No | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | Direct Award - Below Threshold | £100k to £500k | n/a | 2025-05-10 | (f) | 2025-09-07 | (f) | Not yet confirmed