Programme Completion Review

Title: Brazil Prosperity Fund / “UK-Brazil Prosperity Partnership – poverty reduction and productivity gains”
Final Programme Spend £32.80 million	Review Date: August 2023
Programme Code: N/A	Start Date: April 2018	End Date: March 2023

Summary of Programme Performance

Year	2019	2020	2021	2022	2023
Programme Score	B	A-	N/A	N/A	A
Residual Risk Exposure Rating	Moderate	Moderate	N/A	N/A	Moderate

## A. Summary and Overview

Introduction and Context

The Brazil Prosperity Fund (“UK-Brazil Prosperity Partnership – Poverty Reduction and Productivity Gains”) was a multi-year bilateral programme funded by the UK Government in Brazil. The programme aimed at supporting Brazil to increase productivity for renewed and inclusive economic growth, needed for poverty reduction to make development sustainable, in line with the International Development Act (2002), the Gender Equality Act (2014) and the Sustainable Development Goals (SDGs).

The programme operated from April 2018 until March 2023 and was originally conceived to intervene in four principal areas, which demonstrated the most efficient allocation of resources: Energy, Green Finance, Future Cities and Trade. Over the course of its implementation, the programme was required to go through a number of adaptations, including to key political changes in both countries, but mainly due to the unprecedented circumstances of the COVID-19 pandemic and the resulting decisions to reprioritise UK Official Development Assistance (ODA) across the world and close the entirety of the Prosperity Fund globally. As a result of such changes, the programme’s initial scope was mostly reduced or restructured.

At the same time, the Brazil Prosperity Fund Board, also took the decision to allocate part of the programme’s exit allocation to support responsible closure of two global Prosperity Fund programmes that were operating in Brazil at the time – the Better Health Programme and the Brazil Intellectual Property Programme (initially conceived under the legacy Global Trade Programme). Both programmes represented key priority areas of work for the UK in Brazil, and both were able to deliver successful results using their own programme resources with minimum financial support from the Brazil Prosperity Fund – 5% of its final allocation. The performance of the Brazil Better Health Programme and the Brazil Intellectual Property Programme, hereinafter, will not be subject to this particular review. Both of them will be analysed and evaluated under their own global PCRs. Even so, the team responsible for this review decided to include some of their key achievements on Annex A of this report.

Finally, this Programme Completion Review reflects that the Prosperity Fund in Brazil has had limited time to deliver planned results, as well as reflecting the progress and achievements that have been possible. Where objectives have not been completed this does not necessarily reflect on the quality of programme design or delivery. The UK will remain a world leader in development, not just through the impact of our ODA spend but also through our business, trade, civil society, research and technology expertise.

Major Programme Achievements

Given the diversity of interventions and the range of achievements of the programme, we have included a full list of highlight achievements in Annex A. These include:

  1. Supporting the establishment of the first Regulatory Framework for offshore wind energy in Brazil – eventually contributing for the removal of a key market access barrier for British businesses, worth around £55mi according to the Department of Business and Trade, besides contributing to UK Net-Zero objectives.
  2. Catalysing the regulation of biomethane across all twenty-seven states of the country.
  3. The design, development, testing and transfer of the first digital marketplace for trade-related services in Latin America (BRAEXP – Plataforma Brasil Exportação) covering the whole supply chain of export and import service, benefiting Brazil’s MSMEs and promoting equitable access to international markets.
  4. Realisation of trade policies relating to Brazil’s alignment to OECD standards, most notably the reform of the Brazilian transfer pricing system which was one of the largest and most important projects of the programme. After over five years of work, the Brazilian Congress approved the new Transfer Pricing law in May/2023, aligning Brazil’s new system with the OECD standards.
  5. A digital platform to increase port efficiency – the PCS (Ports Community System). The PCS integrates all existing systems that public and private stakeholders use to manage the running of the ports based on new, streamlined port processes.
  6. Supporting Brazilian development banks BNDES and BDMG to set up Paris-aligned targets so they could contribute to efforts to limit global warming.
  7. Promoting integrated and sustainable transport systems in the city of São Paulo and reduced water lost by leakages in Recife Metropolitan Region, improving the quality of life for the poorest, reducing negative impacts on Brazil’s economic development, and combatting climate change.
  8. Trialling of a new model of Telemedicine that benefited 200,000 patients with primary healthcare in remote communities in trial stage alone and is being continued in practice by Hospital das Clínicas in Sao Paulo.

Major lessons learned, evidence generated and recommendations.

There are opportunities for the UK Government to play a political role in the long-term sustainability of the legacy left by the programme. In certain areas, such as Trade, Energy and Health, actions are more pressing and necessary. Such political actions do not require additional budget and might be crucial to guarantee ultimate impact and best value for money from the programme. In the short-term (up to one year), these actions should not take more than a few hours per month and may be sustained in some cases by small to medium investment from non-ODA funding where appropriate.

Despite of the programme’s overall success, the implementation of some recommendations depends on the political will of the local Brazilian government and strong leadership to ensure an adequate budget is earmarked to proceed. Consequently, during the preparation of future programmes, it is crucial that expectations be aligned between all parties at the outset, including technical and political staff, as well as implementing teams.

Digital transformation was key across nearly all programmes – especially for the trade and health initiatives. As implementation progressed, it became clear to stakeholders that there was an opportunity for them to use the programme as an accelerator of digital transformation. This strengthened the case for an ongoing flagship Digital Access Programme (DAP) here at post that seeks to strengthen key aspects of digital security and transformation in Brazil, as an essential enabler for Development across the board.

Moreover, even though an ample budget was available for the programme’s delivery, the reduced time frame and severely reduced budget in the final 2 years meant interventions that could have generated direct impacts on sustainable growth and poverty reduction could not be fully implemented. The resulting impact on relevant stakeholder and government relationships was considerable and should be recorded for future reference when assessing the impact of funding cuts on wider political equities, notwithstanding the challenging financial domestic context throughout the years of the programme that brought about the funding cuts initially.

How this report was conducted

This review was conducted in-house by the acting Heads of Development and the Programmes Officer at post. External reviews were found unfeasible due to timeframe and conflicting schedules of the staff initially involved. Considering all of the programme’s annual reviews and readiness reviews were conducted with external support, a new external review was also not a requirement. Parts of text in this document were taken from the Programme Completion Reports delivered by the implementing partners at the end of each programme strand. In cases where former programme leads were still HMG officers in Brazil, those were asked to support the analysis. Minister Counsellor for Trade & Prosperity reviewed this report and Deputy Head of Mission signed off the definitive version, as the programme’s Senior Responsible Owner.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£56.45 million	£32.80 million
Timeframe	April 2018 – March 2023	April 2018 – March 2023[1]
Outcomes	Better greener’ infrastructure in Brazil, supporting Brazil’s transition to low carbon economy. / Increased trade flows to and from Brazil leading to job creation, investment opportunities and equitable economic growth. / Increased innovation and technological solutions in Brazil increasing productivity and market performance. / Increased opportunities for international businesses in Brazil and increased market share for UK	Despite of the budget cuts and reduced timeframe, and although indicators are hard to assess at this point, the programme was able to achieve results at all outcome levels, e.g.: / Contributing to design the new Offshore Wind legislation in Brazil, which was approved by the Brazilian Lower House later in November 2023 and will eventually secure the removal of a key market access barrier for British businesses. / Providing tools and capacity to Brazil’s main development banks to set up Paris aligned targets, so they can contribute to efforts to limit global warming, besides enabling them to footprint their financed emissions, and to aim for decarbonization trajectories. / Reforming Brazil’s Transfer Pricing system, which will contribute to improve the business environment in Brazil and preventing double taxation. / Developing the first digital marketplace for exporting services in Latin America, with potential to generate up to 600,000 new jobs by 2040.
[1] Only the Trade Programme was authorized to continue until March 2023 at a very reduce scope. The Future Cities Programme was closed on December 2021 and both the Green Finance and Energy Programmes were closed in March 2022.

Overall assessment of programme outcomes, sustainability and VfM

As detailed below in the individual project analyses, the majority of interventions were successful in achieving their ambitions in the first two years of the programme prior to the budget reduction. These programmes realised real material gains for Brazil’s economic system, especially those that concentrated on transformation at the administrative level. There were also examples of programmes such as the Brazil Green Finance Programme that were taken forward into new funding streams such as the International Climate Finance programme UK PACT, and therefore managed to make an impact on Brazil’s economic transition as envisaged in the original Business Case.

Despite this, there were two notable challenges to the integrity of the Theory of Change (ToC) that make it difficult to measure the wider impact of the programme against its original intentions. The first was the substantial cut in funding that the programme experienced in 2021 in accordance with the global closure of the Prosperity Fund. This prevented the programme making the wholistic impact envisaged in Outcomes and Impact section of the ToC, as programmes could not be concluded at the scale originally envisaged. These cuts came with a severe reduction in staff on the Brazil Prosperity Fund Team, including several posts that covered or would cover cross-cutting impact (such as Secondary Benefits, Gender and Inclusion and Monitoring & Evaluation), making wide-ranging analysis of the programme’s achievements at Outcome and Impact level unfeasible. The original team had thirteen full-time employees (FTEs) exclusively dedicated to this programme. By March 2022, when most programme streams were being closed, the team had been reduced to 5 FTEs. By the end of programme, in March 2023, there was only one officer working exclusively on this programme at post, with part-time support from the Head of Development.

The second was the COVID-19 pandemic, which prevented several strands of implementation from taking place on several programmes from March 2020 for as much as 18 months thereafter. This was most impactful where partners were implementing directly with beneficiaries at ‘field level,’ such as specific strands of the Brazil Energy Programme and the Future Cities Programme, as opposed to those projects that sought to achieve more administrative transformation, such as the Trade and Green Finance Programmes.

The overall score of A reflects a picture of good programme management and implementation on the part of our partners and team at post, demonstrating resilience and adaptability amidst budget cuts experienced half-way through its lifetime. Besides that, despite of such challenges, the programme remained aligned to the International Development Act (2002) and the Gender Equality Act (2014). It is possible to note that the successful delivery of outputs will, in turn, contribute to the overall impact of the Programme in Brazil in the mid to long-term.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The Programme’s Theory of Change can be found in the diagram below (Graph 1). The Theory of Change was not amended substantially throughout the life of the programme. The majority of projects performed well as far as they contributed to the Input and Output sections of the Theory of Change, described in the individual programme analyses below. Whilst the political context changed substantively at Federal level (and in many cases, to the opposite effect at Congressional and State level), these changes coincided with only very minimal spend taking place as they did in the final 6 months of the programme where less than £1 million spend was outstanding.

It should be noted that the overall Impact and Outcomes still represent many aspects of UK programme activity and policy ambition in Brazil, albeit now via other funding vehicles. Many of the aims of the ToC are also encapsulated in the new Green and Inclusive Growth partnership signed between the UK and Brazil in May 2023. The achievements of the Trade Facilitation Programme on supporting Brazil’s alignment with OECD standards are now being funded via Non-ODA International Programme Fund grants by FCDO and are being actively managed by Network staff.

Graph 1 – Theory of Change of the Brazil Prosperity Fund Programme

## C: Detailed Output Assessment

BRAZIL ENERGY PROGRAMME

Output Number and Title	1.2 Research-based white papers and legal and regulatory instruments (law amendments, decrees, acts) developed for strengthening the regulatory framework on waste-to-energy based on best practices and approaches for optimal impacts in terms of poverty reduction. / 3.1 Evidence-based strategies to promote innovations in the energy sector with a focus on alternatives for low-carbon hydrogen development and greater access to RD&D investment data. / 5.1 Evidence-based research and advocacy for regulatory reforms that can enable growth in OSW and maximize its economic and social impacts.
Output Score	1.2: A+ / 3.1: A+ / 5.1: A++
Impact weighting (%)	Output 1.2: 4% / Output 3.1: 13% / Output 5.1: 8%	Impact weighting revised since last AR?		Yes, impact weightings have been recalculated in this review to proportionally sum 25% in each of the four programme strands.

Output Indicator			Starting Target		Final Logframe Target	Final Result Achieved
White papers on offshore wind			2		2	4
Number of evidence-based studies addressing strategies to support the development of the low-carbon Hydrogen industry in Brazil			2		2	4
Number of white papers on regulatory reforms and legal procedures in waste-to-energy provided to federal authorities and/or local governments			2		2	5

OUTPUT 1.2

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Biogas is not a new sector in Brazil, but it is far from being fully explored. An important part of BEP's work in this sector has been to unveil the limitations and unlock obstacles to the expansion of W2E market.

BEP provided a draft version of state regulation on biomethane (D3 of TO 1.2.1), a tested methodology for quality control of biomethane to support ANP on market regulations with high-quality biomethane at feasible prices, two regulatory instruments (Final proposal for state regulation on biomethane and RIA analysis) and technical recommendations for the ABC+ Plan, which was planned as a strategy paper but was taken by MAPA as a white paper for a new public policy.

Key Achievements

1. Stakeholders at government agencies now have data and arguments to justify programmes, politics and other works related to W2E. Stakeholders from other segments will still benefit from all the knowledge shared as well.
2. Stakeholders from state regulatory agencies are using BEP’s publications for further development of biogas and biomethane. Other institutions and government bodies as well.
3. The Plan ABC is the major program for tackling climate change through the agricultural sector. BEP influenced the decisions and goals of the Animal Waste Management programme in Plan ABC, placing biogas production as a climate friendly alternative. BEP also developed a calculator to assist the monitoring of Plan ABC+. The calculation tool was developed to estimate the volume of residues treated and the GHG emissions reduction based on basic information as the number of animals, treatment type, and use of the biogas. This tool will improve the calculations of Plan ABC+. The information generated in the documents was successfully incorporated into the texts published by MAPA.

Lessons learned through this output, and recommendations for future programming.

1. BEP validated each main step of the work with main stakeholders, building greater confidence in its utilisation develop a reliable and robust methodology for studies, analysis and proposals. This also increased acceptance and buy-in from market actors and increased the uptake of BEP’s proposals for leveraging the biogas sector and making new steps towards sequential activities.
2. Since biogas and biomethane are not yet widely acknowledged, activities on advocacy must invest in disclosure about the theme before asking for support and discussing legal framework needs and improvements. It is also important to hear from stakeholders and try to understand their reality and “pains” to build a product that can respond to their business needs.
3. It is important to invest in the tropicalization of methods and technologies so that they become accessible and reliable for energy projects in Brazil. The case of methodologies for quality control of biomethane has proved there are national alternatives at lower costs to international technologies but for them to be effective, it is necessary to be adapted to the local reality.

OUTPUT 3.1

Hydrogen is rapidly emerging as globally important in energy sectors for countries seeking to achieve carbon neutrality. Its value as both an energy carrier fuel and a storage solution offer a route to decarbonisation for industry, transportation as well as electricity and demand for heat. However, its flexibility has created many competing views within Brazil (as with many other countries) on how hydrogen should play a role in the energy mix in the future.

This was the case even after the Brazilian government launched its National Hydrogen Programme: proposed guidelines (Programa Nacional do Hidrogênio: proposta de diretrizes - PNH2) in 2021. On MME’s request BEP partnered with EPE, with research centres at the Universities of Sao Paulo and Campinas and with Instituto Escolhas to produce four reports over October-December 2021: two Technical Notes – on blue and turquoise hydrogen, and two additional technical reports - one on the international hydrogen value and innovation chain (provided by CLT, a member of the BEP consortium) and another on GESI aspects in existing (grey) and future (blue and turquoise) hydrogen value chains in Brazil.

Key Achievements

In early 2022 EPE published the two Technical Notes on Blue and Turquoise Hydrogen on its website. This can be considered adoption by BEP as the paper is now being used by the Government to provide direction for investors looking to invest in hydrogen production capacity in the national territory.

Lessons learned through this output, and recommendations for future programming.

In complex tasks such as the hydrogen work, establishing frequent meetings with the teams in charge of specific activities and keeping one or two coordinators to coordinate more than one team, acting transversally, can be extremely useful to allow the work to progress quickly without loss of work.

The study on blue and turquoise hydrogen international value chains identified valuable findings.

OUTPUT 5.1

Wind power has grown exponentially in Brazil over the last decade. However, this growth has all been through onshore wind developments, while offshore wind has remained entirely untapped, unexplored. For the proper and safe development of the OSW industry in Brazil, a specific legal and regulatory framework design is needed to establish the necessary articulation and compliance with the rules applicable in the different segments of this industry, such as electricity generation, use of shipping space, environmental licensing, port infrastructure and management of transmission lines, among many other considerations. Without such issues being regulated, investment in offshore wind will be severely constrained.

To support OSW BEP started by first analysing the existing environment for the development of the OSW industry in Brazil and then, delivering an inclusive legal and regulatory framework for OSW. In order to identify major challenges, BEP analysed five dimensions of the current Brazilian environment (value chain, ports and transmission lines, infrastructure, contracts, technology and innovation) to better identify requirements to aid the sector’s expansion. International best practices from the UK, Germany and Denmark were considered. GESI issues also received special attention.

Key Achievements

MME made use of BEP’s comprehensive analysis of the environmental and socioeconomic impacts of offshore wind and incorporated BEP’s proposed mitigation risks into its analysis for Congress. MME also adopted BEP’s analysis of the current state of soft and hard infrastructure – e.g., port facilities, electricity transmission systems, contractual structures and investment partnerships – and validated it for regulators to address.

BEP’s gap analysis of the current Brazilian Regulatory framework situation allowed MME to accelerate the uptake of the first regulatory framework for OSW in Brazil, which was launched just before BEP’s closure. This is considered one of BEP’s major achievements.

The OSW sector stakeholders now have at their disposal, data and analysis on the best practices in the OSW industry in a form that can inform decision making and formulation of public policies.

Analyses and recommendations presented in the BEP reports on OSW highlight the connections with existing activities along the coast, considering international best practices, social inclusion, job creation, greater equality, innovation and technological evolution. GESI aspects were embedded in all phases of the work. They are represented in the five OSW products produced by BEP. The investor’s guide contains a Chapter on Energy Diversity, Gender Equality and Social Inclusion. The Guidelines for the development of the offshore wind value chain in Brazil, includes a sub-session on reduction of inequality, social inclusion and gender equality. BEP has also advised investors on the inclusion of local content development in their projects, particularly with regards to women and marginalised people.

The investor's guide is a dynamic and constantly updated document designed as an authoritative reference for entrepreneurs and investors interested in the offshore wind sector.

The endorsement and use of BEP contributions (including GESI recommendations) to the Offshore Wind Regulatory Framework, which has been approved by the Brazilian Chamber of Deputies in November 2023 and is expected to be approved by Brazilian Senate in the first quarter of 2024.

Lessons learned through this output, and recommendations for future programming.

When collaborating with stakeholders who are not fully apprised of the subject, there is little point in explaining the project's intentions or going deeper into explanations without first educating the public on the subject at hand, with more basic and introductory notions. It is worth investing that time.

It is important to understand the expectations of the institutions and people involved in the activities. At the beginning of BEP discussions on OSW, some institutions thought that BEP was selecting a site and not just producing studies in the area to support the development of the sector in the country. In addition, after the finalization of the products, many stakeholders began to ask for the final reports produced, which first needed to be delivered to the MME, the main beneficiary of BEP. It is always necessary to improve communication, whether between the team, or between the Programme and the interested parties, always trying to be as objective and direct as possible, but diplomatically.

BRAZIL GREEN FINANCE PROGRAMME

Output Number and Title	Output 3 - Sustainable finance concepts disseminated to beneficiary, as well as a broader audience. / Output 4 - Financial instruments developed with BDMG and BNDES, including blended finance support to BNDES.
Output Score	Output 3: A+ / Output 4: A+
Impact weighting (%)	Output 3: 9% / Output 4: 16%	Impact weighting revised since last AR?	Yes, impact weightings have been recalculated in this review to proportionally sum 25% in each of the four programme strands.

Output Indicator	Starting Target	Final Logframe Target	Final Results Achieved
Output 3 - Sustainable finance concepts disseminated to beneficiary, as well as a broader audience.	Provide a tailored package of training, mentoring, and technical support to an existing Brazilian Development Bank to establish Brazil’s first Green / Investment Vehicle.	More efficient and effective channelling, of government resources into sustainable infrastructure to leverage private financing for Sustainable Infrastructure Investments.	Created a tool to allow municipalities to assess the technical and economic feasibility of solar systems in public buildings.
			Draft benchmark on sustainable recovery delivered in December 2021, and final in March 2022 together with the Sustainable Recovery Taxonomy.
			Sustainable Finance Dissemination Workshops successfully delivered in February 2022.
			Series of six press releases published covering topics including market assessment, solar panel projects, G&I in the finance sector and best practices in ESG for financial institutions.

Output Indicator	Starting Target	Final Logframe Target	Final Results Achieved
Output 4 - Financial instruments developed with BDMG and BNDES, including blended finance support to BNDES.	Design a market framework for capital market and policy instruments for / Sustainable infrastructure investments	An increased number of well-structured financially sustainable infrastructure projects that support the transition to a low carbon economy while reducing.	Two sustainable finance products designed in BNDES and a blended finance programme. One sustainable tool launched by BDMG.
			G&I action plans developed and being implemented by all partners. Tailored benchmarking reports provided to ABDE, BNDES, Badesul and BDMG, and Itaú.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

OUTPUT 3

The Green Finance programme (BGFP) provided a tailored package of training, mentoring, and technical support to BNDES and BDMG to design and implement an Environmental Social and Governance (ESG) methodology for assessing projects and select capital market tools to support attracting private capital as well testing new ESG methodology against pipeline of projects and investor appetite.

Key Achievements

The programme provided BNDES and BDMG with the tools and capacity to set Paris aligned targets so they can contribute to efforts to limit global warming. And enabled them to footprint their financed emissions, and to aim for decarbonization trajectories.

BNDES fed back that recommendations from ESG Management and Blended Finance workstreams were taken into consideration in organisational changes linked to their P3 project’s efforts. The P3 Project is one of four key projects being developed internally by BNDES. The P3 has the objective of addressing the sustainable agenda at various levels and departments within their institution, permitting the development of related projects and products.

The climate agenda has become more visible within BNDES’ institutional priorities. In 2021, BNDES was supported by BGFP to make climate-related commitments publicly at COP26. And in 2022, one of BNDES’ four key internal projects will have a climate focus. BNDES has also joined CDP in order to access climate-related data, thereby implementing a specific recommendation of the BGFP-developed Roadmap.

The Programme has also supported BDMG in accessing their carbon footprint of their full investment portfolio and financed emissions to support a sustainability strategy to achieve their commitments to the Race to Zero Campaign and Fossil Fuel 0%.

Finally, a last delivery of the BGFP to BDMG was a full assessment of the current situation of sanitary landfills in thirty-one municipalities of the state of Minas Gerais. The idea was to evaluate their current emissions and develop a set of ESG recommendations to support innovative and greener solutions for these landfills, that currently account for a significant part of the state’s overall emissions.

Lessons learned through this output, and recommendations for future programming.

Flexible delivery which adapted activities in response to the changing demand from and priorities of beneficiary institutions. It was the case of the inclusion at first of another development bank, CAIXA, previously planned to a beneficiary institution of the programme. As of change of priority, CAIXA has not been included and the programme must adapt itself to the inclusion of another beneficiary: BDMG.

Where activities were co-designed with partners, participants were much more engaged on issues, identifying ‘pain points’ and finding solutions. The design of the programme should be flexible to engage with the beneficiary to co design at output level. The beneficiary at Business Case level can agree on objectives but they have to codesign the output level during the inception phase in order to be more engaged on the delivery of the activities.

Where there is a clear sponsor (senior champion or ‘owner’ with a relevant professional mandate) for an agenda within financial institutions, implementation advanced much faster. It was the case for BNDES when the Presidency committed to the P3 project which was the implementation of the ESG framework. The pace of implementation has been accelerated. As a lesson learnt, a programme design should not sub estimate the onboarding of the relevant governance of the beneficiary to ensure a good delivery of the activities.

As regards capacity building, the amount of time required to refresh challenging technical material with beneficiaries and bring new beneficiary personnel up to speed should not be underestimated. Likewise, considerable ad hoc support (‘hand holding’) is needed to enable implementation of tools and recommendations.

OUTPUT 4

The objective of the output was to design and setting up two financial instruments in two development banks with the aim to address three objectives: (1) mobilize the financial resources required to tackle climate change; (2) finance the transition to a low carbon economy addressing the infrastructure gap in Brazil; (3) unlock flows for mitigation activities that reduce the source or enhances the sinks of GHG. The output intends to develop the national sustainable market through the structuring and deployment of suitable financial instruments and associated de-risking mechanisms that will draw the appetite from the private sector, therefore increasing their participation in emission reduction result-based infrastructure investments in Brazil.

Achievements

BNDES launched two sustainable finance products – the RenovaBio product and Crédito ASG product for Medium enterprises, together the two credit lines already sum a total of R$890 million in loans being implemented (9 operations in the RenovaBio totally R$780 million and the first investment made by the Crédito ASG in February 2022 in the amount of R$110 million) – in doing so implementing the Sustainable Finance Framework delivered by BGFP.

BDMG launched a solar panel technical viability and investment tool for public buildings. The tool has the intention to support municipalities, mainly from Minas Gerais, but also applicable to other Brazilian states, to access their investment needs to adopt solar energy as their main source of energy of their office buildings – to date the tool, that is available Brazil Green Finance Programme Closure Report 5 to download on the BGFP website, has had over 90 downloads.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

Benchmarking policies and practices across financial institutions proved hugely influential in convincing partner institutions to accept BGFP recommendations (the ‘peer pressure’ effect).

The decision of the BGFP to work first with BNDES in order to influence other development banks has proven to be important as BNDES had a role of pioneer and has been able to share lessons learnt and experience with the others development banks of the country.

BRAZIL TRADE FACILITATION PROGRAMME

Output Number and Title	Output 1. MSME Component – Enhanced capability, opportunity and motivation of MSME actors (including under-represented women/Black-owned/led MSMEs) through pilots aimed at providing MSME support, market access interventions, and improving the broader MSME ecosystem through systemic interventions. / Output 2. Ports Component – Demonstrable engagement of key port community actors, formalisation of port community governance structures, diagnosis of port systems and potential efficiency savings, and solutions scoped and supporting PCS IT systems.
Output Score	Output 1: A / Output 2: B
Impact weighting (%)	Output 1: 14% / Output 2: 11%		Impact weighting revised since last AR?	Yes, impact weightings have been recalculated in this review to proportionally sum 25% in each of the four programme strands.

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Governance - Steering Committee (SC) is operational and effectively oversees piloting of interventions and capacity building		SC operational / MSME Services - THSC agree on the implementation of pilots for Y1.	MSME Services - SC oversees pilot interventions. / MSME Services - SC take over operation of the platform and pilots. / Systems - SC agree on 'launch-version' of Trade Hub Digital Platform	A new and permanent Technical Management Committee is in place to approve the launch of the platform, and ApexBrasil has received the technology from BTF to become the operator of BRAEXP.
Systems - Global Trade Hub - GTH (i.e., the 'wardrobe') successfully designed, evaluated and launched		Digital platform design drafted	Digital platform launched	Digital platform finalised and transferred to the Brazilian Government. Partners have agreed to launch the platform by the end of 2023.
Port actors integrated into port community governance structures and benefitting through direct engagement with the programme		Port community governance structures in place in three ports	Actors of four ports participate in sustainability planning workshops	Two rounds of capacity building workshops on governance structures and on PCS business models and prototype were delivered by the programme during Y1. These workshops, divided in two sessions each, were attended by members of the local steering committees at each of the four targeted ports. This workstream was discontinued after budget cuts.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

The Brazil Trade Facilitation (BTF) programme supported inclusive and sustainable economic growth in Brazil through the internationalisation of the country’s micro, small and medium-sized enterprises (MSMEs) and the reduction of trade costs through increased port efficiency.

The programme relied on innovation to deliver two world-class digital solutions that will enable better business conditions for exporting companies. The BRAEXP (Plataforma Brasil Exportação) digital marketplace, previously known as the Global Trade Hub (GTH), will connect MSMEs with trade-related services providers that will help them access global markets on one comprehensive online platform. The Port Community System (PCS) will connect all public and private sector stakeholders involved in the running of Brazil’s key seaports, reducing export and import border crossing time. This will, in turn, mitigate the climate change impact of trade operations by reducing port-related idling of vessels and trucks.

During its three years of implementation, the BTF programme delivered the BRAEXP digital marketplace by: (i) designing, developing and testing the technology; (ii) transferring the technology to the Brazilian operator; (iii) designing and piloting export services to be integrated into the platform; and (iv) structuring a governance group, and negotiating and signing a governance agreement, as well as securing approval of associated legal and operational documents.

In parallel, the programme delivered a PCS toolkit by: (i) designing, developing, testing and publishing the source code of a pilot software with basic functionalities; (ii) mapping and streamlining port operations - and port systems-related processes; and iii) structuring governance groups, developing business cases with governance and financial models, and securing approval of a recommendation for a national standard on PCS interoperability.

Both components of the BTF programme – internationalisation of MSMEs through the delivery of BRAEXP and ports modernisation through the delivery of the PCS toolkit – were implemented with an additional focus on mainstreaming gender and inclusion (G&I), and climate control.

The G&I and climate control impact was particularly visible in the four export services pilots developed by the programme in conjunction with BRAEXP. The pilots positively impacted 905 Brazilian MSMEs, 62% of which owned and/or led by women and other under-represented groups. They also impacted more than 30,000 small-hold farmers from threatened biomes of the Amazon and the Cerrado.

Lessons learned through this output, and recommendations for future programming.

During its three years of implementation, the BTF programme learned a considerable number of lessons to be applied in similar programmes in Brazil. The main lessons are the following.

Governance matters. Governance is the key challenge to overcome in order to make digital platforms – such as BRAEXP and PCS – politically, financially and technologically sustainable overtime, in particular after the programme closes.

Digital transformation is key. Digital transformation was a key aspect of the BTF programme. As implementation progressed, it became clear to stakeholders that there was an opportunity for them to use the programme as an accelerator of digital transformation. Stakeholders had to fast-track their own transformation to the digital environment to receive the products of the programme (BRAEXP and PCS).

Embedding gender inclusion from the design phase. Brazil Trade Facilitation (BTF) programme was mentioned as a reference of gender and inclusion best-practice in the House of Commons – International Development Committee ‘Racism in the aid sector’ report. The report points out how BTF’s model of gender and inclusion integration starting at inception could be replicated as a standard on other projects to introduce ethnic and/or racial analysis.

BILATERAL FUTURE CITIES PROGRAMME

Output Number and Title	1. WATER / Capacity building on NRW and Performance-Based Contracts and Technical assistance for the development of NRW reduction plan in Recife / Behavioural interventions to improve water client behaviour and sanitation services; integration of behavioural science and design thinking into Water Utility’s operations. / Diagnostic and recommendations to enhance Water Utility’s management model. / MOBILITY / Upgrade and improvements in the transit Operations and Control Centre (OCC) in São Paulo / Smart traffic light impact assessment and technical, economic, financial, social and legal requirements for 5g network for a smart traffic lights / Inclusion of gender perspective on planning, operations and management of transport agencies and companies
Output Score	Water: A (all) / Mobility: A (all)
Impact weighting (%)	1. Water: / Output 1: 5% / Output 2: 5% / Output 3: 2.5% / 2. Mobility: / Output 1: 5% / Output 2: 5% / Output 5: 2.5%	Impact weighting revised since last AR?	Yes, impact weightings have been recalculated in this review to proportionally sum 25% in each of the four programme strands.

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Water 1 / 1.1 Training was held on NRW and Performance-Based Contracts for technical staff and Managers. / 1.2 Long-term NRW program for a Management Unit of the RMR was designed.	3	3	3
Water 2 / 2.1 Technical assistance in the design, testing and implementation of behavioural interventions to improve water client behaviours. / 2.2 Recommendations on the integration of behavioural science and design thinking into COMPESA’s operations. / 2.3 Recommendations on the application of behavioural science to sanitation service delivery	4	4	5
Water 3 / 3.7 An organizational structure for innovation was defined in COMPESA. / 3.8 Recommendations to address gender inequalities within COMPESA and its clients.	11	11	12
Mobility 1 / 1. Recommendations for bus system’s OCC and OMMS at São Paulo paper / 2. Recommendations for long term MaaS OCC and OMMS Strategy	12	12	12
Mobility 2 / 3. Methodology for cost-benefit analysis of smart traffic lights implementation / 4. Evaluation, Characterization and Dimensioning of the most recommended technological alternatives for smart traffic light and 5g report and strategy to implement a 5g network	12	12	12
Mobility 3 / 8. Proposal report for a unified 3-digit harassment complaints number / 9. Strategy paper to develop planning and design considering gender differences in mobility and perception of safety / 10. Inclusive job creation plan to contract more women	10	10	10

WATER OUTPUT 1

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Given that metropolitan region of Recife is water stressed (intensified by climate change), reducing water losses was a key element to increasing service resilience and sustainability. This output focused on operational efficiency, particularly on improving water supply management and reducing water losses.

This component focused on developing a structured Non-Revenue Water (NRW) program, and the associated organization structure, as well as on the incorporation of traditional instrumentation and innovative technology to detect and reduce water losses into COMPESA’s operations (the state-owned water and sanitation utility in Recife).

Key Achievements

BFCP successfully integrated NRW considerations into COMPESA's operational activities. NRW reduction became a central focus of the organization, impacting strategies, structures, and operations.

A global indicator for NRW was introduced, reflecting a strategic shift in COMPESA's thinking. This shift emphasized the importance of addressing water losses as a strategic priority. COMPESA indicated the intension to adopt more internationally recognised indicator, denoting a shift in corporate strategic thinking.

The Programme achieved significant success in reducing water losses, surpassing the initial targets. This achievement demonstrated the relevance and effectiveness of the activities implemented.

Lessons learned through this output, and recommendations for future programming.

The Programme highlighted the importance of incorporating NRW considerations into daily operational activities. Such integration should be a continuous process to maintain progress in reducing water losses and should be also encourage in other utilities around Brazil. Furthermore, future initiatives can benefit from adopting key performance indicators that reflect strategic objectives.

Discussions with state-level and national-level water regulator can be essential to incorporate these indicators as benchmarks for tariff reform, this can be replicated to other water utilities across Brazil.

A stimulating learning environment was critical for the generation of numerous inputs from participants and thought-provoking discussions. Not only did COMPESA gained knowledge, but it also helped to reaffirm leaders’ commitment to addressing NRW, given its importance to the achievement of corporate and efficiency performance results.

WATER OUTPUT 2

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

Leveraging behavioural science to help better understand consumer behaviour was conducted to support the water and sanitation sector in improving policy and strategy to reduce water losses, specifically to stimulate legal connections to the networks and ensure sustainable access for low-income users.

Key Achievements

COMPESA incorporated innovative approaches, including human-centred design and behavioural science, into its operations.

BFCP supported staff training and the integration of human-centred design into COMPESA's daily operations, fostering a culture of innovation. Several experiments were implemented to assess behaviourally informed reminders and interventions.

The Programme conducted detailed analyses of customer behaviour related to delayed payments, defaults, and sewerage network connections. Insights from these analyses guided interventions to address these issues.

Lessons learned through this output, and recommendations for future programming.

The Programme demonstrated the potential of innovative approaches to gain deeper insights into customer behaviour. Future projects should explore human-centred design and behavioural science to inform interventions effectively.

Staff training in experimental methodologies and innovative approaches was crucial for successful implementation. Organizations should invest in building staff capacity to adopt new methodologies.

Human-centred design and behavioural insights emphasized the importance of putting the customer at the centre of decision-making processes. Understanding customer needs and behaviour is essential for designing effective interventions. This can be easily replicated to other utilities wishing to enhance its user experience and improve client relations.

Several changes of behaviour, approach, and perspective were incorporated, a longer time frame would have given more time to mainstream these changes and foster sustainability.

WATER OUTPUT 3

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output provided ground for a solid organisational structure to support innovation and gender inclusion. Throughout this output, staff acquired the necessary knowledge and tools to identify, prioritise, apply for funding of, and plan and execute innovation projects.

Key Achievements

BFCP allowed COMPESA to successfully established an innovation lab, providing a dedicated space for innovative thinking and experimentation. Additionally, innovative machine learning techniques were implemented to enhance scenario planning and decision-making.

BFCP was key to establish gender-oriented dialogue, which led to the creation and successful implementation of a Gender Action Plan within COMPESA.

The utility reaffirmed its commitment to narrowing the gender gap and initiated actions such as developing a social responsibility policy and evaluating quotas for female leadership.

Lessons learned through this output, and recommendations for future programming.

The establishment of innovation labs can stimulate creativity and support the development of innovative solutions within organizations.

The Programme's focus on gender equality led to tangible results, including the development of policies and support for gender reassignment. Commitment to diversity and inclusion should remain a priority.

Greater local capacity and a longer time frame could have increased the Programme’s sustainability. Considering staff’s limited availability to undertake new tasks besides their daily routine, some activities resulted in being too ambitious as they were too resource- and time-intensive.

MOBILITY OUTPUTS 1 and 2

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

BFCP provided support processes to improve planning and management of the transport sector. These outputs aimed at supporting capital investments to incorporate innovative technologies in the urban mobility sector, thus improve current practices.

Output 1 focused on identifying innovative alternatives that could be applied to operations control centres (OCCs) and operational management and monitoring systems (OMMSs) to support the incorporation of mobility as a service (MaaS) and optimise transport planning and operations.

Output 2 focused on the cost-benefit analysis of smart traffic light implementation, producing a new methodology to evaluate the performance benefits of implementing several types of geometry relating to traffic flows for both vehicles and public transport.

Additionally, BFCP undertook a case study analysis of São Paulo to address existing and future challenges related to the digitalisation of traffic lights, sustainable traffic management, prioritisation of public transport and non-motorised transport modes, as well as developing the 5G services and intelligent transport systems.

Key Achievements

The Programme successfully modernized traffic lights using 5G technology, resulting in improved traffic flow and reduced congestion in São Paulo. This not only enhanced mobility but also contributed to reducing greenhouse gas emissions associated with idling vehicles.

The Programme promoted evidence-based decision-making in transport planning. By providing methodologies and tools for data-driven assessments, it facilitated more efficient allocation of resources and improvements in transport infrastructure.

The Smart Mobility Programme engagement amongst various stakeholders resulted in the provision of tailored-made recommendations, thereby enhancing the likelihood of their implementation. The activity also served as a learning opportunity by highlighting best practices from cities where big data analysis and machine learning processes have been successfully integrated into transport planning and day-to-day operations to support a local MaaS platform.

Lessons learned through this output, and recommendations for future programming.

The Programme emphasized the need for municipalities and transport authorities to collect and analyse data to make informed choices in infrastructure investments.

Some stakeholder showed resist innovations, and their acceptance frequently depends on the quality of communication. Mobility as a service was the backbone of the Smart Mobility Programme. However, this concept was not adequately disseminated and discussed with the municipality’s technical staff.

The success of urban mobility projects depended on collaboration among stakeholders, including government agencies, public transport providers, and civil society. Future initiatives should prioritize stakeholder engagement to achieve sustainable improvements in urban mobility.

BFCP highlighted the necessity of flexibility in project design to adapt to changing circumstances and political changes. Agile project management can help overcome unexpected challenges and maintain project momentum.

MOBILITY OUTPUT 3

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

BFCP supported measures to improve the regulatory and policy framework that governs the transport sector with focus on different population groups (women, low-income groups, or people in a situation of vulnerability).

The output 3 consisted of coordinating actors to develop the unification of reporting channels and response to harassment in public transport, which required standardized protocols and sharing of responsibilities. In addition, the inclusion of gender perspective in the transport planning and operational management.

Achievements

The Programme made noteworthy progress in addressing gender-specific transportation needs, particularly those of women. It conducted a Gender and Transport Baseline Study, revealing women's travel patterns and safety concerns in public transportation. Strategies were developed to sensitize municipal staff to gender-specific needs in public transport. This awareness aimed to improve the safety and comfort of female passengers.

The programme provided a complete courseware for an open online course for the sensitisation of decision makers and the design of a pilot for the unification of reporting protocols. Recommendations for gender-sensitive design were implemented, enhancing the safety and inclusivity of public transportation.

Lessons learned through this output, and recommendations for future programming.

The Programme underscored the importance of considering gender-specific transportation needs in urban planning. Future projects should prioritize gender-sensitive design to create safer and more accessible transport systems.

Building trust between the public and authorities in reporting harassment was identified as a challenge. Future initiatives should explore comprehensive mechanisms, such as developing a comprehensive database for harassment reporting, to address this issue.

Political engagement to ensure the implementation of the recommendations is essential for the Programme’s next steps. Nevertheless, it is recommended that most of the engagement and alignment is accomplished alongside technical staff, who tend to stay longer than do political appointees.

## D: Value for Money

 VfM performance compared to the original VfM proposition in the business case.

Efficiency

The value of inputs changed markedly from the original envisaged value throughout the course of the programme in two ways. The first occurred during the onset of the Covid-19 pandemic in March 2020 when the Brazilian Real started to depreciate significantly against the GB Pound (see Graph 2, below). By the following year, this had increased the value of any inputs in Reais throughout the programme by as much as 62%. With the value of inputs rising, implementing partners were able to reinvest additional value in the programme for any items that would typically be paid in Reais, such as some staff salaries, the capital assets purchased on the energy programme, and others. This evened out towards the end of the programme, but with the overwhelming bulk of spending concentrated in the first two years of the programme this did not have a significant negative effect on the value of inputs.

Graph 2 – GBP fluctuation against BRL

Another significant feature of inputs was the use of a variety of several types of implementing partners to implement the different strands of the programme. For instance, the Green Finance, Energy and the majority of the Trade Programmes had one commercial partner each leading the delivery of their respective programmes, in some cases through direct implementation and in other cases through subcontractors. On the other hand, the OECD Accession strand of the Trade Programme and the entirety of the Future Cities Programme were implemented directly by multilateral organisations, such as the OECD itself and the World Bank, respectively. This was a healthy spread of diverse types of implementing partner according to stated aims. In only one instance are we following up any perceived inefficiencies in implementation, and indeed we have continued our partnership with the OECD through Non-ODA funding given the value we have realised for relatively modest sums spent on engaging them involved.

Effectiveness

The effectiveness with which inputs were translated to outputs was clearly affected by the substantial and relatively sudden cut in funding down to £1 million in 2021 with the closure of the Global Prosperity Fund. This severely affected the Value for Money of the overall Business Case by cutting all programme strands short before they could realise their full objectives. One case of this was the Brazil Energy Programme where several strands were halted mid-stream, with the loss of any sunk cost or preparatory work as a result.

On the other hand, during the second and third year of implementation the programme team was able to mitigate parts of the impact of the ODA cuts by accessing new types of funding across the UK Government. ICF’s UK PACT programme, in that sense, was key during Year 2 of implementation to make sure the programmes would continue operating in key priority areas, despite of the reduced original funding. In total, the team was able to secure additional £4.4 million for the programme’s second year of implementation, which were used in nine different projects across the four programme workstreams. Besides that, in the third year, the team managed to access additional £175,000 from the non-ODA Challenge Fund to allow the conclusion of one of the main and most important projects of the Brazil Prosperity Fund – the reform of the Transfer Pricing system in Brazil, delivered in partnership with the OECD.

Equity

The Brazil Prosperity Fund Programme portfolio was designed to channel investment into initiatives that reduced poverty and provided economic opportunities for poor or marginalised people in Brazil. This was obviously the case across overtly anti-poverty programmes such as the Brazil Energy Programme, which laid the groundwork for the establishment of a clean energy supply in poor communities of Rio de Janeiro. However, this was also realised in administrative programmes such as the Trade Facilitation programme which established a platform for MSMEs to reach international markets they would not necessarily otherwise have reached.

## E: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Over the duration of the programme, the Prosperity Fund programme in Brazil faced various challenges and uncertainties, particularly influenced by global events such as the Covid-19 pandemic. Reputational risks were the most prominent during this period, as programmes had to close earlier due to funding reduction. Risk management tools evolved, and lessons learnt were carefully assessed, aiming at minimizing disruptions to milestone deliveries while maintaining alignment with the FCDO's risk appetite. The programme also counted on the Prosperity Fund Board which analysed the Risk register quarterly.

Response to Partner-Related Risks: Risks related to partners were evaluated through meticulous due diligence. The programme's response encompassed close collaboration and communication, mitigating potential challenges. Despite external disruptions, the team successfully managed risks arising from reduced buy-in by government stakeholders and ensured continued focus on poverty reduction and international business opportunities.

Effect on Risk Appetite: The program remained within the established risk appetite, even in the face of Covid-19 adaptations. Program forecast spend and allocations were closely monitored, with the PF Operations team implementing monthly evaluations and adjustments to curtail significant variances by the end of the fiscal year.

Managing Early Closure Risks: for programmes closing earlier than anticipated, Brazil team approach involved addressing specific risks identified in relation to early closure. This included outlining the exit strategy and ongoing mitigations. Sustainability actions extending beyond FCDO support have been planned to maintain the desired outcomes. However, this will prove difficult due to the substantial reduction of staff and the consequent loss of programme memory.

Risk Landscape after Covid-19 and early closure: Covid-19 pandemic posed significant challenges to program delivery. Teams had to adapt, leading to revised workplans, remote activity execution and reduction of outputs, and therefore expected outcomes. Risks related to Covid-19 were effectively managed, preserving alignment with business and budget allocations. The risk of underspending was monitored diligently to ensure financial objectives were met. As a consequence, despite of the pandemic, the programme achieved 100% to 105% of spend in all fiscal years of the implementation phase.

Overall, the risks were addressed promptly, and some programmes assessed individually which led to other source of funds for extending the early closure. This approach was essential to mitigate reputational risks and the damage on impactful outcome being missed.

## F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Phase Transition: The Prosperity Fund programmes in Brazil experienced a smooth transition from the inception phase to the implementation phase across all strands, with some minor delays. However, implementation phase was severely affected by COVID-19 and ODA reprioritisation, with some programmes having to discontinuing some strands due to adaptation of shorter timeframe and significant funding cuts.

Value for Money (VfM) Measures: Delivery partners, particularly from the Trade Programme, have displayed commendable fiscal management leadership and robust programme management systems. Their ability to navigate the complexities of programme delivery reflects positively on the VfM measures. However, there is room for streamlining outputs and indicators in logframes to facilitate more straightforward tracking of progress and VfM assessment.

Procurement and Contracting: Delays in procurement and contracting from FCDO slightly affected the start of some programmes. Local staff had access to training and open contact with commercial team in London, which contributed to smooth contract monitoring and management. Due to the COVID-19 and the ODA reduction, contract variations were often required during the second and third years of implementation. All of them were successfully managed by the programme team with support and close supervision by the Commercial Directorate in FCDO HQ.

Delivery Partners: Challenges in engaging with delivery partners were noted, including issues related to program management, definition of objectives, staff turnover, roles, and responsibilities. In order to minimise the impact, suppliers had access to standard reporting templates and performance standards, benefitting the communication and collaboration with delivery partners.

Additionally, supplier Conferences have played a valuable role in setting expectations and fostering collaboration. Suppliers provided positive feedback, contributing to a more partnership-oriented approach and facilitating open dialogue and problem solving between teams and suppliers.

The introduction of standard reporting templates and the creation of the Operations team at the start of the implementation phase significantly enhanced the quality and consistency of narrative reports across programme strands. Nevertheless, a thorough review reveals that narrative reporting could benefit from greater granularity to provide deeper insights into project-specific challenges and accomplishments. Furthermore, the adherence to timelines for financial reporting has improved over the course of the programmes, indicating a positive trend in the accuracy and reliability of financial data.

Additionally, a Strategic Relationship Management scorecard assessment provided valuable insights into the overall performance of partners. While most partners have demonstrated commendable performance, the team faced some challenges with multilateral institutions, mainly due to the nature of their reporting mechanism. To overcome this, the team has developed a closer communication channel and in-depth alignment, especially regarding Theory of Change (ToC) and logframe discrepancies.

FCDO’s role (including local and London staff) in fostering a conducive environment for partnership effectiveness should not be understated. This included facilitating clear lines of communication, proactively addressing partner concerns, and ensuring the mutual alignment of objectives. The teams had shown adaptability and resilience when dealing with uncertainties and challenges to ensure success delivery and impactful outcomes.

Programme-level approach to monitoring and evaluation

The Brazil Prosperity Fund adopted a comprehensive programme-level approach to monitoring and evaluation. This approach leverages Theories of Change, standardized reporting procedures, Performance Standards for suppliers, and engagement mechanisms like Suppliers' Conferences to ensure effective oversight and adaptability. Furthermore, the emphasis on tracking secondary benefits underscores the program's commitment to delivering tangible and sustainable results.

Unfortunately, MREL was one of the first and most severely aspects of the programme affected by the ODA cuts, which resulted on immediate global discontinuation of external evaluating consultancy services, global shut-down of FCDO’s programme management platforms (e.g., Prospero) and instant close of the Secondary Benefits Advisor position at post.

Theory of Change and Logframes: MREL approach has been the development and refinement of Theories of Change (ToCs) and logframes. Over the durations of the programmes, significant efforts have been invested in establishing and revising these frameworks for all programme strands. These methods are not only comprehensive but also consider critical factors, such as potential secondary benefits and the impacts of external factors like COVID-19.

Standard Operating Procedures and Reporting Templates: The introduction of standard reporting templates encompassed critical facets like costed workplans, financial reports, quarterly programme monitoring reports, risk registers, and logframes. This introduction has vastly improved the quality and consistency of reporting across programme strands. Moreover, it has clarified reporting frequency and established a coherent reporting structure, further streamlining the monitoring process.

Secondary Benefits and Knowledge Sharing: A critical component of monitoring and evaluation was also to assessing secondary benefits. Brazil team developed a Tools Pack (which was later incorporated across PF countries), including key performance indicators (KPIs), a plan, and a tracker. The establishment of a secondary benefits' Impact Bank has facilitated the aggregation of both commercial and non-commercial impacts of interventions. Notably, the programme's efforts direct created opportunities of unlocking various areas such as soft power, network effects, and market access, as well supported of export wins, contract awards. This showcases the real-world impact of the programme's interventions.

Date of last narrative financial report	March/2023	Date of last audited annual statement	June/2023

Annex A – Summary of Key Achievements Across Brazil Prosperity Fund Programmes

Brazil Green Finance Programme (BGFP)

The Brazil Green Finance Programme aimed at increasing investment in sustainable infrastructure and contributing to the country’s transition to a low carbon economy by reducing greenhouse gas (GHG) emissions. Following the ODA reprioritisation, the programme was restructured in its final year to fit the criteria of the UK PACT programme, funded by the ICF.

By its end in March/2022, the programme supported Brazilian development banks BNDES and BDMG by providing tools and capacity to set up Paris-aligned targets so they could contribute to efforts to limit global warming. Besides that, the programme also enabled them to footprint their financed emissions and to aim for decarbonisation trajectories.

Following implementation, the climate agenda has become more visible within BNDES’ institutional priorities. BNDES launched two sustainable finance products – the RenovaBio product and Crédito ASG product for medium enterprises. Together the two credit lines already sum a total of R$890 million in loans being implemented. Besides that, BNDES fed back that recommendations from ESG Management and Blended Finance workstreams were taken into consideration in organisational changes. In 2021, the programme supported BNDES to make climate-related commitments publicly at COP26.

BDMG launched a solar panel technical viability and investment tool for public buildings. The tool has the intention to support municipalities, mainly from the Minas Gerais state, but also applicable to other Brazilian states, to access their investment needs to adopt solar energy as their main source of energy of their office buildings. The Programme has also supported BDMG in accessing their carbon footprint of their full investment portfolio and financed emissions to support a sustainability strategy to achieve their commitments to the Race to Zero Campaign and Fossil Fuel 0%.

Brazil Energy Programme (BEP)

The main purpose of the Brazil Energy Programme (BEP) was to accelerate Brazil’s energy transition to a low-carbon economy while promoting inclusive growth and gender equality. The programme aimed at making achievements in three fundamental areas – Public Policy and Regulation, Market Innovations and Technology – across five different energy subsectors – waste-to-energy (W2E), biofuels, solar/electricity, offshore wind (OSW) and low-carbon hydrogen.

By the end of the implementation, in March/2022, the programme had accelerated Brazil’s transition to green energy in a number of areas, namely:

  1. Catalysing the regulation of biomethane across all twenty-seven states with data, guidelines and partnerships that will help state governments to unlock energy potential within their agricultural sectors, solid waste management operations and water treatment plants to the benefit of low-income citizens.

  1. Building consensus within government on the future direction of blue and turquoise hydrogen so that policymakers and investors can begin to build the infrastructure needed to develop a significant hydrogen industry that will empower women and support livelihoods for Afro-Brazilians.

  1. Defining innovative policy alternatives and financing mechanisms to the Social Tariff that can redirect subsidies for low-income household energy consumption into clean distributed energy generation for low-income households.

  1. Secured inclusion of biogas production in Brazil’s agriculture decarbonisation plan and halved the cost of quality controlling biomethane.

  1. Building a demonstration pilot to test the viability of different distributed energy generation models within urban low-income communities and developing options for tariff reform that will facilitate the expansion of such models into the low-income market segmentation.

  1. Building a central online database for all clean energy research, development and innovation (RD&I) public and publicly oriented investments so that policymakers, companies, research institutes and investors have the analysis they need to make the most strategic investments into RD&I.

Bilateral Future Cities Programme (BFCP)

The core objective of the Bilateral Future Cities Programme was to pilot innovative “smart” technologies to promote integrated and sustainable transport systems in São Paulo (Smart Mobility Programme) and reduce water lost by leakages in Recife (Smart Water Programme), improving the quality of life for the poorest, reducing negative impacts on Brazil’s economic development, and combatting climate change. The programme was a partnership with the World Bank, which acted as the implementing partner.

Smart Mobility in São Paulo

Overall, the Smart Mobility Programme achieved more than 96% of its final targets and provided powerful insights into the public transportation sector in São Paulo, providing recommendations and methodological approaches that could be replicated in other cities with similar contexts, potentially increasing the Programme’s impact. Should investments be secured to implement the innovative recommendations delivered, there is potential for São Paulo to become a global transport reference point.

In terms of social inclusion, the most important contribution from the Smart Mobility Programme was bringing attention to women’s needs in transport and how to address them. The Gender and Transport Baseline Study developed by the programme showed that women walk and use more buses and trains than men. It also highlighted the substantial number of hotlines to report harassment in transport as well as the gender gap in transport sector companies’ staff. Under the Programme, strategies were developed to sensitise municipal staff to gender needs in public transport.

Smart Water in Recife

The Smart Water Programme achieved the core objective of reducing non-revenue water (NRW) in the Recife Metropolitan Region (RMR). Although measuring the direct impact on the quality of life of the poorest is difficult, managing water resources more efficiently and reducing water losses increase water availability, enabling the expansion of services to the poor. The programme worked with COMPESA (the state-owned water and sanitation utility in Recife) to improve its operational efficiency by reducing water losses.

As a result, COMPESA now considers NRW in all of its operational activities. For example, they revised all of its strategies and structures to ensure losses are adequately addressed. In addition, a newly defined, global indicator for NRW will be used to design a shared target, reflecting a shift in corporate strategic thinking. In sum, the actions targeting the reduction and control of NRW were highly effective.

Besides that, COMPESA’s innovation lab was reformulated, and staff acquired the necessary knowledge and skills to identify, prioritise, secure funding, plan, and execute innovation projects. Furthermore, innovative machine learning techniques were implemented to help COMPESA prepare better for different scenarios and for more informed decision-making.

Brazil Trade Facilitation Programme (BTF)

The Brazil Trade Facilitation Programme aimed at unlocking additional trade flows from Brazil into the international market, generating job creation, economic growth, women empowerment and poverty reduction, by supporting Brazil to operate according to international efficiency standards in three key areas of foreign trade: Efficiency in Ports, Internationalisation of MSMEs (Micro, Small and Medium Enterprises) and Accession to the OECD.

For the Ports and the MSMEs components, the programme relied on innovation to deliver two world-class digital solutions that will enable better business conditions for exporting companies: the PCS (Ports Community System) and BRAEXP (Plataforma Brasil Exportação). For the third component, the UK made a partnership with the OECD to provide technical assistance to Receita Federal, Brazil’s tax authority, to support the country’s alignment with OECD best practices and standards across several areas.

Ports Efficiency

On the Ports component, the programme delivered a digital platform to increase port efficiency – the PCS (Ports Community System). The PCS integrates all existing systems that public and private stakeholders use to manage the running of the ports based on new, streamlined port processes. It can also provide specific applications suited to the needs of each port, such as real-time mapping of dangerous cargo or reducing the time it takes to get vessels in and out. By increasing efficiency, the platform will further reduce vessel and truck idling time and their emissions of greenhouse gas. The PCS prototype was delivered with basic functionalities in open-source, cloud-ready software.

Besides that, the programme was responsible for creating: a business case model for governance and financial aspects of the platform, with applied cases for the Itajaí and Santos port communities; a vast mapping and streamlining of port-related processes; and a national standard for PCS interoperability. With these tools, any of the thirty-six organised port communities can immediately begin PCS implementation in Brazil. If fully implemented in Santos, the largest seaport in Latin America, the platform has the potential to reduce port processes-related bureaucracy in up to 16% and carbon emissions in up to 52%.

Internationalisation of MSMEs

The main deliverable of the BTF programme’s MSMEs Component was the design, development, testing and transfer of BRAEXP (Plataforma Brasil Exportação) technology to the Brazilian Government. BRAEXP is the first digital marketplace for trade-related services in Brazil covering the whole supply chain of export and import services. The platform will be operated by ApexBrasil (The Brazilian Trade and Investment Promotion Agency), which created a new business unit fully dedicated to BRAEXP’s implementation, launching, operation and evolution, and approved resolutions to incorporate the platform as a strategic objective of the agency. If fully implemented, BRAEXP could increase Brazilian GDP by 2.56%, exports by 9.41% and imports by 5.80% by 2040, creating nearly 630,000 new jobs.

Another key deliverable was the full digitisation and automation of the National Plan for Export Culture (PNCE). PNCE is a free service provided by the Brazilian federal government to any company, in particular MSMEs, that wants to self-assess its export maturity level and receive a tailor-made internationalisation plan. In the future, PNCE will be integrated with BRAEXP.

The programme also implemented four export services pilots to assess new or existing concepts within a digital environment. The aggregated impact of these pilots resulted in £13.72 million in new exports from Brazil, with 905 MSMEs and more than 30,000 small-holder farmers supported.

Brazil’s Accession to the OECD

The programme was delivered through a trilateral partnership between Brazil, the UK and the OECD and focused on providing technical assistance to Brazil in five key areas: Codes of Liberalisation, Enforcement of Minority Shareholder’s Rights, State Owned Enterprises (SOEs), Environment and Transfer Pricing.

As a result of the first four projects, the OECD published reports with analysis and key recommendations on Brazil’s environmental policies and privatisation of SOEs in the short and medium term, besides facilitating the process for international companies to operate Brazil and influencing Brazil’s Securities Commission (CVM) to change key resolutions that will support the rights of minority shareholders’.

Finally, the reform of the Brazilian transfer pricing system was the largest and most important project of the programme. After over five years of work, the Brazilian Congress approved the new Transfer Pricing law in May 2023, aligning Brazil’s new system with the OECD standards, which will contribute to improve the country’s business environment and prevent double taxation, for example.

Brazil Intellectual Property (Global Trade Programme)

The Brazil Intellectual Property (Brazil IP) was a programme originally conceived under the wider Global Trade Programme portfolio and business case. Following the ODA reduction announcements, the programme was under a serious risk of cancellation, which made the Brazil Programme Board to take the decision to collaborate with the GTP and fund part of the programme. Brazil IP aimed at supporting Brazil to improve the management of Intellectual Property Rights by implementing targeted interventions that would bring the country closer to international standards and practices in this sector.

As a result of GESI mainstreaming and GESI assessment on the programme, a proposal has been put forward to the directorate of INPI (Brazil’s IP Office) to create a cross-departmental committee on gender equality and social inclusion (CEGDI), which will institutionalise GESI sensitivity in decision making and activity planning.

In terms of processes, as-is and to-be mapping of eight macroprocesses were completed, resulting in 878 recommendations that will allow significant future benefits when implemented by INPI. On IT, the programme developed IT Service Catalogue report (including identification of 168 IT services) and Strategic Plan (PDTIC) for the IT Department. On pricing, it developed a tariff simulator based on the application TD ABC (Time Driven Activity Based Cost) methodology to four areas in INPI that will be used by INPI going forward.

Brazil Better Health Programme

The Better Health Programme in Brazil (BHP-B) was conceived under a wider BHP portfolio from the Prosperity Fund across the world and aimed at tackling some of the most pressing structural challenges in the Brazilian Public Healthcare System (SUS). Following the ODA cuts, the Brazil Programme Board decided to allocate funds to cover one of the main milestones of the programme: the Digital Health Strategy.

The programme created the ambitious digital health strategy for Hospital das Clínicas (HCFMUSP), the leading public hospital in Latin America, and supported its implementation. As a result, HCFMUSP expanded its teleconsultations, reaching 22,000 monthly video telephone consultations (15%), besides expanding the hospital’s training materials. In total, +200,000 patients were benefitted from the telemedicine solutions as a consequence to the programme’s support.