## Slide 1: DSA Performance Pack: March 2025

## Slide 2: Contents
This pack contains the following:
Contents (2)
DSA application volumes
  Student Finance England (3)
  Student Finance Wales (4)
Customer Satisfaction Survey (CSAT) results (5, 6)
Initial Key Performance Indicator reports (KPIs)
  Capita (7, 8, 9, 10)
  Study Tech (11, 12 , 13, 14)
Applications by disability type
  Student Finance England (15)
  Student Finance Wales (16)

## Slide 3: DSA Application Volumes – Student Finance England (SFE)
SFE
Full Application Volumes
Year | DSA Apps received | Eligible | Ineligible/Lapsed/Cancelled | Pended | Support approved
23/24 (Full Year) | 111,470 | 77,311 | 5,645 | 28,514 | 54,491
24/25 (Full Year) | 108,031 | 73,728 | 3,159 | 31,144 | 44,207
SFE
Like for like comparison
Year | All Apps | Eligible | Ineligible/Lapsed/Cancelled | Pended | Support approved
23/24 (Up to 6/4/2023) | 11,593 | 3,609 | 98 | 7,886 | 736
24/25 (Up to 6/4/2024) | 9,288 | 2,045 | 49 | 7,194 | 92
25/26 (Up to 6/4/2025) | 13,135 | 4,102 | 121 | 8,912 | 158
2025/26 – Current Application Volumes
The application service for SFE full-time undergraduate customers opened on 10 March 2025.
Our aim is to encourage earlier applications this cycle. In partnership with UCAS, we targeted over 450k prospective students in our ‘Apply Now’ email campaign which included new content about applying for DSA as soon as possible.
As of 6 April 2025, the volume of DSA applications received is trending 41% up on the previous year with 71% more customers having agreed DSA support confirmed.
We are working closely with suppliers to learn lessons from the first year of the new service and to deliver improved performance in 25/26, including a faster end-to-end journey.
2024/2025 – Latest position
As of 6 April 2025, we have received over 108k DSA applications and have approved DSA support for over 44.2k customers. This is tracking -1.8% behind performance in the previous year, where 45k customers had support approved by this date.
Some customers waited longer than should be expected at certain stages of the process in 24/25. SLC and the suppliers implemented mitigations to boost capacity and reduce needs assessment wait times.
Our priority is ensuring all students who applied for DSA in 24/25 get their support in place as quickly and efficiently as possible.

## Slide 4: DSA Application Volumes – Student Finance Wales (SFW)
SFW
Full Application Volumes
Year | DSA Apps received | Eligible | Ineligible/Lapsed/Cancelled | Pended | Support approved
23/24 (Full Year) | 6,094 | 4,298 | 330 | 1,466 | 3,230
24/25 (Full Year) | 5,732 | 4,002 | 167 | 1,563 | 2,611
SFW
Like for like comparison
Year | All Apps | Eligible | Ineligible/Lapsed/Cancelled | Pended | Support approved
23/24 (Up to 6/4/2023) | 172 | 31 | 1 | 140 | 3
24/25 (Up to 6/4/2024) | 230 | 82 | 0 | 148 | 5
25/26 (Up to 6/4/2025) | 221 | 58 | 0 | 163 | 2
2025/26 – Current Application Volumes
The application service for SFW full-time undergraduate customers opened on 24 March 2025.
As of 6 April 2025, 221 applications have been received which is broadly in line with the volumes received at this stage in the previous academic cycle.
We are working closely with suppliers to learn lessons from the first year of the new service and to deliver improved performance in 25/26, including a faster end-to-end journey.
2024/2025 – Latest position
As of 6 April 2025, we have received over 5.7k DSA applications which is tracking in line with the previous year’s volume. We have approved DSA support for over 2.6k customers. This is tracking -4.4% behind performance in the previous year, where 2.7k customers had support approved by this date.
Some customers waited longer than should be expected at certain stages of the process in 24/25. SLC and the suppliers implemented mitigations to boost capacity and reduce needs assessment wait times.
Our priority is ensuring all students who applied for DSA in 24/25 get their support in place as quickly and efficiently as possible.

## Slide 5: Customer Satisfaction Survey (CSAT) results - March 2025
THEME | Overall YTD combined 1,410 responses | Study Tech customers 770 responses | Capita customers 640 responses | Baseline Score (Legacy service) >5k responses
Simplicity of following the information, advice and guidance provided | 66% | 65% | 68% | N/A
Simplicity of the Needs Assessment booking process | 74% | 70% | 78% | N/A
Convenience of travel time and location (in-person assessments) | 87% (300 customers) | 88% (165 customers) | 85% (135 customers) | N/A
Satisfaction with the Needs Assessment Service | 81% (+9%) | 81% (+9%) | 80% (+8%) | 72%
Perception of the quality of Assistive Technology products provided | 78% (+3%) | 78% (+3%) | 77% (+2%) | 75%
Satisfaction with the Assistive Technology delivery, set up and customer service | 73% (+6%) | 72% ( +5%) | 73% (+6%) | 67%
Satisfaction with the AT training provided | 81% | 82% | 80% | N/A
Overall satisfaction with the DSA application experience | 71% (+7%) | 69% (+5%) | 73% (+9%) | 64%
Commentary
1,410 customers have responded to our DSA CSAT survey since the launch of the new service in February 2024. Around 4% of DSA customers provide a submission once they receive their support. This aligns with response rates for other SLC customer surveys.
96% of responses are from Student Finance England customers. 4% are from Student Finance Wales customers. 54.6% of responders were supported by Study Tech and 44.4% supported by Capita.
CSAT scores are higher than those recorded for the pre-reforms DSA service. The overall average score is very similar for both suppliers.
The overall DSA experience currently has a satisfaction score of 71% which is 7% higher than the rating for the pre-reforms service. Overall satisfaction scores have declined by 6% since September 2024, due to the longer wait times customers have experienced during our busiest processing period.
21% of customers who responded to the survey suggested they had an in-person needs assessment.
Satisfaction with the Needs Assessment Service continues to perform well with an 81% satisfaction score, which is 9% higher than the baseline. The lowest scoring theme is how simple customers find it to follow the guidance being provided by SLC and the suppliers on how to progress their application.
The baseline results were taken from the previous iteration of the DSA Customer Survey which ran between July 2021 and February 2024.
The survey was refined for the launch of the new DSA service. Where the baseline score is N/A, this is because an equivalent question was not asked in the previous survey.
We are committed to improving the overall application experience and simplifying guidance for DSA customers.

## Slide 6: CSAT participation by disability type - March 2025
Disability Type | Participation in CSAT survey (%)
Autism | 19%
Hearing Impairment | 2%
Learning Difficulty | 22%
Longstanding Illness | 10%
Mental Heath Condition | 15%
Mobility | 9%
Multiple Disabilities | 21%
Visual Impairment | 1%
Commentary
As of March 2025, 22% of students who completed a customer satisfaction survey told us they have a learning difficulty. 19% said they have autism.
Students with a hearing impairment represented 2% of respondents, with 1% of respondents having a visual impairment.

## Slide 7: KPI Reporting Capita – March 2025 (1)
Commentary – Capita
Capita experienced a specific system issue when planned enhancements to the DSA service were introduced in November 2024. This issue, which they worked urgently to resolve, impacted their service performance in December and early January. Capita have confirmed their system is fully restored.
However, due to KPI service performance, a service recovery plan has been created and is reviewed by SLC every two weeks.
KPI 1 - No issues, target being met.
KPI 2 - Improvement has been seen since the system issue was resolved, and focus remains on ensuring Capita continue to improve through weekly performance reviews. For March, the average wait time for an appointment was 22 days with 60% of customers being offered an appointment in 7 days.
KPI 3 - A continued improvement has been seen; however, they remain below the target, which is being tracked under the service recovery plan.
KPI 4 - Improvement is still required here and work is ongoing with SLC and both suppliers around this KPI.
KPI | Description of standard | Name | Description | Service Level | Target | Actual (At 31 March)
1 | Minimum of 95% of offers of NA appointments made within 2 working days of referral of customers by SLC. | NA First Contact | Initial NA communication sent from Supplier to Customer after Supplier receipt of SLC NA referral approval | >=95% | <=2 working days | 100%
2 | Minimum of 95% of NAs should be offered and completed within 7 working days of the successful contact (excluding those where the customer has requested an alternative date). | NA Offered & Completed | NA appointment offered and completed | >=95% | <=7 working days | 48%
3 | Minimum of 95% of NARs made available to SLC within 5 working days of when NA undertaken (excluding those where the customer has requested to review the NAR). | NAR Returns | Completed NAs submitted from Supplier to SLC | >=95% | <=5 working days | 54%
4 | Minimum of 95% of NARs meet the standard of acceptability as defined by SLC. | NARs Quality Standard | Submitted NARs from Supplier to SLC Approved on first submission: Right First Time (not pended) | >=95% | Standard of Acceptability | 84%

## Slide 8: KPI Reporting Capita – March 2025 (2)
Commentary – Capita
KPI 6 - No issues, target being met.
KPI 7 - Continues to be achieved through utilising subcontractors.
KPI 9 - No issues, target being met.
KPI 10 - Improvements made and in target. Capita continue to work with their two subcontractors to achieve further improvement.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
6 | Minimum of 95% of customers will be contacted within 2 working days of receiving SLC approval to arrange delivery of equipment appointment. | AT Equipment First Contact | Customer Contact rate for approved AT Equipment delivery to Customer | >=95% | <=2 working days | 100%
7 | Minimum of 95% of customers will receive equipment package within 5 working days of successful contact, or 5 working days from the date the £200 contribution is received if relevant (excluding customers who request an appointment after the 5 days). | AT Equipment Delivery Offered | AT Equipment Delivery after successful contact and where applicable after contribution payment is received from customer | >=95% | <=5 working days | 99%
9 | Minimum of 95% of customers will be contacted to arrange a suitable date for the first AT training session within 1 working day of receiving their equipment. | AT Training First Contact | AT Training appointment booking contact sent to Customer from Supplier | >=95% | <=1 working days | 97%
10 | Minimum of 95% of customers will have attended their first AT session within 5 working days of receiving the equipment (excluding customers who request an appointment after the 5 working days). | AT Training Offered | AT Training appointment confirmed and attended by Customer | >=95% | <=5 working days | 95%

## Slide 9: KPI Reporting Capita – March 2025 (3)
Commentary - Capita
KPI 12 - Is now split into two measures: Percentage of Calls Answered and Average Speed of Answer. Capita are performing above target on both measures.
Additional KPIs have now also been added to the pack:
KPI 15 - Above target on response time for complaints.
KPI 16 - No issues, target being met.
KPI 19 - No issues, target being met.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
12 | Minimum of 98% of calls by customers to supplier being answered within 1 minute. | Inbound Calls Response | Inbound Calls Percentage Answered (PCA) | >=98% | Answered | 100%
15 | Minimum of 95% of complaints from customers must be investigated and responded to within 10 working days of receipt. | Complaints Handling | Customer Complaints Response Rate | >=95% | <=10 working days | 96%
16 | Monthly reporting must be compiled and submitted to SLC by the 5th working day of each month for the previous month. | Reporting | Monthly reporting compiled and submitted for the previous month | 100% | 5th working day of each month | 100%
19 | Availability of supplier systems supporting DSA must be greater than 99.9% at all times unless planned maintenance has been agreed outside of normal office hours. | Systems Availability | Technology Platform & Systems Uptime | >=99.9% | Available | 100%

## Slide 10: KPI Reporting Capita – March 2025 (4)
These KPIs are related to Customer Satisfaction that has already been covered on slide 5.
Both suppliers are performing above the 70% target across the three KPIs.
Please note, we are undertaking a 3-6 month KPI baselining period, which started in January 2025, to assess the KPIs following the initial performance of the service since February 2024. As part of this, we will consider potential iterations to ensure that they are as effective as possible.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
5 | Satisfaction with the Needs Assessment Service. | NA Experience (SLC report) | CSAT survey satisfaction score for sampled NAs completed | Overall Sat | >=70% | 80%
8 | Satisfaction with the Assistive Technology delivery, set up and customer service. | AT Equipment Experience (SLC Report) | CSAT survey satisfaction score for sampled NAs completed | Overall Sat | >=70% | 73%
11 | Satisfaction with the Assistive Technology Training delivery, set up and customer service. | AT Training Experience (SLC Report) | CSAT survey satisfaction score for Assistive Technology Training delivery and customer service | Overall Sat | >=70% | 80%

## Slide 11: KPI Reporting Study Tech – March 2025 (1)
Commentary – Study Tech
KPI 1 - No issues, target being met.
KPI 2 - Study Tech have an improved performance with 96% of customers offered a needs assessment within 7 working days. Average offered appointment is now 2 days. New data provided by ST shows although offering within 7 days, students are choosing to book day 12/13 on average.
KPI 3 - There has been a significant improvement each month and ST are very close to target. Improvements to their quality assurance process has enabled NARs to be shared more quickly and efficiently with SLC.
KPI 4 - Study Tech are close to target and we will continue to closely monitor. As above, work is ongoing on this KPI with SLC and both suppliers.
KPI | Description of standard | Name | Description | Service Level | Target | Actual (At 31 March)
1 | Minimum of 95% of offers of NA appointment made within 2 working days of referral of customers by SLC. | NA First Contact | Initial NA communication sent from Supplier to Customer after Supplier receipt of SLC NA referral approval | >=95% | <=2 working days | 99%
2 | Minimum of 95% of NAs should be offered and completed within 7 working days of the successful contact (excluding those where the customer has requested an alternative date). | NA Offered & Completed | NA appointment offered and completed | >=95% | <=7 working days | 96%
3 | Minimum of 95% of NARs made available to SLC within 5 working days of when NA undertaken (excluding those where the customer has requested to review the NAR). | NA Returns | Completed NAs submitted from Supplier to SLC | >=95% | <=5 working days | 93%
4 | Minimum of 95% of NARs meet the standard of acceptability as defined by SLC. | NARs Quality Standard | Submitted NARs from Supplier to SLC Approved on first submission: Right First Time (not pended) | >=95% | Standard of Acceptability | 92%

## Slide 12: KPI Reporting Study Tech – March 2025 (2)
Commentary – Study Tech
KPI 6 - No issues, target being met.
KPI 7 – ST are below target on this KPI for March, but for context their average is currently 6.5 days for delivery and as of mid April, up to 47% against the KPI. Further technical improvements are being implement by Study Tech with an aim to increase this KPI but without compromising quality of kit. This KPI will be reviewed as part of the ongoing KPI Baselining exercise.
KPI 9 - No issues, target being met.
KPI 10 – Improvements made and close to target, but supplier continues to review. Average for March is 1.5 days.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
6 | Minimum of 95% of customers will be contacted within 2 working days of receiving SLC approval to arrange delivery of equipment appointment. | AT Equipment First Contact | Customer Contact rate for approved AT Equipment delivery to Customer | >=95% | <=2 working days | 100%
7 | Minimum of 95% of customers will receive equipment package within 5 working days of successful contact, or 5 working days from the date the £200 contribution is received if relevant (excluding customers who request an appointment after the 5 days). | AT Equipment Delivery Offered | AT Equipment Delivery after successful contact and where applicable after contribution payment is received from customer | >=95% | <=5 working days | 12%
9 | Minimum of 95% of customers will be contacted to arrange a suitable date for the first AT training session within 1 working day of receiving their equipment. | AT Training First Contact | AT Training appointment booking contact sent to Customer from Supplier | >=95% | <=1 working days | 100%
10 | Minimum of 95% of customers will have attended their first AT session within 5 working days of receiving the equipment (excluding customers who request an appointment after the 5 working days). | AT Training Offered | AT Training appointment confirmed and attended by Customer | >=95% | <=5 working days | 94%

## Slide 13: KPI Reporting Study Tech – March 2025 (3)
Commentary – Study Tech
KPI 12 - Is now split into two measures, Percentage of Calls Answered and Average Speed of Answer. Study Tech are performing above target on both measures after some recent improvement on the second measure..
KPI 15 - Above target on response time for complaints.
KPI 16 - No issues, target being met.
KPI 19 - No issues, target being met.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
12 | Minimum of 98% of call by customers to supplier being answered within 1 minute. | Inbound Calls PCA | Inbound Calls Percentage Calls Answered (PCA) | >=98% | Answered | 96%
15 | Minimum of 95% of complaints from customers must be investigated and responded to within 10 working days of receipt. | Complaints Handling | Customer Complaints Response Rate | >=95% | <=10 working days | 100%
16 | Monthly reporting must be compiled and submitted to SLC by the 5th working day of each month for the previous month. | Reporting | Monthly reporting compiled and submitted for the previous month | 100% | 5th working day of each month | 100%
19 | Availability of supplier systems supporting DSA must be greater than 99.9% at all times unless planned maintenance has been agreed outside of normal office hours. | Systems Availability | Technology Platform & Systems Uptime | >=99.9% | Available | 100%

## Slide 14: KPI Reporting Study Tech – March 2025 (4)
These KPIs are related to Customer Satisfaction that has already been covered on slide 5.
Both suppliers are performing above the 70% target across the three KPIs.
Please note, we are undertaking a 3-6 month KPI baselining period, which started in January 2025, to assess the KPIs following the initial performance of the service since February 2024. As part of this, we will consider potential iterations to ensure that they are as effective as possible.
KPI | Description of standard | Name | Description | Service Level | Target | Actual At 31 March
5 | Satisfaction with the Needs Assessment Service. | NA Experience (SLC report) | CSAT survey satisfaction score for sampled NAs completed | Overall Sat | >=70% | 81%
8 | Satisfaction with the Assistive Technology delivery, set up and customer service. | AT Equipment Experience (SLC Report) | CSAT survey satisfaction score for sampled NAs completed | Overall Sat | >=70% | 72%
11 | Satisfaction with the Assistive Technology Training delivery, set up and customer service. | AT Training Experience (SLC Report) | CSAT survey satisfaction score for Assistive Technology Training delivery and customer service | Overall Sat | >=70% | 82%

## Slide 15: Applications by disability type - SFE
 | 23/24 | 24/25 | 25/26 | Additional Detail | 24/25 | 25/26
Disability Type | % | % | % | Disability Type | % | %
Autism | 7.4% | 8.7% | 14.7% | Autism | 19.6% | 30.4%
Blind/Partial Sight | 0.9% | 0.9% | 1.0% | Blind/Partial Sight | 1.7% | 1.6%
Deaf/Partial Hearing | 1.3% | 1.3% | 1.9% | Deaf/Partial Hearing | 2.5% | 3.0%
SPLD | 31.3% | 27.6% | 23.1% | SPLD | 38.7% | 33.5%
Longstanding Illness | 13.2% | 13.4% | 13.8% | Longstanding Illness | 27.5% | 26.0%
Mental Health | 21.9% | 21.1% | 17.9% | Mental Health | 40.4% | 36.9%
Wheelchair/Mobility | 1.0% | 0.7% | 0.7% | Wheelchair/Mobility | 2.8% | 2.7%
Multiple Disabilities | 22.9% | 26.2% | 26.8% |  |  | 
Commentary
Disability Type trends change as the academic cycle progresses and the 25/26 is in its infancy. Of note, from 2023/24 to 2024/25:
Students presenting with Autism Conditions have increased by nearly 1.3%
Students presenting with SpLDs only have decreased by 3.7%
Students presenting with multiple disabilities have increased by 3.3%
Please note, the ‘Additional detail’ table shows the breakdown of disability type where more than one disability has been shared.
The table above (right side) shows the percentage of applications which have each disability type recorded against them. Students with multiple disabilities can appear here more than once, therefore the total percentage will exceed 100%.

## Slide 16: Applications by disability type - SFW
 | 23/24 | 24/25 | 25/26 | Additional Detail | 24/25 | 25/26
Disability Type | % | % | % | Disability Type | % | %
Autism | 9.6% | 11.0% | 21.2% | Autism | 17.1% | 32.3%
Blind/Partial Sight | 0.8% | 0.8% | 0.0% | Blind/Partial Sight | 1.7% | 1.0%
Deaf/Partial Hearing | 1.9% | 1.5% | 3.0% | Deaf/Partial Hearing | 2.6% | 5.1%
SPLD | 37.0% | 33.1% | 25.3% | SPLD | 40.7% | 38.4%
Longstanding Illness | 12.0% | 12.1% | 10.1% | Longstanding Illness | 23.2% | 16.2%
Mental Health | 19.9% | 20.9% | 16.2% | Mental Health | 34.7% | 28.3%
Wheelchair/Mobility | 1.0% | 1.0% | 4.0% | Wheelchair/Mobility | 3.2% | 4.0%
Multiple Disabilities | 17.9% | 19.6% | 20.2% |  |  | 
The table above (right side) shows the percentage of applications which have each disability type recorded against them. Students with multiple disabilities can appear here more than once, therefore the total percentage will exceed 100%.
Commentary
Disability Type trends change as the academic cycle progresses and the 25/26 is in its infancy. Of note, from 2023/24 to 2024/25:
Students presenting with Autism Conditions have increased by nearly 1.4%
Students presenting with SpLDs only have decreased by 3.9%
Students presenting with multiple disabilities have increased by 1.7%
Please note, the ‘Additional detail’ table shows the breakdown of disability type where more than one disability has been shared.

## Slide 17: Student Loans Company Stakeholder_Engagement@slc.co.uk www.gov.uk/slc