CSSF Annual Review (23/24)
# A. Summary Sheet
Programme Title	CSSF Terrorist Groups Strategic Communications (TGSC) Programme
Country and Region	Global
Programme ID	C-CTP-0011	IATI Unique ID	CSSF-01-000015
Start Date	1 April 2022	End Date	31 March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth and Development Office (FCDO) Communications Directorate (CD), Counter Terrorism Department (CTD) and Counter Terrorism Network (CTeN), Home Office (HO) and CONTEST Unit (CU) CT Portfolio Management Office (CTPMO), Ministry of Defence (MoD) and Cabinet Office (CO)
	Total overall Programme Allocation (over 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	£10,163,511	£3,972,000	£4,655,966.56
Non-ODA	£8,918,815	£2,073,000	£1,397,329.64
Total	£19,082,326	£6,045,000	£6,053,296.20

## Outputs
Output Statements	Individual Output Rating
Partners deliver relevant strategic communications that challenge and undermine Violent Extremism (VE) and effectively reach and resonate with audiences, using gender-sensitive approach.	3
Cell’s channels reinforce and promote complementary, coordinated messaging across the coalition and its allies.	4
Coalition and partner communications promote Global Coalition (GC) and partners, present alternative narratives, and negatively frame Da'esh's legacy and brand.	4
The Cell leads, coordinates and enables the GC and partners on strategic communications and is increasingly gender balanced.	3
Identified priority partners increasingly participate and lead (incl. co-chair) action groups and meetings, with gender balance and diversity.	4
Overall Rating of Output Delivery	3

## Outcomes
Outcome Statements
Resilience to radicalisation, Violent Extremist Organisations (VEO) narratives and recruitment strategies is increased in defined risk groups, and in new geographies of interest; VEO narratives are challenged in priority communities.
Target audiences in Iraq and Syria and West Africa support the Coalition as a valuable security partner and/or its local security partner.
Target audience have reduced confidence in Da’esh/VEO groups, their territorial legacy and leadership and believe they will face justice for their actions.
Support for legitimate governance and pluralistic communities strengthened in key geographies, and communities in Iraq and Syria accept the reintegration of al Hol returnees.
International cooperation on countering violent extremism (CVE) and Counter Terrorism (CT) related strategic communications and policy to support CT activities is strengthened and publics in coalition countries recognise their government's role in the counter-Da’esh mission.
Outcome Assessment	The achievement of the above five outcomes was on track, but there were some doubts or evidence regarding outcomes one and two. Even though outcome four, towards the reintegration of al Hol returnees still had some distance to go in the final year of this programme, in FY 23/24, after 18 months of no one returning home, 817 applied to leave and eighty-nine left, an excellent achievement jointly with other parts of the CSSF CT Portfolio. This proved that messages on returnees and support for the Global Coalition cut through, albeit in the face of Iran-aligned threat actors. Outcomes one and two faced challenges beyond the programme’s control due to increased anti-West sentiments in the region. The greatest success was in international cooperation with Global Coalition partners, outcome 5, including Arab and East African states as well as the US and advancing a gendered approach to strategic communications.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High (reputation, security)

## Summary of Programme Performance
Year	2021/22		2022/23		2023/24
	Output	Outcome	Output	Outcome	Output	Outcome
Programme Rating	3	Green	3	Amber	3	Amber
Risk Rating	High	High	High	High	High	High
Notes: The overall output rating of 3 reflects an average of how the TGSC programme worked in different geographies, Iraq being 4, Syria, Afghanistan and Kenya being 3 and Nigeria being 2.5.

## What Support Did the UK Provide in FY 23/24?
Various knowledge projects and subject matter expertise to the Global Coalition Against Da’esh, including support to Arab Ambassadors and the East African Caucus, key allies such as the US, and to all members via the Communications Working Group.
## Key Results for FY 23/24:
- Iraqi authorities changed their language, no longer calling for a withdrawal of coalition presence (as the Taliban had done in Afghanistan, leading to an abrupt departure that created space that terrorist groups have since occupied), instead supporting a transition towards a multilateral supportive role of the West. Although a subtle shift, this could be important in reducing the risk of back-sliding towards an Iraq where Da’esh can resurge. This is no small achievement, in pockets attributable to small volumes of TGSC programme work in Iraq.
- After the 7th of October 2023 Hamas attacks in Israel, tailored communications: reached an audience of 28 million; achieved 1.5 million engagements for Coalition Arabic Facebook (up from 120,000 in the quarter before); almost 1 million engagements for Coalition Instagram, reaching younger audiences; and secured 10,500 new Facebook followers, all in Iraq. This reduced the risk of escalation of conflict and the risk that Iraqis become radicalised by manipulation by Iranian-aligned militia groups.
- Enabled HMG politically and reduced the burden of CT on the UK tax-payer, by participating in the Global Coalition’s Communications Working Group and provided a leading role in enabling Global Coalition members, importantly the US, to work in a concerted and internationally coherent way to reduce the threat from terrorism from Da’esh in Iraq and Syria, al Qa’eda’s largest affiliate al Shabaab in Kenya and Somalia, and ISKP in Afghanistan. This included financial burden-sharing by Global Coalition partners.
Key Lessons:
- Campaigns and public communication designed to change the way target audiences think and behave are far more effective when they are coupled with on-the-ground activity, as, through this face-to-face interaction, alternative pathways away from the influence of terrorists can become less theoretical or abstract and more something that can be practically done by individuals taking their own life decisions.
- The face of terrorism changes dynamically. Various threats, from hostile state actors, diverse types of terrorist groups, organised criminal groups etc. can come together. What happens overseas impacts on the UK homeland and vice versa. There are means, such as cyber-attacks, generative artificial intelligence, lack of content control online etc. that can outpace the volumes of verified content humans, and HMG’s FY 23/24 TGSC programme, can make. HMG’s strategic communications capabilities must increasingly integrate with one another, to future-proof and build resilience in the UK’s strategic communications apparatus, to respond to complex terrorism in an increasingly multi-disciplinary way and to optimise value for money of HMG’s approach to CT-enabling strategic communications, whether under the mantle “CT” or not.
## Key Recommendations for FY 24/25:
- Portfolio-wide recommendation: Change the way UKISF governance is applied using results frameworks by having a single results framework for the entire UKISF CT Portfolio, of which the TGSC programme is one of eight tools in the toolbox, and using metrics to track performance over time that are more to do with the reduction of risk from terrorist threats faced in the UK homeland and UK interests, including British national tourists, overseas. By re-focussing and significantly reducing (by a factor of eight) the administration of the UKISF CT Portfolio and spending 5% of the total budget on reinforcing decentralised administrative and MEL capabilities in key theatres, those delivering the programme of work will be more able to work as a team of one to eight workstreams, depending on what’s needed, to tackle the same problems in a theatre against a terrorist group or in a country to drive down risk.
- TGSC-programme-specific recommendations:
  - Build resilience in the TGSC programme, preparing now for turnover of staff, so that institutional memory is not lost.
  - Link up overseas efforts to counter extremism efforts in the UK homeland to reduce extremism in society, exploring ways in which capabilities, including the UK’s strategic communications capabilities already versed in CT communication, such as the Counter Da’esh Communications Cell, can pivot and work with domestic counterparts so that capabilities are not duplicated, and knowledge is shared.