CSSF Annual Review/Programme Completion Review (23/24)
Programme Title	Lebanon CSSF Programme
Country and Region	Lebanon; Middle East and North Africa
Programme ID	C-MNA-0039	IATI Unique ID	CSSF-06-000040
Start date	April 2022	End date	March 2025
HMG Partners / (Lead department in bold)	Foreign, Commonwealth & Development Office (FCDO)
	Total overall Programme Allocation (e.g. 3 years)	Allocation FY2023/24	Spend FY 2023/24
ODA	Year 1: £8,180,000 Year 2: 10,058,234 Year 3: tbc	£10,058,234	£10,044,470
Non-ODA	Year 1: 8,220,000 Year 2: 9,577,500 Year 3: tbc	£9,577,500	£9,566,290
Total	Years 1-2: £16,400,000 ODA, £19,635734 non ODA.	£19,635,734	£19,610,760

Outcomes
Outcome statement(s)
Outcome Area 1: Lebanese Armed Forces (LAF) effectively contribute to maintaining Lebanon's external security along the border with Syria
Outcome Area 2: Internal Security Forces (ISF) and LAF effectively contribute to maintaining Lebanon's internal security and enhance interagency cooperation
Outcome Area 3: Vulnerable groups in flashpoint areas of Tripoli, Beirut and Palestinian camps are more resilient to extremist and violent narratives
Outcome Area 4: Address the root causes of gender inequality, instability and conflict, acknowledging that gender equality is integral to peace and security. ‘Improve Women’s Political Participation’ and ‘Supporting Women on Boards’
Outcome Assessment	Amber
Overall Outcome Progress Rating:	An excellent, well-integrated programme, delivered largely through trusted, locally based partners, providing a critical level of support to Lebanese security institutions in the face of huge political, economic and regional insecurity. Since the Hamas attacks in Israel on 7 October, the Lebanon programme largely remained unchanged and continued to deliver effectively, managing additional instability along the Lebanese southern border. Good level of progress on outcomes despite levels of tension. Outcomes 1 and 2 on maintaining security progressed in year. Improving interoperability is a newer element of support to this long-running work which has the potential to multiply impact (by freeing up the armed forces to focus on their core remit). Innovative concept of work on southern border could lead to outcome level change but will be dependent on political-security situation and decisions outside the realm of the programme. Progress on outcome 3 is strong in Tripoli and Beirut (the preventing radicalisation project should be applauded as a fantastic example of countering violent extremism) but more difficult to assess in Palestinian camps (and with drivers of extremism likely to rise). Delivery against outcome 4 is difficult given the broader approaches taken by the programme and the initial stages of gender-focussed projects, with mixed results to date. However, the programme should be commended for mainstreaming gender equality into all aspects of work and is on track to deliver impactful change within security institutions, as well as providing good support to local women’s rights and civil society organisations, addressing root causes of inequality and empowering women in the political sphere.
Overall Risk Rating:	Medium-High

Summary of Programme Performance
Year	2022/23		2023/24
	Output	Outcome	Output	Outcome
Programme Rating	4	Amber	4	Amber
Risk Rating		Medium-High		Medium-High

What Support Did the UK Provide in FY 23/24?
Support to the Lebanese Armed Forces (LAF) to maintain external security including training and mentoring of the LAF, delivered by UK and Lebanese trainers.
Support to the LAF and the Internal Security Forces (ISF) to manage internal security threats by improving intelligence-led policing and operations, improved coordination and interoperability between the LAF and ISF, and building ISF capability making use of improved technology against a backdrop of scarce resourcing due to the economic climate.
Work to reduce motivations towards extremist violence in particularly vulnerable communities (Tripoli, Beirut and Palestinian camps) providing alternative skills training and social/economic reintegration, plus community projects run by civil society organisations.
Work to address root causes of gender inequality including empowering women’s political participation and ability to run for office, capacity to deliver gender-inclusive development/community work, enabling women to be eligible to join Boards, and supporting a gender strategy for the LAF
Key Results for FY 23/24
The programme enhanced the capacity and capability of the LAF, through a ‘train the trainer’ approach also seeking to embed sustainability.  The programme also leveraged wider door support for the LAF.
In response to the events of 7 October, the programme expanded its border support to the LAF to include the Southern border. Specifically in the period being reviewed the team made a successful bid for funds and mobilised the support in-year with impressive efficiency.
The programme supported the ISF (Internal Security Forces) to establish six new Command and Control Centres, develop standard operating procedures, and continue training.
Tangible progress was also made towards strengthening the organisational resilience and efficiency of the ISF with consultations on resource optimisation and resilience completed and documented, steps taken to strengthen the academy curriculum, and a crisis response planning document produced in the period being reviewed. Six community safety initiatives were also implemented.
The preventing radicalisation project continued to evidence progress in supporting at risk youth in Tripoli and Beirut, with the shop in Beirut (selling products made in Tripoli) and ‘Love not War’ tour in Tripoli demonstrating how the programme is working to make the interventions sustainable.
The programme continued to strengthen community resilience in Palestinian Refugee Camps (PRCs) in Lebanon, including enhancing the capacity of the Palestinian Civil Defence emergency services in PRCs to provide first aid response and strengthened Civil Society Organisations (CSO) networks for inclusive community support.
The programme piloted a number of small gender-focussed projects, which will be continued in FY24-25.
Key Lessons:
Utilising UK expertise on security institution support as the long-running ‘core’ of the programme, and delivering through trusted, high-performing suppliers generates serious Political Access and Influence (PAI) for the UK while delivering against a key risk to further instability in Lebanon. PAI could be better captured particularly of senior embassy engagement.
Excellent programme team, in particular country-based staff, allow for high-risk appetite and long-term relationships with delivery partners to breed innovative ideas as projects mature and evolve, while planning for sustainability.
Key Recommendations for FY 23/24:
In planning for next iteration of programme, consider hooks into new areas of fragility (e.g. political and economic issues, maritime security, climate security etc.) to help diversify and future-proof the programme, against the context of long-running support to the LAF and ISF, supported by the evidence base of the Joint Analysis of Conflict and Stability (JACS) refresh.
Consider the effectiveness and relevance of GESI (Gender Equality Social Inclusion) specific projects, including how they could potentially be better integrated into the wider programme security lens.
If multi-year contracts are not pragmatic (or prove higher risk) for organisations with limited capacity, consider early procurement to allow for maximum delivery time in-year.
Refresh the Results Framework so outcomes and outputs fully align with the Theory of Change and are clearly delineated.
Complete the JACS to strengthen the evidence base, particularly in light of changing landscape, regional crises and direct future evidence-based programme design, including a climate consideration.
Consider how Political Access and Influence (PAI) can be better captured, especially with busy senior embassy staff
Consider minimum viability of security support needed to maintain UK access and influence in Lebanon, while considering long-term sustainability of work and if and when it would be appropriate to ‘taper off’ support. [At time of review, we do not suggest reducing support.]
Consider an assessment of the cumulative impact of long-term security support and seek to capture this – e.g. additional impact from longevity of support and depth of relationship. Draw on reviews done in similar environments.
Consider project champions across embassy, e.g. in pol-econ team.
Assess conflict sensitivity of all projects under programme, particularly those working in Palestinian camps and with vulnerable groups. If needed, support projects to improve their management and mitigation of associated contextual risks.