## 2025
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
GS/1680 | Cancelled |  | OPRED | UK SNS Transformation 3D | WesternGeco | 23/17 - 21; 23,25 and 29. 44/21-30 |  | 2024-03-25 | 2024-10-24 |  |  |  | 178 | not stated | Towed Streamer 3D Marine Seismic Survey in an area just south of the Dogger Bank shallows area in the UK Southern North Sea. The maximum survey area size is approximately 5,100sqkm. | 4.76 | 1090cu in |  | 0.017611 | #VALUE!
GS/1822/0 | Submitted |  | OPRED | POSTPONED: Rough Storage Geophysical Survey | Centrica Energy Storage Limited | 47/2, 47/3, 4/7 and 47/8 | See application | NEW DATES:Autum/winter 2025-2026 | NEW DATES:Autum/winter 2025-2026 |  |  |  | 11 | 3 | 2D high resolution (2DHR) seismic, ultra high resolution (UHRS) seismic, sub bottom profiler (SBP) pinger, single and multibeam echo-sounders, sidescan sonar, grab sampling and drop-down camera | 586 | 160 cu inch | winter | 2.1681 | 0.035543
MLA/2020/00489 | Approved |  | MMO | Sofia OWF UXO Sidescan sonar, multibeam echo sounder and magnetometer equipment | RWE Ltd |  |  | 2023-06-02 | 2028-05-31 | 2024-10-01 | 2028-05-31 |  |  | 0 | Geophysical Surveys | 133.37 |  | Summer | 0.49345 | 0
DCO/2013/00011 | Approved |  | MMO | Sofia OWF Piling - Monopile Installation | Sofia Offshore Wind Farm Limited |  |  | 2024-01-01 | 2025-10-30 | 2024-05-17 | 2025-05-31 |  |  | 56 | Piling abated | 871.58 |  | Summer | 3.2247 | 0.9868
DCO/2013/00011 | Approved |  | MMO | Sofia OWF Piling - Monopile Installation | Sofia Offshore Wind Farm Limited |  |  | 2024-01-01 | 2025-10-30 | 2024-05-17 | 2025-05-31 |  |  | 56 | Piling | 1928.38 |  | Summer | 7.1347 | 2.1833
MLA/2024/00088/1 | Completed |  | MMO | Hornsea 3 UXO removal - High Order (with bubble curtain) |  |  |  | 2025-04-01 | 2025-12-31 | 2025-04-01 | 2025-04-08 | 2025-04-08 | 0 | 0 | 1 High Order detonation per day | 707 |  | Summer | 2.62 | 0.04
MLA/2024/00088/1 | Completed |  | MMO | Hornsea 3 UXO removal - Low order | Orsted |  |  | 2025-04-01 | 2025-12-31 | 2025-04-01 | 2025-04-08 | 2025-04-08 | 8 | 8 | 1 Low Order detonation per day | 79 |  | Summer | 0.29229 | 0.012778
DCO/2018/00001 | Approved |  | MMO | East Anglia 3 Monopile Installation | Scottish Power Renewables |  |  | 2025-04-01 | 2026-01-01 | 2025-04-17 | 2026-01-01 |  | 70 | 70 | Piling (not abated) | 1927 |  | Both | 7.1296 | 2.7272
DCO/2018/00001 | Approved |  | MMO | East Anglia 3 Monopile Installation - abated | Scottish Power Renewables |  |  | 2025-04-01 | 2026-01-01 | 2025-04-17 | 2026-01-01 |  | 100 | 100 | Piling (abated). Total monopiles = 100, these will be a mixture of abated and unabated | 1520 |  | Both | 5.6238 | 3.0731
DCO/2018/00001 | Approved |  | MMO | East Anglia 3 Pin Piling | Scottish Power Renewables |  |  | 2025-04-01 | 2026-01-01 | 2025-07-03 | 2025-07-23 |  | 5 | 5 | Pin Piling | 706 |  | Both | 2.6121 | 0.071369
DCO/2023/00001 | Completed |  | MMO | Dogger Bank D | SSE Renewables |  |  | 2025-05-01 | 2025-05-31 | 2025-05-10 | 2025-05-12 | 2025-05-12 | 3 | 3 | Geophysical survey, still confirming.This is a provisional application that Dogger Bank D made licensing aware of, hiowever, the application has not been submitted yet. | 0.2 |  |  | 0.00073997 | 1.2131e-05
DCO/2016/00018 | Approved |  | MMO | Dogger Bank C Monopiling | SSE Renewables |  |  | 2025-04-23 | 2025-09-30 | 2025-04-23 | 2025-09-04 |  | 4 | 4 | Monopiling. 4 piles will overlap with SNS SAC | 150.7 |  |  | 0.55757 | 0.012187
GS/1853 | Completed |  | OPRED | Phase 1 NEP Survey | BP | 42/25, 42/30, 43/21, 43/26 |  | 2025-02-15 | 2025-04-20 |  |  |  | 30 | 20 | 2DHR seismic survey - SAC work may be completed outside of summer | 798 | 160 cu inch |  | 1.946 | 0.21268
GS/1852 | Submitted |  | OPRED | Expansion Seismic: Part 1 (CS07) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 33 | 31 | 3D Seismic survey, MBES, ADCP | 744 | 400 cu in | Summer | 2.753 | 0.5
GS/1866 | Submitted |  | OPRED | Expansion Seismic: Part 2 (CS25) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 18 | 18 | 3D Seismic survey, MBES, ADCP | 1473 | 400 cu in | Summer | 5.45 | 0.53607
GS/1872 | Approved |  | OPRED | EPCI 3 Geophysical/ Geotechnical (NEP Cable Nearshore) | BP |  |  | 2025-04-24 | 2025-05-01 |  |  |  | 40 | 121 | Sub-bottom profiler, Multibeam, Side scan sonar, Magnetometer |  |  |  | 0.45 | 0.29754
GS/1871 | Approved |  | OPRED | EPCI 3 Geophysical/Geotechnical survey (NEP cable Offshore) | BP |  |  | 2025-05-01 | 2025-06-30 |  |  |  | 40 | 121 | SBP/MB/SSS/Magnetometer. Potentially 2 full route runs (148km) in 24hrs) | 121 |  | summer | 0.44768 | 0.29601
| Approved |  | OPRED | Pegasus West:Pipeline and site Geophysical Survey (SBP) | Ineos |  |  | 2025-04-16 | 2025-05-05 |  |  |  | 12 | 12 | Sub Bottom profiler | 471 |  |  | 1.75 | 0.11475
DCO/2016/00020 | Approved |  | MMO | Dogger Bank C Pin Piling | SSE Renewables |  |  | 2025-04-01 | 2025-04-30 | 2025-04-01 | 2025-04-30 |  | 30 | 30 | Pin Piling |  |  |  | 0 | 0
DCO/2016/00024 | Completed |  | MMO | Dogger Bank B - Piling | SSE Renewables |  |  | 2025-04-16 | 2025-05-31 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 2 | 2 | Contingency piling of 2 piles - provision in case delays in programme | 2873 |  | Both | 10.6297 | 0.11617
DR/2500/2 | Approved | 21/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a-AAF well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-03-31 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | 2.62 | 0.014317
DR/2528/0 | Approved | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- AJ well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-03-31 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2532/0 | Approved | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 1 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-03-31 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2533/0 | Approved | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 6 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-03-31 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
GS/1913 | Submitted |  | OPRED | NEP EPCI 1 Pipeline UXO Survey Offshore | BP | Various |  | 2025-07-01 | 2025-10-01 |  |  |  | 47 | 18 | Geophysical UXO survey utilising SBP, SSS, MBES and magnetometer. | 99 |  | Both
GS/1912 | Submitted |  | OPRED | NEP EPCI 1 Pipeline UXO Survey Nearshore | BP | 40/15 |  | 2025-07-01 | 2025-10-01 |  |  |  | 26 | 0 | Geophysical UXO survey utilising SBP, SSS, MBES and magnetometer. | 0 |  | Both | 0.366 | 0.036
GS/1867 | Submitted |  | OPRED | Expansion Seismic (NEP Expansion stores) | BP | Various |  | 2025-08-01 | 2025-10-17 |  |  |  | 51 | 51 | 400 cubic inches (cu. in) source array | 1473 | 400 cubic inches | Summer | 0.536 | 1
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be 2025 or 2024?
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would be 4.62 - it’s measuring against the summer area here
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would be 0.08
Note on T10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Works completed - no HO was needed so either this row can be removed or threshold contributions need to be adjusted.

## 2026
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed |  | MMO | Hornsea Three Monopiling | Orsted |  |  | 2026-01-01 | 2027-01-01 | [5 empty] | Piling |  |  | Summer
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be 2025 or 2024?