## 2025
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
GS/1680 | Cancelled |  | OPRED | UK SNS Transformation 3D | WesternGeco | 23/17 - 21; 23,25 and 29. 44/21-30 |  | 2024-03-25 | 2024-10-24 |  |  |  | 178 | not stated | Towed Streamer 3D Marine Seismic Survey in an area just south of the Dogger Bank shallows area in the UK Southern North Sea. The maximum survey area size is approximately 5,100sqkm. | 4.76 | 1090cu in |  | 0.017611 | #VALUE!
GS/1822/0 | Submitted |  | OPRED | POSTPONED: Rough Storage Geophysical Survey | Centrica Energy Storage Limited | 47/2, 47/3, 4/7 and 47/8 | See application | NEW DATES:Autum/winter 2025-2026 | NEW DATES:Autum/winter 2025-2026 |  |  |  | 11 | 3 | 2D high resolution (2DHR) seismic, ultra high resolution (UHRS) seismic, sub bottom profiler (SBP) pinger, single and multibeam echo-sounders, sidescan sonar, grab sampling and drop-down camera | 586 | 160 cu inch | winter | 2.1681 | 0.035543
MLA/2020/00489 | Approved |  | MMO | Sofia - Unexploded Ordnance Investigations (Sidescan Sonar, Multibeam Echo Sounder and Magnetometer Equipment) | RWE Ltd |  |  |  |  | 2024-10-01 | 2028-05-31 |  |  | 0 | Geophysical Surveys | 133.37 |  | Summer | 0.49345 | 0
DCO/2013/00011 | Approved |  | MMO | Sofia - Monopile Installation (Abated) | Sofia Offshore Wind Farm Limited |  |  |  |  | 2025-04-02 | 2025-09-01 |  |  | 56 | Piling abated | 871.58 |  | Summer | 3.2247 | 0.9868
DCO/2013/00011 | Approved |  | MMO | Sofia - Monopile Installation (Unabated) | Sofia Offshore Wind Farm Limited |  |  |  |  | 2025-04-02 | 2025-09-01 |  |  | 56 | Piling | 1928.38 |  | Summer | 7.1347 | 2.1833
MLA/2024/00088/1 | Completed |  | MMO | Hornsea Three - Landfall Horizontal Directional Drilling Unexploded Ordnance Clearance (High Order with Bubble Curtain) | Orsted |  |  |  |  | 2025-04-01 | 2025-04-08 | 2025-04-08 | 0 | 0 | 1 High Order detonation per day | 707 |  | Summer | 2.62 | 0.04
MLA/2024/00088/1 | Completed |  | MMO | Hornsea Three - Landfall Horizontal Directional Drilling Unexploded Ordnance Clearance (Low Order) | Orsted |  |  |  |  | 2025-04-01 | 2025-04-08 | 2025-04-08 | 8 | 8 | 1 Low Order detonation per day | 79 |  | Summer | 0.29229 | 0.012778
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Monopile Installation (Unabated) | Scottish Power Renewables |  |  |  |  | 2025-04-17 | 2025-09-30 |  | 70 | 70 | Piling (not abated) | 1927 |  | Both | 7.1296 | 2.7272
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Monopile Installation (Abated) | Scottish Power Renewables |  |  |  |  | 2025-04-17 | 2025-09-30 |  | 100 | 100 | Piling (abated). Total monopiles = 100, these will be a mixture of abated and unabated | 1520 |  | Both | 5.6238 | 3.0731
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Pin Pile Installation | Scottish Power Renewables |  |  |  |  | 2025-07-03 | 2025-07-23 |  | 5 | 5 | Pin Piling | 706 |  | Both | 2.6121 | 0.071369
DCO/2023/00001 | Completed |  | MMO | Dogger Bank D - Geophysical Survey 1 | SSE Renewables |  |  |  |  | 2025-05-10 | 2025-05-12 | 2025-05-12 | 3 | 3 |  | 0.2 |  |  | 0.00073997 | 1.2131e-05
DCO/2016/00018 | Approved |  | MMO | Dogger Bank C Monopiling | SSE Renewables |  |  |  |  | 2025-09-02 | 2025-09-04 |  | 4 | 4 | Monopiling. 4 piles will overlap with SNS SAC | 150.7 |  |  | 0.55757 | 0.012187
| Proposed |  | OPRED | Anglia P&A 2 X wells | Ithaca |  |  | 2025-04-01 | 2025-10-31 | [5 empty] | Downhole wellbore perforation for well abandonment. Need more information but if an EDR is required it will be 5km |  |  |  | 0 | 0
GS/1853 | Completed |  | OPRED | Phase 1 NEP Survey | BP | 42/25, 42/30, 43/21, 43/26 |  | 2025-02-15 | 2025-04-20 |  |  |  | 30 | 20 | 2DHR seismic survey - SAC work may be completed outside of summer | 798 | 160 cu inch |  | 1.946 | 0.21268
GS/1852 | Submitted |  | OPRED | Expansion Seismic: Part 1 (CS07) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 33 | 31 | 3D Seismic survey, MBES, ADCP | 744 | 400 cu in | Summer | 2.753 | 0.5
GS/1866 | Completed |  | OPRED | Expansion Seismic: Part 2 (CS25) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 18 | 18 | 3D Seismic survey, MBES, ADCP | 1473 | 400 cu in | Summer | 5.45 | 0.53607
GS/1872 | Approved |  | OPRED | EPCI 3 Geophysical/ Geotechnical (NEP Cable Nearshore) | BP |  |  | 2025-04-24 | 2025-05-01 |  |  |  | 40 | 121 | Sub-bottom profiler, Multibeam, Side scan sonar, Magnetometer |  |  |  | 0.45 | 0.29754
GS/1871 | Completed |  | OPRED | EPCI 3 Geophysical/Geotechnical survey (NEP cable Offshore) | BP |  |  | 2025-05-01 | 2025-06-30 |  |  |  | 40 | 121 | SBP/MB/SSS/Magnetometer. Potentially 2 full route runs (148km) in 24hrs) | 121 |  | summer | 0.44768 | 0.29601
| Proposed |  | OPRED | VSP on appraisal well (x2) (Winter) | BP |  |  | 2025-10-01 | 2026-04-01 | [5 empty] | BC39 & 37 appraisal wells drilling - vertical seismic profiling. High degree of uncertainty on dates. It is assumed unlikely that any wells drilling will commence in the summer season. BC37 outwith SNS SAC. | TBC |  |  | 0 | 0
| Proposed |  | OPRED | Possible UXO clearance at NEP (unlikely to be in summer) | BP |  |  | TBC | TBC | [5 empty] | UXO clearance - NEP pipeline and cable routing and infield. Requirements for UXO clearance determined through EPCI 1-3 surveys undertaken in March-June 2025. It is assumed unlikely that any UXO clearance would commence within the summer window. It is however feasible that UXO clearance may commence towards the back end of the summer season, however the preference would be to complete these works during the winter season. |  |  |  | 0 | 0
| Completed |  | OPRED | Pegasus West:Pipeline and site Geophysical Survey (SBP) | Ineos |  |  | 2025-04-16 | 2025-05-05 |  |  |  | 12 | 12 | Sub Bottom profiler | 471 |  |  | 1.75 | 0.11475
DCO/2016/00020 | Approved |  | MMO | Dogger Bank C - Pin Piling | SSE Renewables |  |  | 2025-04-01 |  | 2025-04-01 | 2025-04-30 |  | 30 | 30 | Pin Piling |  |  | Summer | 0 | 0
DCO/2016/00024 | Completed |  | MMO | Dogger Bank B - Monopiling (Unabated) | SSE Renewables |  |  |  |  | 2025-04-16 | 2025-04-17 | 2025-04-17 | 2 | 2 | Contingency piling of 2 piles - provision in case delays in programme | 2873 |  | Both | 10.6297 | 0.11617
DR/2500/2 | Completed | 21/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a-AAF well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | 2.62 | 0.014317
DR/2528/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- AJ well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2532/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 1 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2533/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 6 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
GS/1913 | Submitted |  | OPRED | NEP EPCI 1 Pipeline UXO Survey Offshore | BP | Various |  | 2025-07-01 | 2025-10-01 |  |  |  | 47 | 18 | Geophysical UXO survey utilising SBP, SSS, MBES and magnetometer. | 99 |  | Both
GS/1912 | Submitted |  | OPRED | NEP EPCI 1 Pipeline UXO Survey Nearshore | BP | 40/15 |  | 2025-07-01 | 2025-10-01 |  |  |  | 26 | 0 | Geophysical UXO survey utilising SBP, SSS, MBES and magnetometer. | 0 |  | Both | 0.366 | 0.036
GS/1867 | Submitted |  | OPRED | Expansion Seismic (NEP Expansion stores) | BP | Various |  | 2025-08-01 | 2025-10-17 |  |  |  | 51 | 51 | 400 cubic inches (cu. in) source array | 1473 | 400 cubic inches | Summer | 0.536 | 1
GS/1900/0 | Submitted |  | OPRED | Baker and Abbey site Surveys (SBP) | Petrogas | Various |  | 2025-07-01 | 2025-12-01 |  |  |  | 2 | 2 | Sub Bottom profiler survey | 12 |  | Both | 0.044398 | 1 | Winter Area | 143km | Proportion of Winter area | 1.13%
MLA/2023/00532/3 | Approved |  | MMO | East Anglia THREE - UXO Clearance | Scottish Power Renewables |  |  | 2024-04-01 | 2025-06-14 | 2024-07-08 | 2025-04-12 |  | 3 | 3 | High-Order UXO Clearance | 707 |  | Both | 5.57 | 0.09
MLA/2023/00532/3 | Approved |  | MMO | East Anglia THREE - UXO Clearance | Scottish Power Renewables |  |  | 2024-04-01 | 2025-06-14 | 2024-07-08 | 2025-04-12 |  | 73 | 73 | Low-Order UXO Clearance | 79 |  | Both | 0.62 | 0.25
MLA/2024/00345 | Approved |  | MMO | Norfolk Vanguard West - UXO Investigation Marine Licence Application 1 | RWE Ltd |  |  |  |  | 2025-01-01 | 2025-12-31 |  | 365 | 365 | Geophysical Survey | 0.00051 |  | Both | 0 | 0
MLA/2024/00419 | Approved |  | MMO | Norfolk Vanguard West - Unexploded Ordnance Investigations Marine Licence Application 2 | RWE Ltd |  |  |  |  | 2012-01-29 | 2026-01-29 |  | 365 | 365 | Geophysical Survey | 0.000156 |  | Both | 0 | 0
N/A (exemption) |  |  | MMO | National Grid - Electricity Transmission Geophysical Survey | National Grid |  |  |  |  | 2025-05-01 | 2025-05-31 |  | 11 | 11 | Geophysical Survey | 55 |  | summer | 0 | 0
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be 2025 or 2024?
Note on T6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would be 4.62 - it’s measuring against the summer area here
Note on U6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would be 0.08
Note on T10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Works completed - no HO was needed so either this row can be removed or threshold contributions need to be adjusted.
Note on A36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added by Sophia 19/06/2025
Note on A37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added by Sophia 19/06/2025

## 2026
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed |  | MMO | Hornsea Three Monopiling | Orsted |  |  | 2026-01-01 | 2027-01-01 | [5 empty] | Piling |  |  | Summer
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be 2025 or 2024?