SLC DSA Quality Committee
Note to Cascade
Wednesday 5th February 2025

DSA Reforms update
The full commercial framework went live on 18th November 2024. Capita experienced a system issue at this time. This was remediated as quickly as possible, and full service resumed by 10th January.

The next phase of the DSA Service improvements is on track. From 28th March customers will only need to submit medical evidence once. Further customer journey enhancements will follow during the 2025/26 financial year.

Operational performance and CSAT update
SFE application volumes and applications approved as eligible were higher year-on-year (YoY). Volumes of students with support in place are tracking behind YoY figures, but progress has been made to mitigate the system issue encountered by Capita. Approximately 14-15k applications have still to be received. Applications and Needs Assessment Reports (NARs) are being handled within 7 days, and efforts to improve the speed of the customer journey will continue.

SFW applications are tracking closely YoY, with application volumes slightly ahead. Some extended wait times were impacted by Capita’s system issue.

The Customer Satisfaction (CSAT) survey has now received c.1100 responses, which is a response rate of 4% and is consistent with other SLC customer surveys. CSAT scores continue to trend higher than pre-DSA reforms levels. NA satisfaction levels remain high, but there has been a decline due to some extended wait times.

Members reported student challenges in navigating the complaints process and confusion around how and where to complain. SLC recently reviewed the complaints handling process and will provide further information.

Capita’s performance has steadily improved since their system issue. All impacted customers were contacted and all new NAs have now been either completed or booked. Members discussed potential workarounds for any similar future outages. The average wait time for an NA appointment during the outage was 42 days, and this has since been reduced to 21 days, with NA resources continuing to increase.

Capita’s processing figures have been consistently improving since the resolution of its system issue which also impacted their Assistive Technology (AT) training to a lesser degree.

Study Tech’s performance is also seeing significant improvement. SLC is reviewing pending NARs for both suppliers to understand why they are pended and to introduce improvement actions.

SLC approach to reviewing KPIs
The KPI’s are currently being baselined, and SLC will engage with the committee on potential iterations to ensure they are effective as possible in delivering an improved customer experience. The KPI review will allow SLC to identify any unintended consequences and any necessary adjustments, the need to introduce or retire any KPIs, and to verify the quality of NAs via mystery shoppers or side by side observation. Any suggestions from members would be welcome. Any recommendations on future changes will be shared with members for their input. Should poor quality be identified before then, measures will be taken immediately to update KPIs, and SLC will not wait until the end of the baselining period to implement any relevant changes.

Review of ToRs
The key points of the ToRs are:
1. Membership
2. Agenda
3. Frequency of meetings
4. Actions log/plan

Member feedback
- A widening of current membership would help to distribute the responsibility of the Committee across the sector. More active engagement from other bodies directly supporting students was recommended. Members must have no commercial interest in DSA.
- Suggestions for future agenda items included complaints.
- The current frequency of meetings (2-4 annually) seemed appropriate to members, but this can be flexed as needed.
- The actions log/plan is a measure of success and will become more forward-looking to measure progress over time.

AOB
While NAs are not wanted by all students, there are no plans to implement set packages in the short term. A pilot of c.50 students is being considered but will be restricted to cohorts with a high degree of consistency in recommendations, such as SpLDs (Specific Learning Difficulties). Not having an NA would always be optional and the student would continue to have the choice to have one at a later date, and SLC would follow and support them throughout their journey.

Next meeting date: 8th May 2025