## Detailed Plan
Last Updated: 10.07.25
Work Strand |  |  | July - November 2025 |  |  | December 2025 - March 2026
| Date added to priorities table |  | TIER 1 - Committee and Government top priorities and active work strands
No. |  | Policy Area | 14 July 2025 | 6 October 2025 | 3 November 2025 | 1 December 2025 | 2 February 2026 | 2 March 2026
1 | 2024-06-01 | Unregulated Experts | A brief update will be provided following the recent consultation which closed in June 2025 under Matters Arising. Due to the high volume of responses, full analysis is underway and a more substantive update will follow in October 2025. | A substantive update following the analysis of the consultation responses is expected in October 2025
2 | 2022-12-01 | Parental Responsibility and Child Arrangements following imprisonment for murder of the other parent (Jade's Law). | An substantive update will be provided in July
3 | N/A | Private Law Reform - Pathfinder PD36Z (current expiry date 31 March 2026) | Agreement will be sought on amendments to the PD to come into force in August. |  | Minor PD amendment expected to include start date for the courts in Hampshire and the Isle of Wight | Further amendments to the PD are expected following a review of the operating model from July-November
4 | 2023-07-01 | Modernisation of PD27A. | Post-consultation feedback to the Committee, with a revised draft PD27A, will be provided in July. | Subject to planning discussions, draft guidance for the public may be provided to the Committee.
Tier 2: Substantive Items
5 | 2024-12-24 | Financial Remedy: Transparency Orders | Policy to take this forward in Summer 2025.
6 | 2020-11-01 | Deed Poll Name Changes | No update expected. | An update on the progress is expected in the October meeting.
7 | 2022-07-01 | Police Disclosure Orders: the 2024 Protocol and template order for police disclosure | HHJ Wright and Mrs Justice Knowles have discussed the Annex 5 template. It was agreed that Mrs Justice Knowles will review the Annex 5 template further.
8 | 2024-04-01 | Financial remedies after overseas divorce. Proposed amendments to: - FPR 28.3(4)(b)(ii)-(iii) to exclude applications under s.13 of the 1984 Act and paragraph 4, Sch.7 of the 2024 Act (AS v RS) - Part 8 to reflect the Potanina decision (removal of r.8.25) | This item was triaged in April 2024, and two related items were combined into a single workstream. The priority level will be reviewed in Summer 2025. Work on this item will resume when capacity allows.
9 | 2024-04-01 | Interim maintenance application (FPR 9.7) : proposal to amend to prescribe what information the respondent must file | There is currently no work being carried out on this item. Item was triaged in April 2024 and the Committee agreed to add it in tier 2. Priority level to be reviewed in Summer 2025.
10 | 2024-12-01 | Amendments to PD12J and PD12B on disclosure of findings of facts pertaining to domestic abuse | The Committee agreed in December 2024 for this item to be added to the Priorities List following a triage.
11 | 2025-02-03 | Form E - proposal to amend form to include details of pre-marriage or pre-civil partnership Cohabitation | The Committee agreed in February 2025 for this item to be added to the Priorities List following a triage. There is currently no work being carried out on this item.
12 | 2024-05-01 | Applications for permission to revoke a placement order (G v H) | An update is provided in July under Matters Arising.
13 | 2022-10-01 | Case Management and Intimate Images | This item is currently paused due to other priorities.
14 | N/A | Review of provisions relating to disclosure of information from proceedings (including Practice Direction 12G and PD14E). | A substantive item is provided in the July meeting
15 | N/A | Online C100: PD36G and Private Law Portal: PD36ZD (current expiry date 31 March 2026) | PD36ZD: proposals in respect of birth certificates in parental order cases were put to March meeting. These will be included in the next PD Update.
16 | 2024-05-01 | Review of PD12J (domestic abuse) | Update is expected after the summer recess. | MoJ is drafting amendments to PD12J with DAWG input. Depending on the progress made with the DAWG an update on the proposals is expected during the October meeting.
17 | 2025-07-01 | Contested financial remedy online: provision for litigants in person (PD41H) |  | Paper proposing amendments in relation to uploading of documents to the Portal by litigants in person will be submitted to the October meeting.
Tier 3: Work with timings listed as TBC or with longer timescales
18 | 2023-12-01 | Single Lawyer Models. | No current activity
19 | N/A | Review of the overriding objective, to include consideration of amendments relating to vulnerable parties and witnesses (FJC Report). | This workstream is not currently being progressed so an end date cannot be predicted.
20 | N/A | Opposite sex civil partnerships Implementation: consequential amendments to the FPR 2010. | Pending GEO input - timeline to be confirmed
21 | 2024-04-01 | Pension Sharing Orders. | Item was triaged in April 2024 with agreement it will be allocated to Tier 3. This will include responding to the recommendations made by the Pensions Advisory Group. It will return to the Committee when capacity permits.
22 | 2024-04-01 | Enforcement of Financial Remedy orders. | Item was triaged in April 2024 with agreement it will be allocated to Tier 3. This will include reviewing Rule 33.4(3) following the Gladwell v Gladwell judgment (2019). It will return to the Committee when capacity permits.
23 | 2022-12-01 | Closed Material Proceedings (CMP) | The Committee agreed for this item to be paused whilst amendments to CMP are being made in Civil. MoJ colleagues would also require cross-department agreement before FPR amendments can be made.
24 | 2024-05-01 | Disclosure of electronic records | This was triaged in May 2024 and the Committee agreed it should remain at tier 3.
25 | 2023-10-01 | Deprivation of Liberty: amend the C66 application form and reviewing mechanisms on orders | This item was added following a report from the Nuffield Family Justice Observatory published in 2023. The Committee will receive a substantive update in July.
26 | 2024-02-01 | Cape v Dring implications | Update provided at the May 2025 meeting. Committee agreed to form a small Working Group to explore third-party disclosure and confidentiality. Working Group has now been set up.
27 |  | Relationship between rules, PDs and guidance.
28 | 2024-05-01 | Committal proceedings: 'Esper' judgment : amend to ensure consistent with CPR and CoPR | This item was triaged in May 2024 where the Committee agreed it should be added to the Priorities Table in tier 3. It will return to the Committee when capacity permits.
29 | 2024-06-01 | Abduction: The role of a solicitor-guardian under FPR 16.6(1): consideration in light of Re D and CvM | This item was triaged in June 2024 and the Committee agreed it should be added to the Priorities Table under tier 3.
30 | 2025-02-03 | Communications with the Court (FPR 5.7(1) and 18.5(1) : proposal to amend to require "contemporaneous" filing and service | This item was triaged to Tier 3 on 3 Feb 2025. The end date cannot be determined at present.
31 | N/A | PD36ZE (local flexibilities) current expiry date 28 February 2026 | Throughout 2024 officials continued to investigate the impacts of PD36ZE. An update was provided at the December 2024 meeting and the Committee approved a two-year further extension. Matter to return to Committee in due course to established whether a permanent implementation is appropriate.
32 | N/A | Justice Legal Adviser Powers | MoJ policy has also met with HHJ Suh to discuss legal adviser powers in public law cases and potential improvements to the public law file allocation system. This work is in the early stages and is not yet ready for triaging.
33 | 2025-02-03 | D81 Form - Costs : amend to add section requesting information about costs incurred | This item was triaged to Tier 3 on 3 Feb 2025. The end date cannot be determined at present.
34 | N/A | PD12I (transparency) | Proposal to amend to reference Press Association's Media Injunctions Alert Service. Timing TBC.
35 | 2025-04-01 | Special Measures and Screens | This item was triaged to Tier 3 on 7 April 2025. The end date cannot be determined at present.
Tier 4: Update only - these items will be monitored , with updates provided to the Committee, but do not currently involve active policy development
36 | N/A | Web Updates (inaccuracies on Justice.gov.uk). | Web updates are reviewed by the FPRC Secretariat on an ongoing basis
37 | 2025-02-01 | Qualified Legal Representatives | Updates may be provided if needed.
38 | 2021-02-01 | Mediation Vouchers (Pilot PD). | A verbal update is scheduled for the July meeting. |  | An update is expected in November.
39 | 2022-07-01 | Private Law Demand (Early Resolution) | At the June meeting a Sub-group name change was proposed and is now under consideration. Policy lead is following up with Mr Justice Peel on standard orders and recitals. An update is expected in due course.
40 | 2022-10-01 | Domestic Abuse Protection Orders | Update was provided at the FPRC May 2025 meeting. Further update will be provided when there is a ministerial decision on the next steps.
41 | 2024-02-01 | Disclosure of Respondent's Contact Details | Draft rule amendments to rule 29.1 FPR previously approved. Will be included in SI when HMCTS confirm IT readiness - likely to be considered Spring 2026.
42 | 2022-07-01 | Permission to Appeal | Provision in respect of PTA from decisions of lay justices agreed at previous meeting. To be included in the upcoming FPR amending SI and accompanying PD Update.
43 | Ongoing | Forms Working Group (standing forms update with table of work). | The last meeting was in April. Amendments to Form C100 and C1 were agreed in May. Digital updates expected in early 2026. Form E amendments are expected to be reviewed over summer 2025. Members agreed to prepare an initial paper for judicial submission. Update due October 2025.
44 | N/A | Fast Track Procedure – financial remedy applications. | The PD came into force 7 April 2025.
45 | N/A | PD36ZA: North Yorkshire pilot for notification of Part 4 Family law Act 1996 orders: current end date 28 February 2026 | Amendments to PD36ZA and a new linked PD36ZI (on Notification of Non-Molestation Orders) were considered and approved at the June 2025 meeting. An update on the pilot is expected in Autumn 2025.