Public Service Delivery Review Board minutes of meeting

Meeting date: 12 March 2025, hosted remotely via Microsoft Teams.
Attended: Patrick Kiernan (GDS), Sadia Siema (GDS), Sulaiman Saaed (GDS), Ebru Yilmaz (GDS), Julian Firth (GDS), Mark Brewin (HMRC), Stephen Mak (MHCLG),, Mark Williams (LGA), Louise Greenrod (DHSC)
Observers: Daniel Barnett (ICO), Sarah Lawrence (ICO) Alessia Morris (Scottish Government), Anna Bartlett-Avery (Welsh Government), Gerry Thompson (NI)
Speakers: Charlotte Sewell (DESNZ), Anna Carlini (DESNZ), Suzannah Brookner (DESNZ), Lara Weller (DESNZ), Tulika Gupta (DESNZ), Gareth Harvey (DESNZ) and Sophie Leigh
Apologies: Rhian Jones (GDS), Andy Gregory (HO), Helen Walker (DWP), Vicky Chico (NHSX), ,

1	Welcome and introduction from the Chair
1.1	Members were welcomed by Patrick Kiernan, deputising for the chair.
2	Conflicts of interest, minutes, and actions brought forward
2.1	Mark Brewin (HMRC) and Stephen Mak (MHCLG) noted a potential conflict of interest regarding the presentation to be covered later in the meeting as the proposal may involve data from HMRC and MHCLG.
2.2	Minutes from the last meeting 26 September 2024 were approved.
2.3	The following action points were closed: / Action point 77: Secretariat to meet with HMRC to discuss further how the PSD power could support the sharing of VAT data. / Action point 78: Secretariat to liaise with WG and DFE to expand the territorial application of the FSM proposal. / Action point 79: Secretariat to issue FSM proposal form via email. / The following action points are ongoing: / Action point 74: UKSA requested to discuss aligning the updates to the Research and Statistics Codes. / Action point 75: Secretariat to include SM when meeting with the resilience and recovery directorates. / Action point 80: Secretariat to review comments raised on the data sharing register
3	Work programme update
3.1	Amendments to section 38 / Members were informed of an amendment made to section 38 of the DEA via the Water (Special Measures) Act 2025. The Secretariat will continue to support DEFRA in their use of the water poverty powers.
3.2	OFGEM fuel poverty: The secretariat noted that it is engaging with Ofgem and DESNZ at pace to identify how the DEA’s fuel poverty powers could support the delivery of Ofgem’s Debt Relief Scheme.
3.3	Education related passported benefits proposal / Members were informed that the secretariat has been engaging with DfE and the Devolved Administrations of Scotland and Wales to assess the desire to expand the scope of the existing Scottish proposal that was approved by the board in September. The discussions are focussed around introduction of a more comprehensive list of education related benefits and expansion of the territorial application to maximise benefit, delivering on government's commitment to removing barriers to opportunity. / Current benefits identified to be included in the objective include: free school meals (England, Scotland and Wales); pupil premium and related deprivation funding (England), school clothing grants (Scotland), education maintenance allowance (Scotland) and school essentials grant (Wales).
3.4	Businesses objective proposal / Members heard an update on the progression of the Data Use and Access Bill through Parliament and current work that is being undertaken to develop objectives that will provide a benefit to businesses. / ACTION POINT 81: Secretariat to further explore opportunities to share data to support the home buying process review.
3.5	Members were informed that a review of the Public Service Delivery powers for 2023/2024 was submitted to the Minister.
3.6	Northern Ireland commencement / The Secretariat continues to work with colleagues in the Department of Finance (Northern Ireland) on commencing chapters 1, 3 and 4 and identifying which Public Authorities in Northern Ireland would need to be added to the schedules to share data using existing data sharing objectives.
4	Presentation: Energy Efficient Homes Consumer Advice & Information
4.1	Members heard a presentation from the Consumer Advice & Information team in DESNZ. The presentation focussed on access to information could aid in improving energy efficiency and deliver a better service to individuals on the support available to upgrade their homes and reduce energy bills. / The team welcomed comments from the Review Board and will work to address these comments in a formal proposal.
5	AOB
6	DONM 18 June 2025 2 - 4pm