SLC Disabled Student Stakeholder Group	18th June 2025

DSA Transformation Programme update
The next phase of the DSA Transformation Programme was Customer Journey Enhancements. API (Application Programming Interface) had been in place with both suppliers since the end of May.

The scope of Customer Journey Enhancements included provision of online applications for all customers, clearer and more tailored information on student accounts to replace DSA award letters (which would still be available if the student preferred), an online tracker, secure messaging, and the capability to upload evidence.

HEPs would still be notified of the student’s DSA award, with more tailored DSA award letters for the HEP and the supplier. A portal for HEPs was a longer-term objective.

The set packages of support pilot was proceeding as planned, and would run separately from September. Students would continue to have the option of a full assessment at this stage or in future. The pilot parameters and duration were still being defined. DSSG members would receive the pilot findings, an outline of the process, and feedback at the earliest opportunity. Customers would also complete a Needs Assessment (NA) afterwards for comparison of the set package recommendations and needs.

DSA Customer Experience and Operational update
Messaging to encourage early applications had been successful, with current application volumes for SFE 16% higher year-on-year (YoY) and volumes of approved support 58% higher YoY. SFW application volumes were 7% higher YoY and approved support 5.8% higher YoY.

Capita and Study Tech were fulfilling KPIs (Key Performance Indicators) pertaining to the offering of NA appointments. NA appointments were being offered in 1 to 3 days but student choice was pushing the average time for booking to 13 days. Remote assessment continued to be the preferred format among many students, as was the case under the previous model and during the pandemic.

CSAT (Customer Satisfaction) scores were 7% higher YoY but 6% lower than in September 2024. The 4% response rate from 25/26 customers aligned with other CSAT surveys across SLC. Most 25/26 themes were tracking behind 24/25 scores but an upward trend was expected as 25/26 responses were submitted.

Department for Education update
DfE had published an SSIN on changes to funding for spelling and grammar software since the last meeting. Funding for non-specialist spelling and grammar software could be funded via DSA in exceptional circumstances.

DSA travel guidance had been reviewed recently and would be published soon.

DSA Quality Committee and DSA Ops Group readouts
The DSA Quality Committee received updates on the DSA Transformation Programme, KPIs, and DSA Complaints at their May meeting.

The DSA Ops group met in March and May, receiving updates on service performance, the impact of processing delays and interim support, and the closure of Non-Medical Help Provider, Diversity and Ability (D&A). They discussed cases of DSA being exhausted, specifically for BSL (British Sign Language) support. Following a successful pilot with Uber for taxi service, this would be extended in areas where Uber was already available.

AOB
BSL provision
Concerns raised in the ANMHP BSL sub-group around BSL provision were raised with members. Student concerns pertained to difficulties in securing a consistent quality service and a joined-up approach to liability for excess costs. This was not unique to HI (hearing impaired) students, and the issue was to an extent one of policy but also operational. Issues around the balance of availability and consistency of provision were raised.

DfE welcomed any additional evidence.

Next meeting: 16th October 2025