Steering Board Meeting Note
Date: Thursday 19 September 2024
Time: 10:00-15:15
Location: Concept House, Newport, B3

Attendees:

Chair: Harry Rich

Steering Board Members: Andy Bartlett (Deputy CEO), Laurie Benson, Harriet Kelsall, Andrew Lawrence, Lindsay Jaimeson (DSIT), Tim Render, Hilary Newiss, Catherine Salway, Kirsty Whitehead, Adam Williams (CEO)
Executive Directors: Sian-Nia Davies, Neil Hartley, Ben Llewellyn-Jones, Chris Mills, Penny Phillpotts,.
Non-members: Laura Fleck, CEO Office, Secretariat
Presenters:, Jodie Barnard, Natasha Chick, Lorna Dukes, Sam Gowans, Alex Jones, Guy Robinson
Apologies: Steph Dales
SB24/44	Chair’s Introduction

The Chair welcomed everybody to the meeting, including three new Non Executive Directors (Tim Render, Catherine Salway and Kirsty Whitehead). The three new Non Executive Directors (NEDs) provided a brief overview of their backgrounds.

The Chair noted that Ben Llewellyn-Jones was leaving the IPO and that this would be his last Steering Board meeting. The Chair thanked him for his contribution.

It was reported that the Chair and CEO had met with the new Parliamentary Under-Secretary of State for AI and Digital Government, Feryal Clarke MP whose portfolio included Intellectual Property. A positive introductory letter setting out the Secretary of State for Science, Innovation and Technology’s priorities had also been received.

A periodic roundtable had also been held with Department for Science, Innovation and Technology (DSIT) Director General and colleagues to discuss working relationships and mutual priorities for IP and innovation and it was noted that this had been a positive and productive meeting.

SB24/45	Apologies

Apologies were received from Steph Dales

SB24/46	Declaration of Interests

There were no new declarations of interest.

SB24/47	Approval of Minutes – 20 June 2024

AGREED: that the minutes of the Steering Board meeting held on 20 June 2024 be approved as a correct record.

SB24/48	Action log

The action log was noted.

Performance and Delivery

SB24/49	CEO’s Introduction and Quarterly Strategic Report

The Board received the Quarterly Strategic Report, which was in a new format in order to streamline monitoring and reporting against delivery of the corporate plan, without removing key data.

The CEO introduced the report, highlighting some key points. Good progress had been made against most areas of the corporate plan during Quarter One. Customer satisfaction levels were at 89% and Steering Board were advised that the score was developed using an industry wide standard and that significant work had been done to ensure that the IPO was ‘speaking customers language’ and that the improvement in the customer satisfaction could, in many ways, be attributed to this.

Work was underway to progress the 5% pay award agreed across the Civil Service. The IPO had budgeted for a 5% award this financial year so there was no adverse budgetary impact. The government had formally removed the focus on headcount cap however IPOB recognised there was a need to ensure that the IPO was right-sized for its income and activities.

Progress was being made with One IPO Transformation programme and further details would be provided under a separate agenda item.

Work was still underway with NAO to agree the annual accounts. Audit and Risk Committee would therefore consider the accounts at their November meeting. The accounts were required to be laid in parliament by 30 November 2024.

Steering Board were advised that the Director of Strategy permanent post would be advertised during the autumn.

Members sought an update on the review of the UK Designs framework. It was reported that this had been slightly delayed due to the General Election but a consultation was expected to be published shortly and there would be a focus on engaging people who would not usually respond using a variety of methods including roadshows and online events. It was suggested that it would be useful to bring this back to Steering Board during 2025.

In relation to a query around ‘deep fakes’, Steering Board were advised that the policy response was being coordinated by the Home Office as the issue had a number of different lenses through which it could be viewed. The IPO was participating in the cross-government discussions.

Further information was sought in relation to the future change model and It was suggested that it would be useful for Steering Board to receive a more detailed update on the change model at a future meeting.

Overall, Steering Board welcomed the new format and information contained within the report. It was requested that RAG rating parameters could be further explained within the document and acronyms explained.

Action: UK Designs Framework review results to be brought to Steering Board at the appropriate time during 2025 (Chris Mills/Secretariat)
Action: Change model to be added to a future Steering Board agenda (Secretariat/Penny Phillpotts)
Action: RAG ratings to be explained within the Quarterly Strategic Report (Guy Robinson)
Action: Common acronyms list to be added to the Steering Board reading room (Secretariat)

SB24/50	Finance Update

A financial update was received. It was reported that the Quarter One review had just been completed. An overspend was currently predicted but there were a number of factors that were likely to reduce or eliminate this deficit by the end of the financial year. These include reduced exit costs, bank interest and savings on contractor costs. It was further reported that income was ahead of budget and it was noted that the increase due to the reduction in predicted capitalisation cost was likely to be a one off event. It was noted that recruitment controls were still being maintained as a matter of prudence.

SB24/51	Culture Update

Steering Board received an update on the progress being made in the work being done in relation to enabling the future culture that had been identified as being needed to support the delivery of the IPO Strategy. It was reported that work was ongoing to replan and reprioritise activity to focus on those that best supported culture change. The accompanying paper set out actions taken together with risk and mitigations.

Steering Board members welcomed the detail contained within the paper. They noted that regular reporting and Board review was key together with Board members modelling the competencies and behaviours they wished to see across the organisation. It was noted that the Organisational Leaders Network played a key part in modelling and changing behaviours.

Steering Board members recognised that there was not a ‘bad’ culture at the IPO but that there was a desire to continually improve in order to meet our goal of being a high-performing organisation.

SB24/52	DSIT Verbal Update

Alex Jones, Director General DSIT, joined the meeting to provide an update from the Department. Alex began by welcoming the three new Non Executive Directors and noting that since the last Steering Board there had been a change in Government which inevitably led to a great deal of change. It was reported that the new Government had five key missions – kickstarting economic growth, make Britain a clean energy superpower, safer streets, build an NHS fit for the future and break down barriers to opportunity.

Under the new government DSIT now included the Central Digital and Data Office (CCDO) and the Government Digital Service (GDS) and was now responsible for digital government. DSIT had three main priorities – accelerating innovation, investment and productivity, using technology for good and driving forward a modern digital government.

It was noted that the IPO would have a key role to play in all these missions and that the One IPO Transformation programme was a key example of modern digital government.

Alex welcomed the positive relationship between DSIT and the IPO.

SB24/53	Risk Management

Steering Board received the Strategic risk pack which provided an update on Strategic and Corporate level risks.

Further information was requested in relation to risk S108. It was reported that this was not a new risk but had been reshaped, particularly in relation to the controls and actions needed.

Steering Board members queried where the transformation project risks were held. It was noted that there was a separate risk register for Transformation, held at Transformation Programme Board level. However, work was being carried out to establish how to capture high level risks at IPOB level.

Steering Board welcomed the risk pack, particularly the new layout. They suggested that it would be helpful to include details of closed risks. Steering Board were also advised that a session on risk management at the IPO would be arranged for the new Non-Executive Directors.

Action: Closed risk detail to be included within the risk pack
Action: Session on risk to be arranged for new Non Executive Directors

SB24/54	One IPO Transformation Update

Written and verbal updates on the Transformation Programme were received. It was reported that further releases for Phase One were planned for October/November. Development was complete and testing was underway. Release 4 (including deposit accounts) had begun in July.

Steering Board noted the work being carried out by the transformation programme team and passed on their thanks.

SB24/55	ARC Update and to note ARC May 2024 Minutes

Steering Board received and noted the minutes from the ARC meeting held on 24 May 2024.

The Chair of ARC gave a verbal update on the meeting held on 4 July 2024. It was noted at that meeting that there would be a delay laying the accounts before parliament due to the General Election. The current position with the accounts had already been explained to Steering Board.

The ARC meeting on 4 July had examined the content of the annual report together with Internal Audit reports which had been received at ARC. Steering Board was advised that ARC regularly received the Internal Audit reports and monitored progress against any actions contained within them.

SB24/56	SME Sub Strategy

The IPO sub strategy to support Small Medium Enterprises (SMEs) was presented. The sub strategy set out the IP challenges faced by SMEs together with the action the IPO was taking to support them. The sub strategy also included the outcomes the IPO wished to achieve over the next three years with details of how progress against the objectives would be assessed.

Steering Board members welcomed the sub strategy, particularly the emphasis on communicating with key groups . A wide demographic reach was key and it was important that other organisations could help deliver the message to SMEs at the right time. It was reported that an integrated external and internal communications function was being developed.

A query was raised over whether the size of organisations registering rights was captured. It was reported that it was a challenge to know this data but work was ongoing to look at ways to capture this. However ,it was noted that it was important that SMEs made informed decisions around their IP rights and this would be harder to capture. Work was ongoing to collect ‘stories’ from SMEs.

In relation to mapping of activities, it was noted that the ‘Theory of Change’ model was being used.

Steering Board noted that a challenge would be reaching the right kind of SME to have an impact and that reaching young people would be critical.

It was noted that the sub strategy had been a cross-IPO approach and this would need to be sustained.

The Steering Board noted this important sub strategy.

Action: Communications plan to be brought to Steering Board in 2025 (Penny Phillpotts/Secretariat)

SB24/57	Governance Review Update

An update on the governance review was received. The governance review is intended to identify opportunities to simplify processes for more efficient and effective outcomes and enable individuals and teams to make informed decision at the right time and level. It was noted that Steering Board and ARC were out of scope, although any identified process improvements could be used in support of these meetings.

Steering Board members commented that it was important to recognise the value of the assurance role but there was a need to balance the role of committees.

It was hoped that the recommendations of the governance review would be presented to IPOB in the coming months.

SB24/58 A.O.B and reflections on the meeting

There were no items raised.

Reflections of the meeting:

- Welcomed fresh perspectives brought by new NEDs
- Papers were easy to read, new format of strategic report and risk pack welcomed
- SME sub strategy interesting and clearly the result of significant work
- Positive interactions and contributions
- Welcomed the opportunity to network during breaks
- Interactive sessions would add another dimension
- Consider a different room