## External Plan Format
NRS Procurement Plan as at end of July 2025
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded
C21790 | Decommissioning | Oldbury | Oldbury - Demolition of Redundant Timber Buildings | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2024-12-01 | (a) | 2025-04-10 | (a) | Bath Demolition Ltd
C25144 | Decommissioning | Trawsfynydd | Sampling & Analysis Characterisation | Construction | Shelley.Lawrence@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2025-10-07 | (f) | 2026-06-04 | (f) | Not yet confirmed
C25258 | Decommissioning | Maentwrog | Maentwrog Unit 2 Generator/Turbine Overhaul - Outage 2025 | Engineering | claire.scott@nrservices.uk | Direct Award - Below Threshold | £500k to £1m | n/a | 2025-04-10 | (a) | 2025-04-10 | (a) | Quartzelec
C5672 | Decommissioning | Sizewell | Install Modify Vent - Splitter Vane Store (SVS) | Construction | sarah.j.deeble@nrservices.uk | Non-FTS Competition | <£100K | 2026-02-01 | 2026-04-05 | (f) | 2026-06-04 | (f) | Not yet confirmed
C5678 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@nrservices.uk | PA23 Competitive Flexible | £1m to £5m | n/a | 2026-08-13 | (f) | 2027-02-09 | (f) | Not yet confirmed
C5690 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | fiona.pearse@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-10-08 | (a) | 2025-08-08 | (f) | Not yet confirmed
C5693 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | PA23 Open | <£100K | n/a | 2025-10-07 | (f) | 2026-02-04 | (f) | Not yet confirmed
C8950 | Decommissioning | Dungeness | Package 1 Demolition, Boiler & ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@nrservices.uk | FTS Comp Proc with Negotiation | £50m to £100m | 2023-02-07 | 2023-06-10 | (a) | 2026-09-12 | (f) | Not yet confirmed
C9092 | Decommissioning | Oldbury | Oldbury Turbine Hall Demolition | Decommissioning, Demolition & Deplant | danielle.staples@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2026-02-04 | (f) | 2027-02-09 | (f) | Not yet confirmed
C9924 | Decommissioning | Harwell | LETP Land Re-instatement & SUDS system (Package 8b) | Construction | paul.phillips@nrservices.uk | PA23 Open | £1m to £5m | n/a | 2025-06-09 | (a) | 2025-08-08 | (f) | Tend: Gallagher Limited,Jones Bros Ruthin (Civ Eng) Co.Ltd,Breheny Civil Engineering Ltd,Oldham Engineering Ltd,Seymour Civil Engineering,VHE Construction
C25602 | Decommissioning | Enablers/Not Location Specific | Ground Water Monitoring Services 2025-2028 | Support Services | lindsay.gibson@nrservices.uk | Mini Competition F/W | £1m to £5m | n/a | 2025-06-09 | (a) | 2025-09-07 | (f) | Not yet confirmed
C25638 | Decommissioning | Harwell | BEPO Characterisation DQO / Sampling Plan | Design services/support | Shelley.Lawrence@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-02-04 | (f) | 2026-07-14 | (f) | Not yet confirmed
C25644 | Decommissioning | Harwell | BEPO Welfare Facilities | Plant & Equipment & Materials | Shelley.Lawrence@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2027-02-09 | (f) | 2027-05-10 | (f) | Not yet confirmed
C25654 | Decommissioning | Maentwrog | Maentwrog Estate Management 2025 - 2029 | Support Services | lindsay.gibson@nrservices.uk | PA23 Open | £100k to £500k | n/a | 2025-09-07 | (f) | 2025-11-06 | (f) | Not yet confirmed
C25655 | Decommissioning | Maentwrog | Maentwrog Outage Welding Support 2026-2030 | Construction | lindsay.gibson@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2026-03-06 | (f) | 2026-06-04 | (f) | Not yet confirmed
C24971 | Decommissioning | Berkeley | Berkeley Blower Houses Interim Safe State | Engineering | david.m.sanderson@nrservices.uk | Direct Award F/W | £1m to £5m | n/a | 2025-06-09 | (a) | 2025-10-07 | (f) | Not yet confirmed
C24978 | Decommissioning | Oldbury | Auto-SAS Enablers - Oldbury Co2 Tank Removal + Option to demolish Permit Office | Decommissioning, Demolition & Deplant | david.m.sanderson@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-07-09 | (a) | 2025-08-08 | (f) | Tend: More than 10
C26368 | Decommissioning | Dungeness | Dungeness A: Replace Surface Drains Pumps 1&3 | Construction | danyal.nawaz@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-11-06 | (f) | 2025-12-06 | (f) | Not yet confirmed
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health Services 25+ | Support Services | Amy.Vale@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-05-10 | (a) | 2025-11-06 | (f) | Not yet confirmed
C13038 | Ops & Enablers | Enablers/Not Location Specific | Drawing Management System - 2026 | IT hardware/software | jayne.chalmers@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-11-06 | (f) | 2026-03-06 | (f) | Not yet confirmed
C13774 | Ops & Enablers | Enablers/Not Location Specific | Fleet Management and provision of Lease Cars 2025-29 | Support Services | holly.griffith@nrservices.uk | CCS F/W Call off | £5m to £10m | n/a | 2024-10-02 | (a) | 2025-06-09 | (a) | Knowles Fleet
C14315 | Ops & Enablers | Enablers/Not Location Specific | Project Controls & Commercial Services (2026+) | Design services/support | michelle.a.edwards@nrservices.uk | Mini Competition F/W | £50m to £100m | n/a | 2026-07-14 | (f) | 2027-07-09 | (f) | Not yet confirmed
C16731 | Ops & Enablers | Enablers/Not Location Specific | Consolidated Testing Services - 2025 | Manpower | jayne.chalmers@nrservices.uk | CCS F/W Call off | £5m to £10m | n/a | 2025-05-10 | (a) | 2025-06-09 | (a) | H3O DIGITAL ltd
C17087 | Ops & Enablers | Enablers/Not Location Specific | Supply of Metrology Instruments (Installed and Portable) | Engineering | caroline.j.milner@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification
C17387 | Ops & Enablers | Bradwell; Dungeness; Sizewell | Civils Support DPS - South East Region | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C17421 | Ops & Enablers | Dounreay; Enablers/Not Location Specific | Workplace Services 2027 | Maintenance | steven.j.lock@nrservices.uk | CCS F/W Call off | £250m plus | n/a | 2025-04-10 | (a) | 2025-10-07 | (f) | Not yet confirmed
C17423 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - System | IT hardware/software | james.hiller@nrservices.uk | PA23 Competitive Flexible | £10m to £25m | n/a | 2025-06-26 | (a) | 2026-06-05 | (f) | Not yet confirmed
C17426 | Ops & Enablers | Enablers/Not Location Specific | Enterprise Asset Management (EAM) - Data Management | Manpower | james.hiller@nrservices.uk | Mini Competition F/W | £25m to £50m | n/a | 2026-02-04 | (f) | 2026-10-12 | (f) | Not yet confirmed
C19724 | Ops & Enablers | Enablers/Not Location Specific | Asbestos Analytical Services 2025 | Design services/support | Shelley.Lawrence@nrservices.uk | DPS Call-Off | £25m to £50m | n/a | 2025-12-06 | (f) | 2026-06-04 | (f) | Not yet confirmed
C19793 | Ops & Enablers | Chapelcross; Hunterston | Civils Support DPS (Scottish Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20508 | Ops & Enablers | Berkeley; Hinkley; Oldbury | Civils Support DPS (South West Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C20831 | Ops & Enablers | Maentwrog; Trawsfynydd; Wylfa | Civils Support DPS (Welsh Region) - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £5m to £10m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C21428 | Ops & Enablers | Enablers/Not Location Specific | Supply of Air Filter & Ancilary Equipement 2026-2030 | Consumables | sion.apglyn@nrservices.uk | New Framework set up | £1m to £5m | n/a | 2025-11-06 | (f) | 2026-05-05 | (f) | Not yet confirmed
C21710 | Ops & Enablers | Enablers/Not Location Specific | Access & Insulation Services 2025-2029 | Construction | michelle.newcombe@nrservices.uk | FTS Restricted | £50m to £100m | 2024-10-17 | 2025-01-10 | (a) | 2025-09-07 | (f) | Not yet confirmed
C21822 | Ops & Enablers | Harwell; Winfrith | Civils Support DPS - South Region - Pre-Qualification | Construction | adrian.h.williams@nrservices.uk | DPS Set up | £1m to £5m | n/a | n/a |  | n/a |  | DPS is now live and open for supplier registration, pre-qualification and the issuing of tendering opportunities via further competition
C21842 | Ops & Enablers | Enablers/Not Location Specific | Project Controls & Commercial Services Bridging Contract | Design services/support | michelle.a.edwards@nrservices.uk | Direct Award F/W | £10m to £25m | n/a | 2025-07-09 | (a) | 2025-10-07 | (f) | Not yet confirmed
C24227 | Ops & Enablers | Enablers/Not Location Specific | Pension Trustee Services | Manpower | alwena.owen@nrservices.uk | PA23 Competitive Flexible | £500k to £1m | n/a | 2025-10-07 | (f) | 2026-06-04 | (f) | Not yet confirmed
C24235 | Ops & Enablers | Berkeley; Bradwell; Chapelcross; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Sizewell; Trawsfynydd; Winfrith; Wylfa | Category 2 - Health Physics Monitoring Resource | Design services/support | sukyee.hermon@nrservices.uk | DPS Call-Off | £25m to £50m | n/a | 2025-10-07 | (f) | 2026-05-05 | (f) | Not yet confirmed
C24237 | Ops & Enablers | Berkeley; Bradwell; Carlisle; Chapelcross; Crewe; Dounreay; Dungeness; Harwell; Hinkley; Hunterston; Oldbury; Preston; Sizewell; Trawsfynydd; Winfrith; Wylfa | Security Personnel Services 2027 | Support Services | steven.j.lock@nrservices.uk | CCS F/W Call off | £50m to £100m | n/a | 2026-03-06 | (f) | 2027-01-10 | (f) | Not yet confirmed
C24524 | Ops & Enablers | Enablers/Not Location Specific | Contract a job site & global matching and hiring platform | Support Services | alwena.owen@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-03-11 | (a) | 2025-06-09 | (a) | Indeed
C25013 | Ops & Enablers | Enablers/Not Location Specific | Legal Advice Services July 25 - Nov 27 | Support Services | gissela.m.hughes@nrservices.uk | CCS F/W Call off | £1m to £5m | n/a | 2025-05-10 | (a) | 2025-09-07 | (f) | Not yet confirmed
C25425 | Ops & Enablers | Hinkley | ACP-1885-HPA Site roofs by priority | Construction | louise.x.brown@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-05-10 | (a) | 2025-07-09 | (a) | Central Roofing and Building Services Ltd
C25464 | Ops & Enablers | Hinkley | HPA RCA Welfare Facility | Construction | louise.x.brown@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-08-08 | (f) | 2025-11-06 | (f) | Not yet confirmed
C5824 | Ops & Enablers | Enablers/Not Location Specific | Statutory Examination Services 2026+ | Design services/support | caroline.j.milner@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2025-11-06 | (f) | 2026-07-14 | (f) | Not yet confirmed
C23408 | Ops & Enablers | Enablers/Not Location Specific | Pension secretarial services | Support Services | alwena.owen@nrservices.uk | PA23 Open | £100k to £500k | n/a | 2026-12-11 | (f) | 2027-06-09 | (f) | Not yet confirmed
C10684 | Ops & Enablers | Enablers/Not Location Specific | Calibration and Maintenance of Radiological Instruments - Installed | Engineering | caroline.j.milner@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2026-07-14 | (f) | 2027-03-11 | (f) | Not yet confirmed
C19489 | Ops & Enablers | Enablers/Not Location Specific | PM&BA and TDA 2026 (Procurement) | IT hardware/software | jonathan.harris@nrservices.uk | CCS F/W Call off | £5m to £10m | n/a | 2026-01-05 | (f) | 2026-08-13 | (f) | Not yet confirmed
C19614 | Ops & Enablers | Enablers/Not Location Specific | Calibration and Maintenance of Radiological Instruments - Portable | Engineering | caroline.j.milner@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2026-07-14 | (f) | 2027-03-11 | (f) | Not yet confirmed
C25807 | Ops & Enablers | Berkeley | Berkeley Site Services Building | Construction | ben.bilton@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-06-09 | (a) | 2025-08-08 | (f) | Tend: More than 10
C13780 | Ops & Enablers | Enablers/Not Location Specific | Provision of a Managed Learning Service 26+ | Support Services | holly.griffith@nrservices.uk | PA23 Open | £5m to £10m | n/a | 2025-12-06 | (f) | 2026-09-12 | (f) | Not yet confirmed
C26111 | Ops & Enablers | Hunterston | BATS 074 Inspection of Stack and Ducts | Design services/support | louise.waldron@nrservices.uk | PA23 Open | £100k to £500k | n/a | 2025-06-09 | (a) | 2025-08-08 | (f) | Not yet confirmed
C24019 | Ops & Enablers | Oldbury | Radios - Oldbury | Maintenance | Kwadwo.Awuku@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-09-07 | (f) | 2025-12-06 | (f) | Not yet confirmed
C26821 | Ops & Enablers | Hunterston | Hunterston Site A - Site Office Repairs | Construction | ben.bilton@nrservices.uk | Dynamic Market Call Off | £100k to £500k | n/a | 2025-08-08 | (f) | 2025-11-06 | (f) | Not yet confirmed
C26824 | Ops & Enablers | Sizewell | Sizewell A Reactor Building Structural Investigations | Construction | adrian.h.williams@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-08-08 | (f) | 2025-09-07 | (f) | Not yet confirmed
C26881 | Ops & Enablers | Sizewell | Frisker Probes - SZA | Engineering | caroline.j.milner@nrservices.uk | DPS Call-Off | <£100K | n/a | 2025-07-09 | (a) | 2025-12-06 | (f) | Tend: More than 10
C17610 | Waste | Hinkley | Hinkley - Design, supply and installation of 415V Switchboard | Consumables | karen.maguire@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-08-25 | (f) | 2026-02-04 | (f) | Not yet confirmed
C20416 | Waste | Enablers/Not Location Specific | Characterisation Services | Design services/support | Liz.Gilbert@nrservices.uk | New Framework set up | £10m to £25m | 2025-02-22 | 2025-09-07 | (f) | 2025-12-06 | (f) | Not yet confirmed
C23142 | Waste | Dungeness | Overhead Gantry Cranes (Wet Waste Transfer Facility) | Engineering | karen.maguire@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2024-12-01 | (a) | 2025-05-10 | (a) | Penny Engineering Ltd
C23875 | Waste | Chapelcross | Manufacture of Stainless Steel 500L Drums, Stillages & Sleeves | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £1m to £5m | n/a | 2025-02-09 | (a) | 2025-07-09 | (a) | Carr's Engineering Ltd (T/A Bendalls Engineering)
C24146 | Waste | Berkeley | 2 Forklifts 5 year hire for Berkeley site | Support Services | jake.roberts@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-07-08 | (a) | 2025-08-11 | (f) | Not yet confirmed
C24391 | Waste | Chapelcross | Special Waste Management – Provisions of Containers, Carriage and Disposal of No | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | Non-FTS Competition | £100k to £500k | n/a | 2025-09-22 | (f) | 2026-02-06 | (f) | Not yet confirmed
C24817 | Waste | Winfrith | Demo Penetrations 2025 | Construction | chris.dorain@nrservices.uk | Direct Award - Below Threshold | £1m to £5m | n/a | 2025-04-10 | (a) | 2025-04-10 | (a) | Drillcut (UK) Ltd
C24841 | Waste | Winfrith | BATS 073 100425 JS AW Non-Radiological Determination Period Support - Winfrith | Design services/support | janet.smith@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-04-10 | (a) | 2025-07-09 | (f) | Tend: More than 10
C25273 | Waste | Winfrith | BATS 072 100425 JS AW - Radiological Determination Period Support - Winfrith | Design services/support | janet.smith@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-04-10 | (a) | 2025-07-09 | (f) | Tend: More than 10
C25818 | Waste | Dungeness | Fill House fire remediation works – Dungeness A Site | Construction | karen.maguire@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-05-10 | (a) | 2025-06-09 | (a) | AW Construction Services
C24840 | Waste | Winfrith | Winfrith Engineering: ILW Management Support | Design services/support | janet.smith@nrservices.uk | Direct Award - Above Threshold - PA23 Section 41 (Special cases) | £500k to £1m | n/a | 2025-08-30 | (f) | 2025-08-08 | (f) | Not yet confirmed
C25148 | Waste | Hinkley | Design, Manufacture, Trials and Delivery of an External Mixer (ILW Waste stream) | Waste management, disposal & storage | karen.maguire@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-11-06 | (f) | 2026-07-14 | (f) | Not yet confirmed
C26596 | Waste | Berkeley; Oldbury | Low Level Waste Assay System at Berkeley & Oldbury Site | Engineering | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £500k to £1m | n/a | 2025-07-09 | (a) | 2025-10-07 | (f) | Tend: More than 10
C26579 | Waste | Hunterston | DESIGN, MANUFACTURE & OVERSIGHT THE INSTALLATION OF TWO LARGE ITEM BAG MONITORS | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | DPS Call-Off | £100k to £500k | n/a | 2025-07-09 | (a) | 2025-10-07 | (f) | Tend: More than 10
C26757 | Waste | Harwell | HF Containment for Manufacture | Waste management, disposal & storage | pauline.z.mackemsley@nrservices.uk | Non-FTS Competition | <£100K | n/a | 2025-07-09 | (a) | 2025-07-09 | (a) | TML (WEYMOUTH) LTD
C26820 | Waste | Hinkley | 2KM Polymer Dispensing System (PDS) Support Contract | Design services/support | pauline.z.mackemsley@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-07-09 | (a) | 2025-07-09 | (a) | 2KM (UK) LIMITED
C26848 | Waste | Dungeness | 5-year contract hire with service and maintenance package of 20te counterbalance | Plant & Equipment & Materials | pauline.z.mackemsley@nrservices.uk | Other - No Competition | £100k to £500k | n/a | 2025-07-09 | (a) | 2025-07-09 | (a) | Briggs Equipment