TERMS OF REFERENCE / Mapping Kenya’s Bioscience Sector - a Review of the Current Landscape and Future Prospects for Bioscience Innovation in Kenya / August 2025

1. BACKGROUND

1.1 About the Evidence Fund
The Foreign, Commonwealth & Development Office (FCDO) requires accessible high-quality research, evaluation and evidence products which target policy, country-specific and regional priorities and are available for use by FCDO and the international development sector. FCDO’s Research and Evidence Directorate (RED) has as its mission to develop and deliver new technologies and innovations that can help solve development challenges, test high potential interventions, and support the delivery of His Majesty’s Government (HMG) objectives. The Evidence Fund is a co-ordinated effort to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.
1.2 Details on the Research Context
The Bioscience Sector has been selected as the first ‘innovation cluster’ for the Kenyan National Innovation Agency (KeNIA)’s new cluster-driven approach to innovation. The sector is of mutual interest to both Kenya and the UK, given the potential it holds to promote economic transformation and address social and economic challenges, including through innovations in health, agriculture and industry. Biosciences are critical to effective health systems, playing a role in disease detection and creation of vaccines and therapeutics, with biomedical engineering being a particularly significant sector. Biosciences also form a foundation for agricultural research and development, with synthetic biology supporting crop resilience, improving yields and creating bio-based pest control that can support food security. Biosciences are also critical to industrial development, playing a role in the production of biofuels, biodegradable materials, environmentally friendly chemicals and bio-based solutions for environmental challenges such as waste management and pollution control etc.

The East Africa Research and Innovation Hub (EARIH) is working in partnership with KeNIA (Kenyan National Innovation Agency) and NACOSTI (National Commission for Science Technology and Innovation) to commission a landscape mapping with the objective of providing an assessment of the current state of innovation within the Bioscience Sector in Kenya.
The study aims to identify key sub-sectors within the Biosciences that offer most potential for innovation, investment and growth, and present insights and recommendations on forward-looking opportunities for the UK and Kenya, as well as other key stakeholders working towards the development of the Bioscience sector. This research will complement and build on existing mapping of the Bioeconomy that has been carried out by the Stockholm Environment Institute (SEI) in partnership with the Kenyan Private Sector Alliance (KEPSA) as part of the Swedish Government’s ‘Advancing Bioeconomy Development in Kenya’ (ABDK) project.
2. KEY EVIDENCE GAPS

Despite Kenya’s emergence as a leading innovation hub in the region and a magnet for startup investment in Africa, the role of science-driven innovation, and particularly the role of the Bioscience sector in driving innovation, creating new ventures, attracting investment and contributing to economic growth, has not been exploited to its full potential and is still not well evidenced or understood. There are critical gaps in knowledge and data around the state of existing research and development (R&D) and innovation in the Bioscience sector in Kenya, the levels of investment that the sector is attracting, the type of Bioscience innovations that are being commercialised and developed into Bioscience ventures, the challenges and bottlenecks that may be constraining Bioscience innovations (including institutional, financial, skills-related and market related), as well as the state of the existing regulatory and policy environment with regard to Bioscience Innovation. This section outlines the key areas where further research and data collection are needed.
Mapping of Existing Bioscience Research and Innovation in Kenya
Information on where the most cutting-edge R&D in biosciences is taking place and how much of this R&D is being translated into commercial outcomes, products or services whether as start-ups or joint ventures with industry. This will include a mapping of the skills and capabilities in the sector and where the key strengths and gaps are.
Infrastructure and Resources for Bioscience Innovation
There is a need to understand the state of existing infrastructure (including laboratory and research facilities) as well as factors such as digital architecture, energy supply, transport logistics, cold chain storage, availability of biological resources etc. that all affect the potential for innovation in the sector.
Understanding Key Stakeholders in the Bioscience Sector
While some mapping has been done of key stakeholders and activities in the Bioeconomy in Kenya, there is still a lack of data on the role of different actors within the wider Bioscience Sector and who these key stakeholders are – whether academic institutions, industry partners, investors and financial institutions, enterprise support organizations (ESOs), international partners (including global research networks), end users (whether hospitals, medical companies, agribusiness, NGOs, CSO etc.) and government and policy makers. Further mapping is also needed to understand the existing linkages and collaboration between these stakeholders and the steps that are needed to address fragmentation within the sector.
Funding and Investment
More information is needed on the funding flows for Bioscience research and innovation, including research funding from national and international sources, venture capital and angel investment, DFI flows, commercial investments and donor/philanthropic funding flows. A mapping of the sources and recipients of different funding flows and how these are being used to drive Bioscience innovation will be critical to identify funding gaps as well as areas of high potential.
Policy and Regulatory Environment
The frameworks and strategies governing Bioscience research and innovation are poorly understood in Kenya and a stronger understanding of the existing policy and regulatory environment is needed to facilitate further innovation and investment in the Bioscience sector. This includes mapping out existing regulations around issues such as biosafety, but also regulatory approval processes for new drugs, diagnostics and products such as GM crops, as well as understanding IP frameworks and rights.
3. OBJECTIVES AND SCOPE OF WORK

3.1. Objectives
To provide a mapping of the current state of innovation within the Bioscience Sector in Kenya (including defining key priority areas and subsectors within the Biosciences) and an analysis and foresight study of future opportunities for Bioscience innovation, with clear recommendations for government, academia, private sector, and other stakeholders to realise this potential.
The study will have two parts to it:
1. A landscape mapping of Bioscience Innovation in Kenya to understand the current state of the sector and
2. A foresight study that identifies future trends and opportunities and provides recommendations for the future.
3.2 Scope
The mapping will focus on Innovation in the Bioscience Sector in Kenya, identifying the key sub-sectors within the Biosciences (whether agriculture, healthcare, industry or bioeconomy) and focusing in on those which hold most relevance and potential for the country. The study will map the status of existing research, development and innovations in the Biosciences, start-ups and ventures in the sector, funding sources as well as assessing the state of infrastructure and capabilities, policies and regulations. The study will also explore barriers to innovation and growth in the sector and document successful case studies of existing Bioscience innovations that have been successfully commercialised and scaled (whether through creation of start-ups, joint ventures or partnerships with industry).
The research will be implemented over three phases:
1. Inception phase
2. Research and analysis; and
3. Validation and stakeholder workshops.
Phase 1 – Designing the Research Approach and Conducting the Research:
The Supplier will work with the key stakeholders of this research (KeNIA, NACOSTI, FCDO and the Bioscience Innovation Working Group) to understand their priorities and key issues that need to be considered when conducting the study. The inception meeting will involve a review of ToR, agree on the final objectives of the study (including its intended use), the proposed approach and methodology, consider the research questions and parameters, roles and responsibilities, any risks to delivery especially in-country data collection, the timeline, and deliverables, as well as to start brainstorming an initial list of key informants for consultation. During this phase, the team will produce an Inception Report (no more than 15 pages), which will include:
- Research questions and parameters that will be prioritised.
- Existing datasets, reports and sources of information which will be identified for the desk-based analysis.
- A list of key stakeholders to be interviewed during the fieldwork phase including academic institutions, industry partners, government officials, development partners, investors, and other relevant stakeholders.
- The proposed methodology for research, including details of how the approach will be adaptive and respond to changes, and ensuring this is relevant to the needs of government, industry, academia and investors.
- A detailed work plan for conducting the remainder of the study, including details of data collection tools and stakeholder engagement strategy.
Phase 2 – Research and Analysis:
This will be the principal phase of the research study and will include three components (a) the desk-based analysis of existing datasets and evidence on the Bioscience sector, including analysis of literature, reports, policies and data gaps (b) fieldwork and data collection (qualitative and quantitative) to map current actors, capabilities, infrastructure, funding flows and regulatory frameworks, as well interviews and consultations with a representative set of stakeholders to fill evidence gaps and identify key Bioscience innovations that can be used as case studies, (c) foresight study that includes horizon scanning and trend analysis to identify opportunities for the sector, including risks and pathways that could shape the development of the sector over the next ten years. A draft report will be submitted at the end of this phase for review by the Steering Group before proceeding to the validation phase.
Phase 3 - Validation and Stakeholder Workshops:
The supplier will be responsible for leading a structured validation process where a series of workshops are held with different stakeholders to review the findings from the research and analysis conducted in Phase 2, test assumptions and build consensus. Workshops will also be used to co-create key recommendations and actions that can be used to strengthen collaboration, guide policy and investment decisions and support the future development of the sector.
The Final deliverables from the three phases will include:
- A detailed report and mapping on the state of the Bioscience Sector in Kenya, including a database setting out the status of existing ventures and start-ups in Biosciences in Kenya.
- A Policy brief (max. 4 pages) that sets out key recommendations for government, academia, private sector, investors and development partners to maximise the potential for innovation and growth in the sector.
- A PowerPoint presentation of the report for dissemination purposes.
- A set of infographics to visually represent the key findings of the report.
3.3 Research Questions
Part A: Mapping of Current State of Innovation in Bioscience Sector
Key research questions for the mapping will include:
- Which are the key sub-sectors and areas within the Biosciences where Kenya holds an advantage, and which offer the most potential for innovation and growth? (e.g., healthcare, agriculture & food security, industry, bio-based economy etc)
- Who are the key players (academic institutions, research organisations, and public and private sector actors, including start-ups) in the priority Bioscience sectors in Kenya?
- What are the current national policies and regulations (including biosafety) and how do they impact the development of the Bioscience sector (in particular, innovations in biosciences) in Kenya?
- What are the major funding and investment sources and incentives for Bioscience research and development, and start-up ventures?
- What are the research and technical capabilities that Kenya holds in the Bioscience sector (and the sub-sectors which the mapping focuses on) and what is the state of research to commercialisation in these areas?
- What is the state of current bioscience ventures and innovations in Kenya, and which of these offer most potential for growth?
- What is the status (and requirements) of necessary infrastructure to facilitate innovation and ventures in the bioscience sector (including physical and digital infrastructure?

Part B: Foresight and analysis of Future Opportunities for Bioscience Innovation
Key research questions for the analysis and foresight will include:
- What are the main policy gaps and challenges facing the growth and development of innovations and ventures in Biosciences in Kenya?
- What could be strategic and policy recommendations to attract more investment in Bioscience research, development and innovation?
- What are the key trends and opportunities, within a 10-year timeframe, for innovation in Kenya’s Bioscience sector (investments in R&D capacity, partnerships across academia, industry, and government, educational and training programs, regulatory frameworks)?
- Which key thematic sectors should Kenya prioritize to advance innovations in the Biosciences, specifically in health, agriculture, industrial manufacturing/biotechnology and the bioeconomy?
- How can the UK Government, academia, and industry sectors partner with Kenya to harness innovation potential in the Bioscience sector? (R&D partnerships, funding, joint ventures, technical guidance for the commercialization of Bioscience innovations)?
3.3 Research Methodology
The study will use a mixed-methods approach including desk-based analysis of existing data and reports, followed by stakeholder interviews, focus group discussions, surveys, and case studies. Both qualitative and quantitative data will be collected and analysed to provide comprehensive insights. The exact methodological approach will be finalised during the inception phase.
3.4 Theory of Change
Investing in a robust mapping and landscaping study such as this one will create a foundation for long-term sectoral growth by generating high quality evidence and data on the status of innovation in the Biosciences Sector, including strengths, capabilities, gaps and opportunities. The study will also identify the challenges and bottlenecks that need to be overcome for the sector to achieve its full potential, with the evidence and data it provides helping to strengthen policy and investment decisions and guiding governments, funders and investors to allocate resources more effectively. At the same time, the process of conducting this research and creating this mapping will act as a means of convening stakeholders, fostering dialogue and encouraging greater collaboration between academia, industry, government, investors and other key stakeholders in the Biosciences sector. By improving access to data, enhancing transparency and promoting better coordination in the sector, the study aims to reduce information asymmetries and provide a foundation for stronger coordination and enhanced investment that can enable the Bioscience sector to continue to grow, innovate, create jobs and contribute to Kenya’s economic development.

3.5 Required Skills
The Supplier will lead the research design, data collection, analysis, and reporting. FCDO and the East Africa Research and Innovation Hub will provide oversight and strategic guidance. Regular coordination meetings will be held to ensure alignment. The team should include both international and national experts, with a strong preference for collaboration with form local organisations or researchers who have a deep understanding of Kenya’s Bioscience Landscape.
Team Composition
The core team should include the following profiles:
- Advanced degree in a relevant Bioscience field
- Proven experience in industry and knowledge of research commercialisation/innovation
- Knowledge of Kenyan context with particular focus on the Research and Innovation Ecosystem
- Demonstrated experience managing interdisciplinary teams and ensuring quality assurance in complex studies
- Demonstrated experience in high quality science communication and content design and creative dissemination methods.
4. PROJECT MANAGEMENT ARRANGEMENTS

The Supplier will be responsible for:
- Designing and delivering all research activities
- Producing interim and final outputs for review by FCDO
- Participating in validation workshops and dissemination events
The FCDO will:
- FCDO will chair a study steering committee which will review and sign off all deliverables.
- Deliverables must be shared a minimum of 5 working days in advance for comments.
- Deliverable will not be considered final until FCDO confirm in writing that all comments have been addressed.
- FCDO and the supplier will hold fortnightly update meetings to review progress against the agreed workplan. Additional meetings will be held to discuss ad hoc matters or milestone deliverables.

5. TIMEFRAME, EXPECTED DELIVERABLES, AND OVERALL BUDGET

The study should be completed in a maximum period of 6 months, starting November 2025.
The budget for the study should not exceed £80,000, excluding taxes.
The deliverables and timelines/milestones expected of the Supplier are as follows:
Milestone	Description	Milestone Payments / (% of Overall Budget Amount)	Delivery By
	Inception Report – Methodology and Approach (Phase 1)	20%	November 2025
	Preliminary Findings of Desk Based Analysis (Phase 2)		December 2025
	Draft Analytical Report including Foresight Study with full data analysis, case studies, recommendations, among others	20%	January 2026
	A Detailed Analytical Report and mapping on the state of the Bioscience Sector in Kenya, including a database setting out the status of existing ventures and start-ups in Biosciences in Kenya.	20%	February 2026
	Validation Workshops (Phase 3)		March 2026
	A Policy Brief (max. 4 pages) setting out key recommendations for government, academia, private sector, investors and development partners to maximise the potential for innovation and growth in the sector.		March 2026
	PowerPoint presentation of the report for dissemination purposes. / Set of infographics to visually represent key findings of the report.	40%	April 2026
	Final Report and Dissemination Materials. / Dissemination workshop with key stakeholders to disseminate final study outputs.

6. QUALITY ASSURANCE MECHANISMS

The Supplier will implement internal quality assurance mechanisms and submit outputs for review by the FCDO technical steering group. Peer review and feedback will be incorporated throughout the project.
Peer review/Quality Assurance Required
Peer review/ quality assurance completed in-house by FCDO
Peer review/ quality assurance arranged by the research provider as part of their contract
Independent peer review independently carried out, through a contract with the Fund Manager
Further EqUALS review for all evaluation products

8. COMPETENCIES

It is expected that the core team delivering this work will have the requisite technical and contextual experience in the collation, interpretation, synthesis, and communication of the research findings and recommendations.
9. SUBMISSIONS

The Supplier is required to submit all outputs in accordance with the expectations and page limits set out in sections 4 and 5 above.
10. MANAGEMENT ARRANGEMENTS

1. The Supplier will design and manage this research study, including drawing together the findings for reporting.
2. This project will be administered by a FDCO EARIH lead adviser.
3. The Supplier will quality-assure all outputs before submission to the EARIH lead adviser. The Supplier will be required to comply with FCDO reporting requirements. The Supplier will be responsible for alerting the EARIH lead adviser as early as possible of any emerging issues and risks, to ensure that the project is staying on track.
4. All deliverables will need to be reviewed and approved by the FCDO technical steering group; however, the Supplier is encouraged to embed their own internal mechanisms for quality assurance.
5. The Supplier will be required to review and outline how they plan to manage any potential conflicts of interest identified during proposal development.
6. The Supplier will be required to attend several meetings during all phases of the work, comprising largely of virtual meetings.
11. DUTY OF CARE ARRANGEMENTS

The Supplier should set out duty of care arrangements for any country visits or field-based activities.
12. ETHICAL CONSIDERATIONS, DATA PROTECTION, AND SAFEGUARDING

The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. The FCDO will monitor risk, and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied. The approach will help to promote the adoption of new standards for all organisations in the aid sector.
It is expected that the Supplier will put forward any considerations for ethical approvals required in adherence to the principles outlined in DFID Ethical Guidance for Research, Evaluation and Monitoring Activities and includes safeguarding guidelines.

13. GENERAL DATA PROTECTION REGULATIONS (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Section 15: Interpretation, the clause on Data Protection Laws in Volume 6: Pro Forma Contract of the ITT Application Pack 4.
14. RISK MANAGEMENT

The Supplier will be expected to set out their understanding of the most important anticipated risks in the proposal, with an explanation of their mitigating strategies in a risk matrix.
15. FCDO RESEARCH GUIDANCE DOCUMENTS

DFID VFM guidelines:
www.gov.uk/government/uploads/system/uploads/attachment_data/file/49551/DFID-approach-value-money.pdf
DFID (2013), Research Uptake: a guide for DFID-funded research programmes:
www.gov.uk/government/uploads/system/uploads/attachment_data/file/200088/Research_uptake_guidance.pdf
DFID (2012) DFID Research Open and Enhanced Access Policy.
https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/181176/DFIDResearch-Open-and-Enhanced-Access-Policy.pdf
DFID (2013) How to note: Assessing the Strength of Evidence:
https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/291982/HTN-strength-evidence-march2014.pdf
DFID, Guidance on the Government’s Marketing, Advertising and Communications Spending Controls for Research Programmes: https://www.gov.uk/government/uploads/

Annex 1: Guidance on Communication and Research Uptake Strategy
Stakeholder Mapping and Research Uptake Strategy
	Key communications and research uptake considerations
Audience mapping	Which organisations are the main intended audiences for the research? Who are the key decision-makers in the policy area and are they involved and aware of the research (and how are they involved in the research design and intent)? Are there other actors who may use findings or are involved in this policy area? / Within FCDO – which teams and departments are involved?
Knowledge requirements of stakeholders	What are the evidence gaps that actors are interested in? Are there key statistics or data that can define the research? What new evidence does the research offer to both strategic planning and informing programming?
Decisions to be influenced	What are the key programming decisions that the research will influence – both for FCDO policy teams and country offices? Will the research support decision-making among other actors? E.g., multilateral, and bilateral donors, non-government organisations, regional governments? What decisions are those?
What are the outputs?	Largely defined by the ToR, but what outputs will be produced? I.e., will there be supporting infographics, summary briefs, or single case studies in order to land the research more effectively/efficiently with particular audiences? How do these map to particular stakeholders?
How will outputs be communicated?	How will various audiences be kept abreast or informed about the research? Will different audiences require different communications? What will be the balance of different dissemination techniques: i.e., seminars, emails, social media, meetings, slide decks, use of the internet or published documentation?
Relevance of research products	The communications plan (and research products) should be iterative and reflect research needs from all stakeholders. Considering responses to the points outlined above, how will the research be designed, produced, and disseminated to meet these needs?
How will research impact be measured?	What methods and indicators can be used to measure or assess how useful the research is? I.e., to what extent has it been used and by which audiences, what are the outcomes of the research, and what impact has it had on policy making and programming?