TERMS OF REFERENCE / Understanding Start-up Funding in East Africa: ‘Follow the Money’ and analysing the ‘valley of death’ in the African context / August 2025

1. BACKGROUND

1.1 About the Evidence Fund
The Foreign, Commonwealth & Development Office (FCDO) wants accessible high-quality research, evaluation and evidence products which target policy, country-specific and regional priorities and are available for use by FCDO and the international development sector. FCDO’s Research and Evidence Directorate (RED) has as its mission to develop and deliver new technologies and innovations that can help solve development challenges, test high potential interventions, and support the delivery of His Majesty’s Government (HMG) objectives. The Evidence Fund is a co-ordinated effort to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.

1.2 Details on the Research Context

East Africa has emerged as a key player in Africa’s start-up ecosystem, attracting significant investment flows that fuel innovation and economic growth. In 2024, the region secured approximately $690 million in start-up funding, accounting for 33% of Africa’s total start-up investment. Kenya remains the top destination for funding, attracting $630 million (29% of Africa’s total).

Despite this substantial inflow of funds, questions remain about the sources, mechanisms, modalities, allocation, and ultimate impact of these investments. In addition to exploring where funding comes from and how it is allocated, it is crucial to analyse the mechanisms and modalities used to provide start-up funding, such as angel investment, debt, venture capital, revenue-based financing, in order to understand the dynamics of investment in the region.

Similarly, the transition from accessing seed funding to Series A remains a significant challenge for start-ups in East Africa. Despite the growing interest and investment in the region’s start-up ecosystem, many promising start-ups struggle to scale due to challenges related to access to finance, market expansion, talent acquisition, and ecosystem support.

The UK Kenya Tech Hub, through the East Africa Research and Innovation Hub and Evidence Fund, is commissioning this research to provide an in-depth analysis of start-up funding in East Africa (with a deep dive into Kenya and Tanzania as focus countries). This analysis will provide a better understanding funding sources, recipients, investment criteria, and the overall impact on the start-up (Innovation driven Entrepreneurship) ecosystem as well as uncovering the key barriers and enablers for startups in East Africa to successfully transition from Minimum Viable Product (MVP) to Seed funding, and then Series A funding. The growing perception around grant funding has been that it makes it harder for startups to transition to investment funding or profitability. We seek to understanding if this is true and why and how to better use grant funding to support startups.

2. KEY EVIDENCE GAPS

Despite Kenya’s emergence as a leading destination for start-up investment in Africa—attracting approximately 29% of the continent’s total start-up funding in 2024 (Africa: The Big Deal, 2025)—critical gaps in knowledge and evidence about start-up funding persist. These gaps hinder effective programme design, equitable policy development, and targeted investment strategies. This section outlines the key areas where further research and data collection are needed.

Incomplete Data on Funding Flows
Current datasets (e.g., AVCA, Crunchbase) predominantly capture venture capital deals above US$100,000, excluding smaller sums and early-stage support from accelerators, incubators, impact investors and non-profit organizations. This results in underrepresentation of local and early-stage funders and limited visibility into the full spectrum of start-up financing.

Lack of Intersectional and Demographic Analysis
There is a notable absence of intersectional analysis linking funding outcomes to founder characteristics such as gender, race, education, disability and geographic origin. This gap obscures systemic inequalities and limits the ability to design inclusive interventions.

Limited Evidence on Regional Spillover Effects
While Kenya’s start-up ecosystem is believed to influence neighboring countries, there is no empirical evidence to confirm how this influence happens and whether this impact is positive or negative. The influence could be multi-faceted, spanning policy, culture, markets, funding, talent, and infrastructure. The net impact, positive or negative, remains under-researched, and empirical evidence is needed to understand the mechanisms and outcomes of this influence. Further research is needed to understand regional interdependence and inform policy decisions.

Lifecycle Funding Gaps
There is a shortage of follow-on funding, particularly at Series A and B stages. Commercial capital is retreating from early-stage investments, leaving grants and accelerator funding as the primary sources—often insufficient for scaling. Grants may encourage start-ups to prioritise donor requirements over commercial viability, potentially leading to business models that are less attractive to private investors. This dependency can make it more challenging for start-ups to demonstrate the scalability, profitability, and resilience that commercial capital seeks, thereby impeding their progression to Series A and B funding rounds. Addressing this evidence gap is crucial for understanding how to better support start-ups in becoming investment-ready and attracting commercial capital.

Sectoral Imbalance
Fintech dominates the start-up funding landscape (~50%), while sectors such as health, education, and agrifood remain underfunded despite their social relevance. This imbalance is partly driven by investor preferences for scalable, data-driven ventures. Further research is needed to understand the factors such as scalability, investor preferences, regulatory environment, or technological readiness, that make fintech more attractive to investors, and identifying barriers unique to these underfunded sectors and exploring whether strategies or models from fintech could be adapted to improve their access to funding.

Weak Coordination Among Funders
The startup funding ecosystem suffers from fragmentation and lack of coordination among stakeholders, as well as a siloing of different types of funding partners, a lack of data and evidence and a lack of sharing of information. This leads to inefficiencies and fragmented support for ventures.

Limited Local Investment Participation
Less than 10% of investors in Kenya are locally based. The dominance of US and European capital raises concerns about sustainability, local ownership, and the relevance of investment priorities.

3. OBJECTIVES AND SCOPE OF WORK

3.1. Objectives
Part A: Start-up Finance

1. Map the start-up funding landscape: Identify key sources of start-up funding in East Africa (e.g., venture capital, angel investors, development finance institutions, grants, accelerators, corporate investors, impact investors) and the key mechanisms used (debt, equity, alternative models)
2. Analyse Start-up Funding Recipients, Sectors and Trends: Profile the start-ups receiving funding, including sectors, size, growth stages, and business models. Assess the demographic and gender distribution among funded start-ups. (Special focus on Climate, Fintech, BioScience and AgriTech sectors) Nuanced perception within the ecosystem of funding following founders from the global north as well as Kenya being an expatriate destination.
3. Examine Investment Criteria and Funding Theses: Investigate the selection criteria used by investors to fund start-ups and nuances around the East African market that may not align with dominant funding theses (especially from Silicon Valley).
4. Evaluate the Effectiveness of Start-up Funding: Measure the impact of investments on start-up growth, job creation, and economic contributions. Assess the long-term sustainability and scalability of funded start-ups. Impact on start-ups’ ability to transition from MVP to Seed and Series A.
5. Alignment/misalignment of outcome/objectives of those considered to be most important players in funding and the ecosystem/start-ups. Communicating/miscommunication of expectation as well as competing expectation between funders and startups. What is the cost of misalignment, miscommunication of expectations.
Part B: Start-up Scaling

1. Identify Challenges: Conduct an in-depth analysis of the key challenges that hinder start-ups from transitioning from MVP to seed funding and then to Series A funding, focusing on finance, market access, talent, and ecosystem support. / Problem framing
2. Case Studies: Document successful as well as unsuccessful transitions of start-ups that have progressed to Series A, highlighting key factors that contributed to their growth and sustainability and any challenges or constraints that may have been overcome to do this.
3. Recommendations and Strategies: Develop practical recommendations and actionable strategies for start-ups, investors, policymakers, and ecosystem enablers to bridge the identified gaps and more (expand)
4. Collaboration Opportunities: Identify potential areas for collaboration among stakeholders to address the fragmentation within the ecosystem and create a conducive environment for sustainable funding for scaling start-ups in East Africa.

3.2 Scope
The research will cover start-up funding and scaling challenges across East Africa, focusing on Kenya and Tanzania, but with analysis of start-up funding in Uganda, Rwanda, and Ethiopia as well. It will include mapping funding sources and mechanisms, analysing startup profiles, evaluating investment criteria, and assessing the effectiveness of funding. The study will also explore barriers to scaling from MVP to Series A and document key lessons as captured in a series of successful case studies. The study will investigate the barriers to scaling start-ups from MVP to Series A, documenting key lessons through a series of successful case studies. Additionally, it will examine case studies of failed start-ups, including those that scaled too rapidly or failed after securing Series A funding, to identify common pitfalls and deepen understanding of the factors influencing start-up success and failure.

3.3 Research Questions
1. What are the key sources and mechanism for start-up funding in East Africa (with a deep dive on Kenya and Tanzania)?
2. What are the characteristics of start-ups receiving funding, and what trends can be observed (including demographic analysis and gender of founder etc)?
3. What criteria do investors use to select start-ups for funding?
4. What sources of data and information do investors rely on when selecting start-ups for funding in East Africa?
5. What are the main barriers, (such as information gaps, perceived risk, lack of trust, or absence of bankable initiatives), that deter both local and international investors from investing in the region’s start-ups?
1. In line with the barriers, are perceptions around funding following founders from the global north (and funding influenced by Kenya being an expatriate destination) based on any evidence? What is the impact of these perceptions and how can funding decisions be better informed?
2. What is the impact of grant and VC funding on start-up growth and sustainability?
3. What challenges hinder start-ups from scaling from MVP to Series A?
4. What lessons can be learned from start-ups that have successfully transitioned to Series A (or start-ups that have failed to transition)?

3.3 Research/Evaluation Methodology
The study will use a mixed-methods approach including desk-based research including a thorough literature review and robust analysis of existing data sets, stakeholder interviews, focus group discussions, surveys, and case studies. Both qualitative and quantitative data will be collected and analysed to provide comprehensive insights.

Detailed methodology is to be proposed by the Bidder in the proposal, drawing attention to specific sources of information where relevant. This should include approaches to sourcing appropriate evidence to respond to all objectives/research questions – both literature and (an indication of) key informants. The exact details of the methodology will be finalised in the inception phase.

3.4 Theory of Change
The research assumes that identifying funding gaps and scaling barriers and strengthening the availability of evidence on the start-up ecosystem in East Africa, will inform targeted interventions by stakeholders - investors, accelerators and incubators, government agencies and policy makers, development partners - leading to improved access to finance and support for startups, thereby enhancing their growth and sustainability.

3.5 Required Skills
The Supplier will lead the research design, data collection, analysis, and reporting. FCDO and the East Africa Research and Innovation Hub will provide oversight and strategic guidance. Regular coordination meetings will be held to ensure alignment.

4. PROJECT MANAGEMENT ARRANGEMENTS

The Supplier will be responsible for:

Designing and delivering all research activities

Producing interim and final outputs for review by FCDO

Participating in validation workshops and dissemination events

The FCDO will:

- Chair a study steering committee which will review and sign off all deliverables. Deliverables must be shared a minimum of 5 working days in advance of comments. Deliverable will not be considered final until FCDO confirm all comments have been addressed.
- Hold monthly update meetings to review progress against the agreed workplan. Additional meetings will be held to discuss ad hoc matters or milestone deliverables.

5. TIMEFRAME, EXPECTED DELIVERABLES, AND OVERALL BUDGET

The total budget for the study should not exceed £150,000 including all applicable taxes. The study should be completed within six months from the date of the contract award (October 2025).

Expenses related to travel, workshops and other modes of data collection related to the study should be explicitly built into the budget. The first two weeks is envisaged as an inception phase, to finalise the methodology and confirm the scope of work. The remaining time is to be used in delivering the study, inclusive of time for review and revisions. Fortnightly meetings are to be scheduled to update on the progress

The deliverables and timelines/milestones expected of the Supplier will be finalised during the Inception phase but are expected to follow the approximate schedule below:

Milestone	Description	Milestone Payments / (% of Overall Budget Amount)	Delivery By
	Inception Report	10%	Month 1
	Interim Report	30%	Month 2-3
	Validation Workshop	10%	Month 4
	Final Report	30%	Month 4-5
	Final Dissemination Materials	20%	Month 6

6. QUALITY ASSURANCE MECHANISMS

The Supplier will implement internal quality assurance mechanisms and submit outputs for review by the FCDO technical steering group. Peer review and feedback will be incorporated throughout the project.

Peer review/Quality Assurance Required
Peer review/ quality assurance completed in-house by FCDO
Peer review/ quality assurance arranged by the research provider as part of their contract	X
Independent peer review independently carried out, through a contract with the Fund Manager
Further Equals review for all evaluation products

8. COMPETENCIES

It is expected that the core team delivering this work will have the requisite technical and contextual experience in the collation, interpretation, synthesis, and communication of the research findings and recommendations. The team should also demonstrate previous experience in undertaking similar research collecting, analysing and presenting quantitative and qualitative data with examples. In addition, the supplier should have good knowledge of the start up ecosystem and stakeholders. The supplier should provide clear examples of adequate expertise and contextual understanding and experience in conducting assignments of a similar nature in the four target countries. Collaboration between start-up ecosystem practitioners and established academic experts/thought leaders in the field of innovation systems strengthening is encouraged.

9. SUBMISSIONS

The Supplier is required to submit all outputs in accordance with the expectations and page limits set out in sections 4 and 5 above.

10. MANAGEMENT ARRANGEMENTS

1. The Supplier will design and manage this research study, including drawing together the findings for reporting.
2. This project will be administered by a FDCO EARIH lead adviser.
3. The Supplier will quality-assure all outputs before submission to the EARIH lead adviser. The Supplier will be required to comply with FCDO reporting requirements. The Supplier will be responsible for alerting the EARIH lead adviser as early as possible of any emerging issues and risks, to ensure that the project is staying on track.
4. All deliverables will need to be reviewed and approved by the FCDO technical steering group; however, the Supplier is encouraged to embed their own internal mechanisms for quality assurance.
5. The Supplier will be required to review and outline how they plan to manage any potential conflicts of interest identified during proposal development.
6. The Supplier will be required to attend several meetings during all phases of the work, comprising largely of virtual meetings.

11. DUTY OF CARE ARRANGEMENTS

The Supplier should set out duty of care arrangements for any country visits or field-based activities.

12. ETHICAL CONSIDERATIONS, DATA PROTECTION, AND SAFEGUARDING

Describe any ethical considerations that will be expected of the Supplier. This should include research ethics, safeguarding and child protection, inclusion, and any other relevant ethical considerations, dependent on the type of study and its anticipated participants. This may also include GDPR and other data protection considerations.

The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. The FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied. The approach will help to promote the adoption of new standards for all organisations in the aid sector.

It is expected that the Supplier will put forward any considerations for ethical approvals required in adherence to the principles outlined in DFID Ethical Guidance for Research, Evaluation and Monitoring Activities and includes safeguarding guidelines.

13. GENERAL DATA PROTECTION REGULATIONS (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Section 15: Interpretation, the clause on Data Protection Laws in Volume 6: Pro Forma Contract of the ITT Application Pack.4

14. RISK MANAGEMENT

The Supplier will be expected to set out their understanding of the most important anticipated risks in the proposal, with an explanation of their mitigating strategies in a risk matrix.

15. FCDO RESEARCH GUIDANCE DOCUMENTS

DFID VFM guidelines:
www.gov.uk/government/uploads/system/uploads/attachment_data/file/49551/DFID-approach-value-money.pdf
- DFID (2013), Research Uptake: a guide for DFID-funded research programmes: www.gov.uk/government/uploads/system/uploads/attachment_data/file/200088/Research_uptake_guidance.pdf
- DFID (2012) DFID Research Open and Enhanced Access Policy. https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/181176/DFIDResearch-Open-and-Enhanced-Access-Policy.pdf
- DFID (2013) How to note: assessing the strength of evidence https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/291982/HTN-strength-evidence-march2014.pdf
- DFID, Guidance on the Government’s marketing, advertising and communications spending controls for research programmes: https://www.gov.uk/government/uploads/

Annex 1: Guidance on Communication and Research Uptake Strategy

Stakeholder Mapping and Research Uptake Strategy
	Key communications and research uptake considerations
Audience mapping	Which organisations are the main intended audiences for the research? Who are the key decision-makers in the policy area and are they involved and aware of the research (and how are they involved in the research design and intent)? Are there other actors who may use findings or are involved in this policy area? / Within FCDO – which teams and departments are involved?
Knowledge requirements of stakeholders	What are the evidence gaps that actors are interested in? Are there key statistics or data that can define the research? What new evidence does the research offer to both strategic planning and informing programming?
Decisions to be influenced	What are the key programming decisions that the research will influence – both for FCDO policy teams and country offices? Will the research support decision-making among other actors? E.g., multilateral, and bilateral donors, non-government organisations, regional governments? What decisions are those?
What are the outputs?	Largely defined by the ToR, but what outputs will be produced? I.e., will there be supporting infographics, summary briefs, or single case studies in order to land the research more effectively/efficiently with particular audiences? How do these map to particular stakeholders?
How will outputs be communicated?	How will various audiences be kept abreast or informed about the research? Will different audiences require different communications? What will be the balance of different dissemination techniques: i.e., seminars, emails, social media, meetings, slide decks, use of the internet or published documentation?
Relevance of research products	The communications plan (and research products) should be iterative and reflect research needs from all stakeholders. Considering responses to the points outlined above, how will the research be designed, produced, and disseminated to meet these needs?
How will research impact be measured?	What methods and indicators can be used to measure or assess how useful the research is? I.e., to what extent has it been used and by which audiences, what are the outcomes of the research, and what impact has it had on policy making and programming?