## 2025
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
GS/1680 | Cancelled |  | OPRED | UK SNS Transformation 3D | WesternGeco | 23/17 - 21; 23,25 and 29. 44/21-30 |  | 2024-03-25 | 2024-10-24 |  |  |  | 178 | not stated | Towed Streamer 3D Marine Seismic Survey in an area just south of the Dogger Bank shallows area in the UK Southern North Sea. The maximum survey area size is approximately 5,100sqkm. | 4.76 | 1090cu in |  | 0.017611 | #VALUE!
GS/1822/0 | Completed |  | OPRED | POSTPONED: Rough Storage Geophysical Survey | Centrica Energy Storage Limited | 47/2, 47/3, 4/7 and 47/8 | See application | NEW DATES:Autum/winter 2025-2026 | NEW DATES:Autum/winter 2025-2026 |  |  |  | 11 | 3 | 2D high resolution (2DHR) seismic, ultra high resolution (UHRS) seismic, sub bottom profiler (SBP) pinger, single and multibeam echo-sounders, sidescan sonar, grab sampling and drop-down camera | 586 | 160 cu inch | winter | 2.1681 | 0.035543
MLA/2020/00489 | Approved |  | MMO | Sofia - Unexploded Ordnance Investigations (Sidescan Sonar, Multibeam Echo Sounder and Magnetometer Equipment) | RWE Ltd |  |  |  |  | 2024-10-01 | 2028-05-31 |  |  | 0 | Geophysical Survey | 133.37 |  | Summer | 0 | 0
DCO/2013/00011 | Approved |  | MMO | Sofia - Monopile Installation (Abated) | Sofia Offshore Wind Farm Limited |  |  |  |  | 2025-04-02 | 2025-09-30 |  |  | 56 | Monopiling Abated (Big Bubble Curtain) | 871.58 |  | Summer | 3.2247 | 0.9868
DCO/2013/00011 | Approved |  | MMO | Sofia - Monopile Installation (Unabated) | Sofia Offshore Wind Farm Limited |  |  |  |  | 2025-04-02 | 2025-09-30 |  |  | 56 | Monopiling Unabated | 1928.38 |  | Summer | 7.1347 | 2.1833
MLA/2024/00088 | Completed |  | MMO | Hornsea Three - Unexploded Ordnance Clearance (Low Order) for Transmission Assets. | Orsted |  |  |  |  | 2024-10-01 | 2025-04-15 | 2025-04-15 |  | 24 |  | 79 |  | Summer | 0.29 | 0.04
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Monopile Installation (Unabated) | Scottish Power Renewables |  |  |  |  | 2025-04-17 | 2025-09-30 |  |  | 95 | Monopiling Unabated | 1927 |  | Both | 7.1296 | 3.7012
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Monopile Installation (Abated) | Scottish Power Renewables |  |  |  |  | 2025-04-17 | 2025-09-30 |  |  | 95 | Piling Abated (MENCK Hammer Adaptation) | 1520 |  | Both | 5.6238 | 2.9195
DCO/2018/00001 | Approved |  | MMO | East Anglia Three - Pin Pile Installation | Scottish Power Renewables |  |  |  |  | 2025-07-03 | 2025-07-23 |  |  | 8 | Pin Piling | 706 |  | Both | 2.6121 | 0.11419
DCO/2023/00001 | Completed |  | MMO | Dogger Bank D - Geophysical Survey 1 | SSE Renewables |  |  |  |  | 2025-05-10 | 2025-05-12 | 2025-05-12 |  | 3 | Geophysical Survey | 0.2 |  | Summer | 0.00073997 | 1.2131e-05
DCO/2016/00018 | Approved |  | MMO | Dogger Bank C - Monopile Installation (Unabated) | SSE Renewables |  |  |  |  | 2025-09-02 | 2025-09-04 |  |  | 4 | Monopiling Unabated | 150.7 |  | Summer | 0.55757 | 0.012187
GS/1853 | Completed |  | OPRED | Phase 1 NEP Seismic Survey | BP | 42/25, 42/30, 43/21, 43/26 |  | 2025-02-15 | 2025-04-20 |  |  |  | 30 | 20 | 2DHR seismic survey - SAC work may be completed outside of summer | 798 | 160 cu inch |  | 1.946 | 0.21268
GS/1867 | Approved |  | OPRED | Expansion Seismic: Part 1 (CS07) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 33 | 31 | 3D Seismic survey, MBES, ADCP | 744 | 400 cu in | Summer | 2.753 | 0.5
GS/1866 | Completed |  | OPRED | EPCI Seismic: Part 2 (CS25) (NEP Expansion stores) | BP |  |  | 2025-08-01 | 2025-10-17 |  |  |  | 18 | 18 | 3D Seismic survey, MBES, ADCP | 1473 | 400 cu in | Summer | 5.62 | 0.55279
GS/1872 | Approved |  | OPRED | EPCI 3 Geophysical/ Geotechnical (NEP Cable Nearshore) not in SAC | BP |  |  | 2025-04-24 | 2025-05-01 |  |  |  | 0 | 0 | Sub-bottom profiler, Multibeam, Side scan sonar, Magnetometer |  |  |  | 0.64 | 0
GS/1913 | Approved |  | OPRED | EPCI 1 Geophysical - Pipeline | BP | [7 empty] | 18 | 18 | Sub-bottom profiler, Multibeam, Side scan sonar, Magnetometer |  |  |  | 0.366 | 0.036
GS/1871 | Completed |  | OPRED | EPCI 3 Geophysical/Geotechnical survey (NEP cable Offshore) | BP |  |  | 2025-05-01 | 2025-06-30 |  |  |  | 40 | 121 | SBP/MB/SSS/Magnetometer. Potentially 2 full route runs (148km) in 24hrs) | 121 |  | summer | 0.44768 | 0.29601
DCO/2016/00020 | Approved |  | MMO | Dogger Bank C - Pin Piling | SSE Renewables |  |  |  |  | 2025-04-01 | 2025-04-30 |  |  | 30 | Pin Piling | TCB |  | Summer | #VALUE! | #VALUE!
DCO/2016/00024 | Completed |  | MMO | Dogger Bank B - Monopile Installation (Unabated) | SSE Renewables |  |  |  |  | 2025-04-16 | 2025-04-17 | 2025-04-17 |  | 2 | Monopiling Unabated | 2873 |  | Summer | 10.6297 | 0.11617
GS/1886/0 | Completed |  | OPRED | Pegasus West:Pipeline and site Geophysical Survey (SBP) | Ineos |  |  | 2025-04-16 | 2025-05-05 | 2025-04-21 | 2025-05-26 | 2025-05-26 | 12 | 12 | Sub Bottom profiler | 471 |  | summer | 1.75 | 0.11475
1 | Completed | 21/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a-AAF well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | 2.62 | 0.014317
DR/2528/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- AJ well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2532/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 1 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
DR/2533/0 | Completed | 23/2/25 | OPRED | Cyngus - Conductor driving of the 44/12a- Slot 6 well | ITHACA (NE) E&P LIMITED | 44/12 |  | 2025-02-24 | 2025-04-30 |  |  |  | 1 | 1 | Conductor driving 15km EDR | 706 | 90 kJ | Winter | N/A | N/A
GS/1900/0 | Approved |  | OPRED | Baker and Abbey site Surveys (SBP) and Sleeve Gun. | Petrogas | Outside Summer area but worst case EDR shows possible overlap with Summer area |  | 2025-07-01 | 2025-12-01 |  |  |  | 21 | 10 | Sub Bottom profiler survey | 155 | N/A | Both | 0.57 | 1 | Proportion of Winter area | 2.96%
MLA/2023/00532/3 | Completed |  | MMO | East Anglia Three - Unexploded Ordnanc Clearance (Low Order) | Scottish Power Renewables |  |  |  |  | 2024-07-08 | 2025-04-27 | 2025-04-27 |  | 55 | Low-Order UXO Clearance | 79 |  | Both | 0.62 | 0.19
MLA/2024/00345 | Approved |  | MMO | Norfolk Vanguard West - UXO Investigation Marine Licence Application 1 | RWE Ltd |  |  |  |  | 2025-01-01 | 2025-12-31 |  |  | 365 | Geophysical Survey | 0.00051 |  | Both | 0 | 0
MLA/2024/00419 | Approved |  | MMO | Norfolk Vanguard West - Unexploded Ordnance Investigations Marine Licence Application 2 | RWE Ltd |  |  |  |  | 2025-01-29 | 2026-01-29 |  |  | 365 | Geophysical Survey | 0.000156 |  | Both | 0 | 0
N/A (exemption) |  |  | MMO | National Grid - Electricity Transmission Geophysical Survey | National Grid |  |  |  |  | 2025-05-01 | 2025-05-31 |  | 11 | 11 | Geophysical Survey | 55 |  | Summer | 0 | 0
[15 empty] | Geophysical Survey | 56 |  | Summer | 0 | 0
GS/1976/0 | Approved |  | OPRED | Platypus - SBP survey | Perenco |  |  | 2025-09-15 | 2025-11-30 | 2025-09-15 | 2025-09-30 |  | 15 | 15 | Geophysical Survey | 57 |  | Summer | 1.01 | 0.08

## 2026
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed |  | MMO | Hornsea Three Monopiling | Orsted |  |  | 2026-01-01 | 2027-01-01 | [5 empty] | Piling |  |  | Summer
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this be 2025 or 2024?