## INTRO
The WH:LG Project Change Request Form template is used to capture proposals for changes made to projects as agreed via the MoU, Delivery Assurance Check (DAC), and any subsequent rebaselining. Please liaise with your Delivery Support Manager (DSM) to complete and submit this form. Once you have completed the Form, please submit it to WHLG@turntown.co.uk using the following subject line – CHANGE REQUEST: [Your Grant Recipient Name]/[Your project ID]. Grant Recipients can submit a Project Change Request form anytime after passing their DACs. If you want to make a change before passing a DAC, please check the guidance on DACs as you may be able to make the change as part of the DAC (e.g. confirming suppliers) - if you are unsure, you can contact the DESNZ WH:LG Delivery Team. Please ensure you have spoken to your DSM before submitting a change request, and be aware that deciding whether to grant the change request is at DESNZ and its appointed delivery partners' discretion.
HOW TO:
Change Request Summary
Complete the 'Change Request Summary' tab with all relevant details. This tab needs to be completed before submitting. In sections D to E, ensure you have confirmed you are the authorised representative and sign and date this proposal. Ensure there is a clear summary of changes detailed within Sections B to C. This will only require a brief explanation.
After completing the Change Request Summary, select the tab that is most relevant to your changes and use this to outline your proposed change. Each tab will have clear instructions on how to complete the form and you will also receive support from your allocated point of contact.
TURN AROUND TIMES
The typical turn-around time for a decision on the change request will be 5 - 10 working days. However this may be longer if further information is required or if the change request falls outside of the policy thresholds. In the event that this happens, your change request will be escalated to a board for consideration and this can take up to 30 working days maximum. It is important that Grant Recpipients respond promptly to a request for further information to ensure that the decision-making process remains on schedule. Delays in your replies may impact the timeframe for making a decision.

## 1. Change Request Summary
WH:LG Project Change Request
A. CHANGE REQUEST APPLICANT
| Lead Local Authority |  | Broadland District Council |  |  | OFFICE USE ONLY
| Consortium Name (if part of a consortium) |  | Norfolk Warm Homes |  |  | Account Manager (or equivalent)
| WH:LG Project ID |  | WHLG_008 |  |  | Date Submitted
| Change Requested By | Name | Chris Bailey |  |  | Change Request ID
|  | Phone | 01603 430468 |  |  | Previous Change Request? (Y/N)
|  | Email | chris.bailey@southnorfolkandbroadland.gov.uk
B. SUMMARY OF CHANGES
| Deviation from the approved position. Answer Yes or No to each area if change has been made |  | Select as many options as relevant from the list below: |  |  | Changes made? (Y/N) | Path location:
|  |  | Income verification (any changes to the approach stated in Section 6 of your DAC form) |  |  | N | click here to provide detail of change requested
|  |  | Your consortium (any changes to the table listing consortia members as per your MOU) |  |  | N | click here to provide detail of change requested
|  |  | Primary Suppliers (any changes to the table as per section 3B of your DAC form) |  |  | N | click here to provide detail of change requested
|  |  | Delivery Forecast Plan (only select this option with explicit instruction from DESNZ) |  |  | Y | click here to provide detail of change requested
| Other Changes (Anything not listed above) As this is a non-standard change, further evidence and additional information may be requested. |  | Change from: | Current Y1 allocation (£1,071,429.00)
|  |  | Change to: | Uplift of £238,391.37 to Y1 allocation (£1,309,820.06)
C. DETAILED OVERVIEW OF THE PROPOSED CHANGES (at B or C above)
| What Change Needs To Happen Describe the requested change in as much detail as needed to make the request clear for readers. Use a bullet point list for clarity. (max 500 words) |  |  | We are submitting this change request as per the instructions outlined in DESNZ's letter, advising that our Warm Homes: Local Grant project has been provisionally allocated additional funding via an uplift of £238,391.37 for Financial Year 1 (2025-26) of the scheme.
| Why Change Is Required Overview of reasons necessitating the change. (max 500 words) |  |  | Our original funding award was significantly less than requested, therefore our contractors, assessors and internal team have the capcity and ability to deliver an additional £500k of work in year one and we have submitted a detailed proposal to evidence this. Following the submission of the proposal, we were informed that we could provisionally recieve an uplift of £238,391.37 for Y1 delivery and are confident in achieving this additional delivery.
| Mitigation We expect you to have considered alternative options before submitting a change request. Please outline explicitly any action you have taken to try and minimise the need for this change, particularly for changes to expenditure. (max 500 words) |  |  | N/A
| Implementation Plan Work required to implement the change. (max 500 words) |  |  | Please see the origional re-allocation proposal documents supplied as part of our initial request for re-allocation. We have reviewed our risk and mitigation in line with this uplift and based on our current conversion rates, pipleine and workforce capcity we can facilitate this additional Y1 spend with no further change to contract values or supplementary lead generation activity.
| Implications If Not Approved Resulting impact on outputs and outcomes achievement. (max 500 words) |  |  | Without an uplift in Y1 allocation, fewer Norfolk residents would receive support and there is a risk that underspend across GR's will have to be returned to treasury.
D. DECLARATION
| Individial Applicants Only |  | I have the express authority to fill out this application on behalf of the Grant Recipient.
| Consortium Applicants Only |  | I have the express authority to fill out this application on behalf of the lead organisation and its project partners. |  |  |  | Yes
Additional Comments Where Relevant (max 500 words)
E. SIGNATURE
| Grant Recipient Signature Please sign here to confirm your proposal of changes. This signature will be taken as agreement if changes are approved. |  | Chris Bailey |  | Submit the completed template to WHLG@turntown.co.uk using the following subject line – CHANGE REQUEST: [Your Grant Recipient Name]/[Your project ID]
| Date Signed |  | 2025-10-21

## 2. Income Verification
INCOME VERIFICATION
There are three Eligibility Pathways in WH:LG: Pathway 1: Homes in the most economically deprived neighbourhoods in England (defined as living in an Income Deciles 1-2 of the Indices of Multiple Deprivation). Pathway 2: in receipt of an eligible means tested benefit or meet the ECO 4 Flex Route 2 Criteria Pathway 3: Households with a combined gross income of no more than £36,000 or below the eligible income threshold according to the household composition (income thresholds are set out in the After Housing Costs Equivalisation Tables in the published policy guidance which can be found at:
https://www.gov.uk/government/publications/warm-homes-local-grant).
Acceptable evidence
| Pathway 1 | Postcodes
| Pathway 2 | Means tested benefits
Eco Flex route 2
| Pathways 3 | Payslips
Bank Statements
Tax Returns
Self-assessment Tax Returns
P60s
Pension Statements
Other (please specify)
Please outline how your eligibility criteria and household income varification strategy will be changing. Only add the changes that are being made. Include what has been removed, what has been included and the reason for this change.
What is changing in your use of the three Eligibility Pathways and why?
What changes are there to the evidence that you will use and how it will be collected?

## 3. Consortium Structure
CONSORTIUM STRUCTURE
Please provide the original consortium structure and then the new structure. Please note that adding or removing projects may impact consortium funding levels.
If a consortium member is being removed or added follow these instructions: In the FROM fields, please insert and highlight any lines that will be removed in red In the TO fields, please insert and highlight any new lines in green
FROM | Name of Local Authority | English Region | TO | Name of Local Authority | Name Change | English Region
| If the number of Local Authorities exceeds the number of rows available in the tables above or are not included in the dropdown, please use this text box. Please provide any additional names of Local Authorities, Combined Authorities or Net Zero Hubs their region (if applicable). |  |  | If the number of Local Authorities exceeds the number of rows available in the tables above or are not included in the dropdown, please use this text box. Please provide any additional names of Local Authorities, Combined Authorities or Net Zero Hubs their region (if applicable).
In the text field below, please detail the reasons for the change to your consortium and the impact it will have.

## 4. Suppliers
SUPPLIERS
Only add the changes that are being made to your supplier list from those included in section 3B of your DAC form If there are changes to your supplier, insert the original details / agreement in the FROM fields and add the changes in the TO fields.
For Suppliers contracted by either direct Grant Recipients or by the lead Local Authority / Organisation which will cover the constituent LAs in the case of a consortium.
FROM | Supplier Name (Companies House Name) | Supplier Contract Type | Contract Value (£) | Role in Project | Transferred from HUG 2? | Companies House Registered No. (or enter N/A) | Contract Start Date | Contract End Date | Mobilisation Date | Procurement Methodology and Regulations | Estimated average installs/month | SME | TrustMark No. (if applicable) | MCS No. (if applicable) | PAS 2035 Certified
TO | Supplier Name (Companies House Name) | Supplier Contract Type | Contract Value (£) | Role in Project | Transferred from HUG 2? | Companies House Registered No. (or enter N/A) | Contract Start Date | Contract End Date | Mobilisation Date | Procurement Methodology and Regulations | Estimated average installs/month | SME | TrustMark No. (if applicable) | MCS No. (if applicable) | PAS 2035 Certified
For Suppliers contracted by a consortium member organisation. Please add additional sections if more than one consortium member is changing their contracted supplier/s.
Consortium member name
FROM | Supplier Name (Companies House Name) | Supplier Contract Type | Contract Value (£) | Role in Project | Transferred from HUG 2? | Companies House Registered No. (or enter N/A) | Contract Start Date | Contract End Date | Mobilisation Date | Procurement Methodology and Regulations | Estimated average installs/month | SME | TrustMark No. (if applicable) | MCS No. (if applicable) | PAS 2035 Certified
TO | Supplier Name (Companies House Name) | Supplier Contract Type | Contract Value (£) | Role in Project | Transferred from HUG 2? | Companies House Registered No. (or enter N/A) | Contract Start Date | Contract End Date | Mobilisation Date | Procurement Methodology and Regulations | Estimated average installs/month | SME | TrustMark No. (if applicable) | MCS No. (if applicable) | PAS 2035 Certified

## 5. Delivery Plan
DELIVERY PLAN
This tab should only be completed with explicit instruction from DESNZ and is designed for changes in funding amount or changes to amount of homes being delivered.
In the text field below, please detail the reasons for change to your delivery plan.
As per our re-allocation proposal, we have the capacity, resource and pipleine to facilitate an uplift in delivery. We are completing this change request as per the instruction outlined in the provisional re-allococation letter received from DESNZ. Please note that we have recallibrated our delivery based on actuals to date and estimated delivery based on average property grants. Please note that we have reduced our Y1 property numbers despite an uplift, this is because our actual average grant spend per property is higher that we initially set as part of our DAC.
FROM | Current projected forecast of total number of homes to be upgraded |  | 205
| Current estimated Capital cost of project |  | 3399181.45
| Current estimated Admin and Ancillary cost of project |  | 599855.55
| Current estimated total cost of project |  | 3999037
Homes Submitted
| Month | Validated Homes Signed Up | Retrofit Assessed | Number of Batches | Average Per Batch | All Installation Measures Completed |  | Number of TM Lodgements | Capital Expenditure | A&A Expenditure | Planned Engagement Activities (Optional)
| 2025-04-01 | 5 |  |  |  | 0 |  |  |  | 13480
| 2025-05-01 | 10 | 10 |  |  | 0 |  |  |  | 11480
| 2025-06-01 | 20 | 10 | 4 | 1 | 0 |  |  |  | 11480
| 2025-07-01 | 15 | 15 | 6 | 1 | 4 |  |  | 60714.28 | 14000
| 2025-08-01 | 5 | 10 | 12 | 1 | 6 |  | 4 | 91071.42 | 14000
| 2025-09-01 | 15 | 10 | 12 | 1 | 12 |  | 6 | 182142.84 | 14000
| 2025-10-01 | 15 | 5 | 12 | 1 | 12 |  | 12 | 182142.84 | 15000
| 2025-11-01 | 15 | 5 | 6 | 1 | 12 |  | 12 | 182142.84 | 15314
| 2025-12-01 | 5 |  | 5 | 1 | 6 |  | 12 | 91071.42 | 15000
| 2026-01-01 | 5 | 5 | 3 | 1 | 5 |  | 6 | 75892.85 | 14000
| 2026-02-01 | 10 | 10 |  |  | 3 |  | 5 | 45535.71 | 11480
| 2026-03-01 | 5 | 10 | 7 | 1 | 0 |  | 3 |  | 11480
| End of FY 25/26 | 125 | 90 | 67 |  | 60 |  | 60 | 910714.2 | 160714
| 2026-04-01 | 10 | 15 | 7 | 1 | 7 |  |  | 117315.52 | 18000
| 2026-05-01 | 10 | 15 | 8 | 1 | 7 |  | 7 | 117315.52 | 18000
| 2026-06-01 | 10 | 15 | 9 | 1 | 8 |  | 7 | 134074.88 | 18000
| 2026-07-01 | 10 | 15 | 7 | 1 | 9 |  | 8 | 150834.24 | 18000
| 2026-08-01 | 10 | 15 | 9 | 1 | 7 |  | 9 | 117315.52 | 22000
| 2026-09-01 | 10 |  | 8 | 1 | 9 |  | 7 | 150834.24 | 22000
| 2026-10-01 | 10 |  | 8 | 1 | 8 |  | 9 | 134074.88 | 22000
| 2026-11-01 | 10 |  | 5 | 1 | 8 |  | 8 | 134074.88 | 20000
| 2026-12-01 |  |  | 4 | 1 | 5 |  | 8 | 83796.8 | 16000
| 2027-01-01 |  |  | 3 | 1 | 4 |  | 5 | 67037.44 | 16000
| 2027-02-01 |  |  |  |  | 3 |  | 4 | 50278.08 | 16000
| 2027-03-01 |  |  | 8 | 1 |  |  | 3 |  | 15815
| End of FY 26/27 | 80 | 75 | 76 |  | 75 |  | 75 | 1256952 | 221815
| 2027-04-01 |  | 15 | 8 | 1 | 8 |  |  | 140744.56 | 18000
| 2027-05-01 |  | 15 | 10 | 1 | 8 |  |  | 140744.56 | 18000
| 2027-06-01 |  | 10 | 10 | 1 | 10 |  | 8 | 175930.7 | 18000
| 2027-07-01 |  |  | 7 | 1 | 10 |  | 8 | 175930.7 | 18000
| 2027-08-01 |  |  | 10 | 1 | 7 |  | 10 | 123151.49 | 22000
| 2027-09-01 |  |  | 10 | 1 | 10 |  | 10 | 175930.7 | 22000
| 2027-10-01 |  |  | 9 | 1 | 7 |  | 7 | 123151.49 | 22000
| 2027-11-01 |  |  | 1 | 1 | 8 |  | 10 | 140744.56 | 20000
| 2027-12-01 |  |  |  |  | 2 |  | 7 | 35186.14 | 16000
| 2028-01-01 | Batch System Closes on 31/12/2027 | [5 empty] | 8 |  | 16000
| 2028-02-01 | [6 empty] | 2 |  | 16000
| 2028-03-01 | [8 empty] | 11326
| End of FY 27/28 | 0 | 40 | 65 |  | 70 |  | 70 | 1231514.9 | 217326
| Totals | 205 | 205 | 208 | 0 | 205 |  | 205 | 3399181.1 | 599855
TO | New Projected forecast of total number of homes to be upgraded |  | 193
| New estimated Capital cost of project |  | 3601814.1145
| New estimated Admin and Ancillary cost of project |  | 635614.2555
| New estimated total cost of project |  | 4237428.37
Homes Submitted
| Month | Validated Homes Signed Up | Retrofit Assessed | Number of Batches | Average Per Batch | All Installation Measures Completed |  | Number of TM Lodgements | Capital Expenditure | A&A Expenditure | Planned Engagement Activities (Optional)
| 2025-04-01 | 9 | [6 empty] | 0 | 10854.46
| 2025-05-01 | 13 | 5 | [5 empty] | 180 | 20998.28
| 2025-06-01 | 2 | 5 | 3 | 1 |  |  |  | 490 | 20866.46
| 2025-07-01 | 16 | 10 | 7 | 1 | 4 | 4 | 4 | 150 | 17042.11
| 2025-08-01 | 5 | 10 | 6 | 1 | 3 | 3 | 3 | 26507.26 | 19770.32
| 2025-09-01 | 8 | 10 | 10 | 1 | 4 | 4 | 4 | 76458 | 17545.95
| 2025-10-01 | 10 | 5 | 9 | 1 | 5 |  | 5 | 136427.3047 | 14899.2459
| 2025-11-01 | 20 | 5 | 10 | 1 | 10 |  | 10 | 272854.6093 | 14899.2459
| 2025-12-01 | 20 | 3 | 3 | 1 | 7 |  | 7 | 190998.2265 | 14899.2459
| 2026-01-01 | 10 | 5 |  |  | 10 |  | 10 | 272854.6093 | 14899.2459
| 2026-02-01 | 7 | 10 |  |  | 5 |  | 5 | 136427.3047 | 14899.2459
| 2026-03-01 | 5 | 10 | 4 | 1 |  |  |  |  | 14899.2459
| End of FY 25/26 | 125 | 78 | 52 |  | 48 |  | 48 | 1113347.3145 | 196473.0555
| 2026-04-01 | 10 | 15 | 7 | 1 | 7 |  |  | 117315.52 | 18000
| 2026-05-01 | 10 | 15 | 8 | 1 | 7 |  | 7 | 117315.52 | 18000
| 2026-06-01 | 10 | 15 | 9 | 1 | 8 |  | 7 | 134074.88 | 18000
| 2026-07-01 | 10 | 15 | 7 | 1 | 9 |  | 8 | 150834.24 | 18000
| 2026-08-01 | 10 | 15 | 9 | 1 | 7 |  | 9 | 117315.52 | 22000
| 2026-09-01 | 10 |  | 8 | 1 | 9 |  | 7 | 150834.24 | 22000
| 2026-10-01 | 10 |  | 8 | 1 | 8 |  | 9 | 134074.88 | 22000
| 2026-11-01 | 10 |  | 5 | 1 | 8 |  | 8 | 134074.88 | 20000
| 2026-12-01 |  |  | 4 | 1 | 5 |  | 8 | 83796.8 | 16000
| 2027-01-01 |  |  | 3 | 1 | 4 |  | 5 | 67037.44 | 16000
| 2027-02-01 |  |  |  |  | 3 |  | 4 | 50278.08 | 16000
| 2027-03-01 |  |  | 8 | 1 |  |  | 3 |  | 15815
| End of FY 26/27 | 80 | 75 | 76 |  | 75 |  | 75 | 1256952 | 221815
| 2027-04-01 |  | 15 | 8 | 1 | 8 |  |  | 140744.56 | 18000
| 2027-05-01 |  | 15 | 10 | 1 | 8 |  |  | 140744.56 | 18000
| 2027-06-01 |  | 10 | 10 | 1 | 10 |  | 8 | 175930.7 | 18000
| 2027-07-01 |  |  | 7 | 1 | 10 |  | 8 | 175930.7 | 18000
| 2027-08-01 |  |  | 10 | 1 | 7 |  | 10 | 123151.49 | 22000
| 2027-09-01 |  |  | 10 | 1 | 10 |  | 10 | 175930.7 | 22000
| 2027-10-01 |  |  | 9 | 1 | 7 |  | 7 | 123151.49 | 22000
| 2027-11-01 |  |  | 1 | 1 | 8 |  | 10 | 140744.56 | 20000
| 2027-12-01 |  |  |  |  | 2 |  | 7 | 35186.24 | 16000
| 2028-01-01 | Batch System Closes on 31/12/2027 | [5 empty] | 8 |  | 16000
| 2028-02-01 | [6 empty] | 2 |  | 16000
| 2028-03-01 | [8 empty] | 11326
| End of FY 27/28 | 0 | 40 | 65 |  | 70 |  | 70 | 1231515 | 217326
| Totals | 205 | 193 | 193 | 0 | 193 |  | 193 | 3601814.3145 | 635614.0555
This question is only required for Grant Recipients who wish to make a reduction to their funding allocation.
Please provide details if your requested capital funding has changed since the allocation provided to you and you wish to return funding to DESNZ (e.g. consortium member withdrawal, reduced scope of homes targeted etc.). At this stage we are not considering requests for additional funding.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this one's tricky - feels a bit extreme to hold them to each month's delivery being the exact number of homes that they forecast (e.g. if a home slips back a month it feels disproportionate to go through a whole change control process), but at the same time there definitely is a point (at minimum if they're timing out to deliver their funding within a given financial year) where we would need a change request to be filled out. how far along are we on the thinking on this/have HUG2 or SHF W2 got an approach that we could borrow re. the tolerances/process for this? Reply: Hmm, if it helps. This is the delivery profile information requested at DAC Reply: First thing to say is that slippage of homes between months should be captured in the delivery reports/monthly forecasting submitted to the DMS by GRs. As we won’t need to claw back funds, there isn’t really an urgent need to go through a change control process for scaling back projects. Reply: Added a suggestion for how we might approach it. At the top of the tab

## Validation (hidden)
LA Code | LA Name | Region | Rural-Urban Classification
E07000223 | Adur | South East | Urban with City and Town
E07000026 | Allerdale | North West | Mainly Rural
E07000032 | Amber Valley | East Midlands | Urban with Minor Conurbation
E07000224 | Arun | South East | Urban with City and Town
E07000170 | Ashfield | East Midlands | Urban with City and Town
E07000105 | Ashford | South East | Urban with Significant Rural
E07000200 | Babergh | East of England | Mainly Rural
E09000002 | Barking and Dagenham | London | Urban with Major Conurbation
E09000003 | Barnet | London | Urban with Major Conurbation
E08000016 | Barnsley | Yorkshire and The Humber | Urban with Minor Conurbation
E07000027 | Barrow-in-Furness | North West | Urban with Significant Rural
E07000066 | Basildon | East of England | Urban with City and Town
E07000084 | Basingstoke and Deane | South East | Urban with Significant Rural
E07000171 | Bassetlaw | East Midlands | Largely Rural
E06000022 | Bath and North East Somerset | South West | Urban with Significant Rural
E06000055 | Bedford | East of England | Urban with Significant Rural
E09000004 | Bexley | London | Urban with Major Conurbation
E08000025 | Birmingham | West Midlands | Urban with Major Conurbation
E07000129 | Blaby | East Midlands | Urban with City and Town
E06000008 | Blackburn with Darwen | North West | Urban with City and Town
E06000009 | Blackpool | North West | Urban with City and Town
E07000033 | Bolsover | East Midlands | Urban with Significant Rural
E08000001 | Bolton | North West | Urban with Major Conurbation
E07000136 | Boston | East Midlands | Urban with Significant Rural
E06000058 | Bournemouth, Christchurch and Poole | South West | Urban with City and Town
E06000036 | Bracknell Forest | South East | Urban with City and Town
E08000032 | Bradford | Yorkshire and The Humber | Urban with Major Conurbation
E07000067 | Braintree | East of England | Largely Rural
E07000143 | Breckland | East of England | Mainly Rural
E09000005 | Brent | London | Urban with Major Conurbation
E07000068 | Brentwood | East of England | Urban with Significant Rural
E06000043 | Brighton and Hove | South East | Urban with City and Town
E06000023 | Bristol, City of | South West | Urban with City and Town
E07000144 | Broadland | East of England | Urban with Significant Rural
E09000006 | Bromley | London | Urban with Major Conurbation
E07000234 | Bromsgrove | West Midlands | Urban with City and Town
E07000095 | Broxbourne | East of England | Urban with Major Conurbation
E07000172 | Broxtowe | East Midlands | Urban with Minor Conurbation
E06000060 | Buckinghamshire | South East | Urban with Significant Rural
E07000117 | Burnley | North West | Urban with City and Town
E08000002 | Bury | North West | Urban with Major Conurbation
E08000033 | Calderdale | Yorkshire and The Humber | Urban with Major Conurbation
E07000008 | Cambridge | East of England | Urban with City and Town
E09000007 | Camden | London | Urban with Major Conurbation
E07000192 | Cannock Chase | West Midlands | Urban with Significant Rural
E07000106 | Canterbury | South East | Urban with City and Town
E07000028 | Carlisle | North West | Urban with Significant Rural
E07000069 | Castle Point | East of England | Urban with City and Town
E06000056 | Central Bedfordshire | East of England | Largely Rural
E07000130 | Charnwood | East Midlands | Urban with City and Town
E07000070 | Chelmsford | East of England | Urban with City and Town
E07000078 | Cheltenham | South West | Urban with City and Town
E07000177 | Cherwell | South East | Urban with Significant Rural
E06000049 | Cheshire East | North West | Urban with Significant Rural
E06000050 | Cheshire West and Chester | North West | Urban with Significant Rural
E07000034 | Chesterfield | East Midlands | Urban with City and Town
E07000225 | Chichester | South East | Largely Rural
E07000118 | Chorley | North West | Urban with Significant Rural
E09000001 | City of London | London | Urban with Major Conurbation
E07000071 | Colchester | East of England | Urban with Significant Rural
E07000029 | Copeland | North West | Mainly Rural
E06000052 | Cornwall | South West | Mainly Rural
E07000079 | Cotswold | South West | Mainly Rural
E06000047 | County Durham | North East | Largely Rural
E08000026 | Coventry | West Midlands | Urban with City and Town
E07000163 | Craven | Yorkshire and The Humber | Mainly Rural
E07000226 | Crawley | South East | Urban with City and Town
E09000008 | Croydon | London | Urban with Major Conurbation
E07000096 | Dacorum | East of England | Urban with Significant Rural
E06000005 | Darlington | North East | Urban with City and Town
E07000107 | Dartford | South East | Urban with Major Conurbation
E06000015 | Derby | East Midlands | Urban with City and Town
E07000035 | Derbyshire Dales | East Midlands | Mainly Rural
E08000017 | Doncaster | Yorkshire and The Humber | Urban with Minor Conurbation
E06000059 | Dorset | South West | Largely Rural
E07000108 | Dover | South East | Urban with Significant Rural
E08000027 | Dudley | West Midlands | Urban with Major Conurbation
E09000009 | Ealing | London | Urban with Major Conurbation
E07000009 | East Cambridgeshire | East of England | Mainly Rural
E07000040 | East Devon | South West | Largely Rural
E07000085 | East Hampshire | South East | Mainly Rural
E07000242 | East Hertfordshire | East of England | Urban with Significant Rural
E07000137 | East Lindsey | East Midlands | Mainly Rural
E06000011 | East Riding of Yorkshire | Yorkshire and The Humber | Largely Rural
E07000193 | East Staffordshire | West Midlands | Urban with Significant Rural
E07000244 | East Suffolk | East of England | Largely Rural
E07000061 | Eastbourne | South East | Urban with City and Town
E07000086 | Eastleigh | South East | Urban with City and Town
E07000030 | Eden | North West | Mainly Rural
E07000207 | Elmbridge | South East | Urban with Major Conurbation
E09000010 | Enfield | London | Urban with Major Conurbation
E07000072 | Epping Forest | East of England | Urban with Significant Rural
E07000208 | Epsom and Ewell | South East | Urban with Major Conurbation
E07000036 | Erewash | East Midlands | Urban with Minor Conurbation
E07000041 | Exeter | South West | Urban with City and Town
E07000087 | Fareham | South East | Urban with City and Town
E07000010 | Fenland | East of England | Largely Rural
E07000112 | Folkestone and Hythe | South East | Urban with Significant Rural
E07000080 | Forest of Dean | South West | Mainly Rural
E07000119 | Fylde | North West | Urban with City and Town
E08000037 | Gateshead | North East | Urban with Major Conurbation
E07000173 | Gedling | East Midlands | Urban with Minor Conurbation
E07000081 | Gloucester | South West | Urban with City and Town
E07000088 | Gosport | South East | Urban with City and Town
E07000109 | Gravesham | South East | Urban with Major Conurbation
E07000145 | Great Yarmouth | East of England | Urban with Significant Rural
E09000011 | Greenwich | London | Urban with Major Conurbation
E07000209 | Guildford | South East | Urban with City and Town
E09000012 | Hackney | London | Urban with Major Conurbation
E06000006 | Halton | North West | Urban with City and Town
E07000164 | Hambleton | Yorkshire and The Humber | Mainly Rural
E09000013 | Hammersmith and Fulham | London | Urban with Major Conurbation
E07000131 | Harborough | East Midlands | Mainly Rural
E09000014 | Haringey | London | Urban with Major Conurbation
E07000073 | Harlow | East of England | Urban with City and Town
E07000165 | Harrogate | Yorkshire and The Humber | Urban with Significant Rural
E09000015 | Harrow | London | Urban with Major Conurbation
E07000089 | Hart | South East | Urban with Significant Rural
E06000001 | Hartlepool | North East | Urban with City and Town
E07000062 | Hastings | South East | Urban with City and Town
E07000090 | Havant | South East | Urban with City and Town
E09000016 | Havering | London | Urban with Major Conurbation
E06000019 | Herefordshire, County of | West Midlands | Largely Rural
E07000098 | Hertsmere | East of England | Urban with Major Conurbation
E07000037 | High Peak | East Midlands | Largely Rural
E09000017 | Hillingdon | London | Urban with Major Conurbation
E07000132 | Hinckley and Bosworth | East Midlands | Largely Rural
E07000227 | Horsham | South East | Largely Rural
E09000018 | Hounslow | London | Urban with Major Conurbation
E07000011 | Huntingdonshire | East of England | Mainly Rural
E07000120 | Hyndburn | North West | Urban with City and Town
E07000202 | Ipswich | East of England | Urban with City and Town
E06000046 | Isle of Wight | South East | Mainly Rural
E06000053 | Isles of Scilly | South West | Mainly Rural
E09000019 | Islington | London | Urban with Major Conurbation
E09000020 | Kensington and Chelsea | London | Urban with Major Conurbation
E07000146 | King's Lynn and West Norfolk | East of England | Largely Rural
E06000010 | Kingston upon Hull, City of | Yorkshire and The Humber | Urban with City and Town
E09000021 | Kingston upon Thames | London | Urban with Major Conurbation
E08000034 | Kirklees | Yorkshire and The Humber | Urban with Major Conurbation
E08000011 | Knowsley | North West | Urban with Major Conurbation
E09000022 | Lambeth | London | Urban with Major Conurbation
E07000121 | Lancaster | North West | Urban with Significant Rural
E08000035 | Leeds | Yorkshire and The Humber | Urban with Major Conurbation
E06000016 | Leicester | East Midlands | Urban with City and Town
E07000063 | Lewes | South East | Urban with Significant Rural
E09000023 | Lewisham | London | Urban with Major Conurbation
E07000194 | Lichfield | West Midlands | Urban with Significant Rural
E07000138 | Lincoln | East Midlands | Urban with City and Town
E08000012 | Liverpool | North West | Urban with Major Conurbation
E06000032 | Luton | East of England | Urban with City and Town
E07000110 | Maidstone | South East | Urban with Significant Rural
E07000074 | Maldon | East of England | Mainly Rural
E07000235 | Malvern Hills | West Midlands | Largely Rural
E08000003 | Manchester | North West | Urban with Major Conurbation
E07000174 | Mansfield | East Midlands | Urban with City and Town
E06000035 | Medway | South East | Urban with City and Town
E07000133 | Melton | East Midlands | Mainly Rural
E07000187 | Mendip | South West | Mainly Rural
E09000024 | Merton | London | Urban with Major Conurbation
E07000042 | Mid Devon | South West | Mainly Rural
E07000203 | Mid Suffolk | East of England | Mainly Rural
E07000228 | Mid Sussex | South East | Urban with City and Town
E06000002 | Middlesbrough | North East | Urban with City and Town
E06000042 | Milton Keynes | South East | Urban with City and Town
E07000210 | Mole Valley | South East | Urban with Significant Rural
E07000091 | New Forest | South East | Urban with Significant Rural
E07000175 | Newark and Sherwood | East Midlands | Largely Rural
E08000021 | Newcastle upon Tyne | North East | Urban with Major Conurbation
E07000195 | Newcastle-under-Lyme | West Midlands | Urban with City and Town
E09000025 | Newham | London | Urban with Major Conurbation
E07000043 | North Devon | South West | Largely Rural
E07000038 | North East Derbyshire | East Midlands | Urban with City and Town
E06000012 | North East Lincolnshire | Yorkshire and The Humber | Urban with City and Town
E07000099 | North Hertfordshire | East of England | Urban with Significant Rural
E07000139 | North Kesteven | East Midlands | Mainly Rural
E06000013 | North Lincolnshire | Yorkshire and The Humber | Urban with Significant Rural
E07000147 | North Norfolk | East of England | Mainly Rural
E06000061 | North Northamptonshire | East Midlands | Urban with Significant Rural
E06000024 | North Somerset | South West | Urban with Significant Rural
E08000022 | North Tyneside | North East | Urban with Major Conurbation
E07000218 | North Warwickshire | West Midlands | Mainly Rural
E07000134 | North West Leicestershire | East Midlands | Largely Rural
E06000057 | Northumberland | North East | Largely Rural
E07000148 | Norwich | East of England | Urban with City and Town
E06000018 | Nottingham | East Midlands | Urban with Minor Conurbation
E07000219 | Nuneaton and Bedworth | West Midlands | Urban with City and Town
E07000135 | Oadby and Wigston | East Midlands | Urban with City and Town
E08000004 | Oldham | North West | Urban with Major Conurbation
E07000178 | Oxford | South East | Urban with City and Town
E07000122 | Pendle | North West | Urban with City and Town
E06000031 | Peterborough | East of England | Urban with City and Town
E06000026 | Plymouth | South West | Urban with City and Town
E06000044 | Portsmouth | South East | Urban with City and Town
E07000123 | Preston | North West | Urban with City and Town
E06000038 | Reading | South East | Urban with City and Town
E09000026 | Redbridge | London | Urban with Major Conurbation
E06000003 | Redcar and Cleveland | North East | Urban with Significant Rural
E07000236 | Redditch | West Midlands | Urban with City and Town
E07000211 | Reigate and Banstead | South East | Urban with City and Town
E07000124 | Ribble Valley | North West | Mainly Rural
E09000027 | Richmond upon Thames | London | Urban with Major Conurbation
E07000166 | Richmondshire | Yorkshire and The Humber | Mainly Rural
E08000005 | Rochdale | North West | Urban with Major Conurbation
E07000075 | Rochford | East of England | Urban with City and Town
E07000125 | Rossendale | North West | Urban with City and Town
E07000064 | Rother | South East | Largely Rural
E08000018 | Rotherham | Yorkshire and The Humber | Urban with Minor Conurbation
E07000220 | Rugby | West Midlands | Urban with City and Town
E07000212 | Runnymede | South East | Urban with Major Conurbation
E07000176 | Rushcliffe | East Midlands | Largely Rural
E07000092 | Rushmoor | South East | Urban with City and Town
E06000017 | Rutland | East Midlands | Mainly Rural
E07000167 | Ryedale | Yorkshire and The Humber | Mainly Rural
E08000006 | Salford | North West | Urban with Major Conurbation
E08000028 | Sandwell | West Midlands | Urban with Major Conurbation
E07000168 | Scarborough | Yorkshire and The Humber | Urban with Significant Rural
E07000188 | Sedgemoor | South West | Largely Rural
E08000014 | Sefton | North West | Urban with Major Conurbation
E07000169 | Selby | Yorkshire and The Humber | Mainly Rural
E07000111 | Sevenoaks | South East | Largely Rural
E08000019 | Sheffield | Yorkshire and The Humber | Urban with Minor Conurbation
E06000051 | Shropshire | West Midlands | Largely Rural
E06000039 | Slough | South East | Urban with City and Town
E08000029 | Solihull | West Midlands | Urban with Major Conurbation
E07000246 | Somerset West and Taunton | South West | Largely Rural
E07000012 | South Cambridgeshire | East of England | Largely Rural
E07000039 | South Derbyshire | East Midlands | Urban with Significant Rural
E06000025 | South Gloucestershire | South West | Urban with City and Town
E07000044 | South Hams | South West | Mainly Rural
E07000140 | South Holland | East Midlands | Largely Rural
E07000141 | South Kesteven | East Midlands | Largely Rural
E07000031 | South Lakeland | North West | Mainly Rural
E07000149 | South Norfolk | East of England | Mainly Rural
E07000179 | South Oxfordshire | South East | Mainly Rural
E07000126 | South Ribble | North West | Urban with City and Town
E07000189 | South Somerset | South West | Largely Rural
E07000196 | South Staffordshire | West Midlands | Urban with Significant Rural
E08000023 | South Tyneside | North East | Urban with Major Conurbation
E06000045 | Southampton | South East | Urban with City and Town
E06000033 | Southend-on-Sea | East of England | Urban with City and Town
E09000028 | Southwark | London | Urban with Major Conurbation
E07000213 | Spelthorne | South East | Urban with Major Conurbation
E07000240 | St Albans | East of England | Urban with City and Town
E08000013 | St. Helens | North West | Urban with Major Conurbation
E07000197 | Stafford | West Midlands | Urban with Significant Rural
E07000198 | Staffordshire Moorlands | West Midlands | Largely Rural
E07000243 | Stevenage | East of England | Urban with City and Town
E08000007 | Stockport | North West | Urban with Major Conurbation
E06000004 | Stockton-on-Tees | North East | Urban with City and Town
E06000021 | Stoke-on-Trent | West Midlands | Urban with City and Town
E07000221 | Stratford-on-Avon | West Midlands | Mainly Rural
E07000082 | Stroud | South West | Urban with Significant Rural
E08000024 | Sunderland | North East | Urban with Major Conurbation
E07000214 | Surrey Heath | South East | Urban with City and Town
E09000029 | Sutton | London | Urban with Major Conurbation
E07000113 | Swale | South East | Largely Rural
E06000030 | Swindon | South West | Urban with City and Town
E08000008 | Tameside | North West | Urban with Major Conurbation
E07000199 | Tamworth | West Midlands | Urban with City and Town
E07000215 | Tandridge | South East | Urban with Significant Rural
E07000045 | Teignbridge | South West | Largely Rural
E06000020 | Telford and Wrekin | West Midlands | Urban with City and Town
E07000076 | Tendring | East of England | Largely Rural
E07000093 | Test Valley | South East | Urban with Significant Rural
E07000083 | Tewkesbury | South West | Largely Rural
E07000114 | Thanet | South East | Urban with City and Town
E07000102 | Three Rivers | East of England | Urban with Major Conurbation
E06000034 | Thurrock | East of England | Urban with Major Conurbation
E07000115 | Tonbridge and Malling | South East | Urban with Significant Rural
E06000027 | Torbay | South West | Urban with City and Town
E07000046 | Torridge | South West | Mainly Rural
E09000030 | Tower Hamlets | London | Urban with Major Conurbation
E08000009 | Trafford | North West | Urban with Major Conurbation
E07000116 | Tunbridge Wells | South East | Urban with Significant Rural
E07000077 | Uttlesford | East of England | Mainly Rural
E07000180 | Vale of White Horse | South East | Largely Rural
E08000036 | Wakefield | Yorkshire and The Humber | Urban with City and Town
E08000030 | Walsall | West Midlands | Urban with Major Conurbation
E09000031 | Waltham Forest | London | Urban with Major Conurbation
E09000032 | Wandsworth | London | Urban with Major Conurbation
E06000007 | Warrington | North West | Urban with City and Town
E07000222 | Warwick | West Midlands | Urban with City and Town
E07000103 | Watford | East of England | Urban with Major Conurbation
E07000216 | Waverley | South East | Largely Rural
E07000065 | Wealden | South East | Mainly Rural
E07000241 | Welwyn Hatfield | East of England | Urban with City and Town
E06000037 | West Berkshire | South East | Urban with Significant Rural
E07000047 | West Devon | South West | Mainly Rural
E07000127 | West Lancashire | North West | Urban with Significant Rural
E07000142 | West Lindsey | East Midlands | Mainly Rural
E06000062 | West Northamptonshire | East Midlands | Urban with Significant Rural
E07000181 | West Oxfordshire | South East | Mainly Rural
E07000245 | West Suffolk | East of England | Largely Rural
E09000033 | Westminster | London | Urban with Major Conurbation
E08000010 | Wigan | North West | Urban with Major Conurbation
E06000054 | Wiltshire | South West | Largely Rural
E07000094 | Winchester | South East | Largely Rural
E06000040 | Windsor and Maidenhead | South East | Urban with City and Town
E08000015 | Wirral | North West | Urban with Major Conurbation
E07000217 | Woking | South East | Urban with Major Conurbation
E06000041 | Wokingham | South East | Urban with City and Town
E08000031 | Wolverhampton | West Midlands | Urban with Major Conurbation
E07000237 | Worcester | West Midlands | Urban with City and Town
E07000229 | Worthing | South East | Urban with City and Town
E07000238 | Wychavon | West Midlands | Mainly Rural
E07000128 | Wyre | North West | Largely Rural
E07000239 | Wyre Forest | West Midlands | Urban with Significant Rural
E06000014 | York | Yorkshire and The Humber | Urban with City and Town

## Data Validation (hidden)
LA Code | LA Name | Region | Rural-Urban Classification | Region | Rural-Urban Classification
E07000223 | Adur | South East | Urban with City and Town | East Midlands | Largely Rural
E07000026 | Allerdale | North West | Mainly Rural | East of England | Mainly Rural
E07000032 | Amber Valley | East Midlands | Urban with Minor Conurbation | London | Urban with City and Town
E07000224 | Arun | South East | Urban with City and Town | North East | Urban with Major Conurbation
E07000170 | Ashfield | East Midlands | Urban with City and Town | North West | Urban with Minor Conurbation
E07000105 | Ashford | South East | Urban with Significant Rural | South East | Urban with Significant Rural
E07000200 | Babergh | East of England | Mainly Rural | South West
E09000002 | Barking and Dagenham | London | Urban with Major Conurbation | West Midlands
E09000003 | Barnet | London | Urban with Major Conurbation | Yorkshire and The Humber
E08000016 | Barnsley | Yorkshire and The Humber | Urban with Minor Conurbation
E07000027 | Barrow-in-Furness | North West | Urban with Significant Rural
E07000066 | Basildon | East of England | Urban with City and Town
E07000084 | Basingstoke and Deane | South East | Urban with Significant Rural
E07000171 | Bassetlaw | East Midlands | Largely Rural
E06000022 | Bath and North East Somerset | South West | Urban with Significant Rural
E06000055 | Bedford | East of England | Urban with Significant Rural
E09000004 | Bexley | London | Urban with Major Conurbation
E08000025 | Birmingham | West Midlands | Urban with Major Conurbation
E07000129 | Blaby | East Midlands | Urban with City and Town
E06000008 | Blackburn with Darwen | North West | Urban with City and Town
E06000009 | Blackpool | North West | Urban with City and Town
E07000033 | Bolsover | East Midlands | Urban with Significant Rural
E08000001 | Bolton | North West | Urban with Major Conurbation
E07000136 | Boston | East Midlands | Urban with Significant Rural
E06000058 | Bournemouth, Christchurch and Poole | South West | Urban with City and Town
E06000036 | Bracknell Forest | South East | Urban with City and Town
E08000032 | Bradford | Yorkshire and The Humber | Urban with Major Conurbation
E07000067 | Braintree | East of England | Largely Rural
E07000143 | Breckland | East of England | Mainly Rural
E09000005 | Brent | London | Urban with Major Conurbation
E07000068 | Brentwood | East of England | Urban with Significant Rural
E06000043 | Brighton and Hove | South East | Urban with City and Town
E06000023 | Bristol, City of | South West | Urban with City and Town
E07000144 | Broadland | East of England | Urban with Significant Rural
E09000006 | Bromley | London | Urban with Major Conurbation
E07000234 | Bromsgrove | West Midlands | Urban with City and Town
E07000095 | Broxbourne | East of England | Urban with Major Conurbation
E07000172 | Broxtowe | East Midlands | Urban with Minor Conurbation
E06000060 | Buckinghamshire | South East | Urban with Significant Rural
E07000117 | Burnley | North West | Urban with City and Town
E08000002 | Bury | North West | Urban with Major Conurbation
E08000033 | Calderdale | Yorkshire and The Humber | Urban with Major Conurbation
E07000008 | Cambridge | East of England | Urban with City and Town
E09000007 | Camden | London | Urban with Major Conurbation
E07000192 | Cannock Chase | West Midlands | Urban with Significant Rural
E07000106 | Canterbury | South East | Urban with City and Town
E07000028 | Carlisle | North West | Urban with Significant Rural
E07000069 | Castle Point | East of England | Urban with City and Town
E06000056 | Central Bedfordshire | East of England | Largely Rural
E07000130 | Charnwood | East Midlands | Urban with City and Town
E07000070 | Chelmsford | East of England | Urban with City and Town
E07000078 | Cheltenham | South West | Urban with City and Town
E07000177 | Cherwell | South East | Urban with Significant Rural
E06000049 | Cheshire East | North West | Urban with Significant Rural
E06000050 | Cheshire West and Chester | North West | Urban with Significant Rural
E07000034 | Chesterfield | East Midlands | Urban with City and Town
E07000225 | Chichester | South East | Largely Rural
E07000118 | Chorley | North West | Urban with Significant Rural
E09000001 | City of London | London | Urban with Major Conurbation
E07000071 | Colchester | East of England | Urban with Significant Rural
E07000029 | Copeland | North West | Mainly Rural
E06000052 | Cornwall | South West | Mainly Rural
E07000079 | Cotswold | South West | Mainly Rural
E06000047 | County Durham | North East | Largely Rural
E08000026 | Coventry | West Midlands | Urban with City and Town
E07000163 | Craven | Yorkshire and The Humber | Mainly Rural
E07000226 | Crawley | South East | Urban with City and Town
E09000008 | Croydon | London | Urban with Major Conurbation
E07000096 | Dacorum | East of England | Urban with Significant Rural
E06000005 | Darlington | North East | Urban with City and Town
E07000107 | Dartford | South East | Urban with Major Conurbation
E06000015 | Derby | East Midlands | Urban with City and Town
E07000035 | Derbyshire Dales | East Midlands | Mainly Rural
E08000017 | Doncaster | Yorkshire and The Humber | Urban with Minor Conurbation
E06000059 | Dorset | South West | Largely Rural
E07000108 | Dover | South East | Urban with Significant Rural
E08000027 | Dudley | West Midlands | Urban with Major Conurbation
E09000009 | Ealing | London | Urban with Major Conurbation
E07000009 | East Cambridgeshire | East of England | Mainly Rural
E07000040 | East Devon | South West | Largely Rural
E07000085 | East Hampshire | South East | Mainly Rural
E07000242 | East Hertfordshire | East of England | Urban with Significant Rural
E07000137 | East Lindsey | East Midlands | Mainly Rural
E06000011 | East Riding of Yorkshire | Yorkshire and The Humber | Largely Rural
E07000193 | East Staffordshire | West Midlands | Urban with Significant Rural
E07000244 | East Suffolk | East of England | Largely Rural
E07000061 | Eastbourne | South East | Urban with City and Town
E07000086 | Eastleigh | South East | Urban with City and Town
E07000030 | Eden | North West | Mainly Rural
E07000207 | Elmbridge | South East | Urban with Major Conurbation
E09000010 | Enfield | London | Urban with Major Conurbation
E07000072 | Epping Forest | East of England | Urban with Significant Rural
E07000208 | Epsom and Ewell | South East | Urban with Major Conurbation
E07000036 | Erewash | East Midlands | Urban with Minor Conurbation
E07000041 | Exeter | South West | Urban with City and Town
E07000087 | Fareham | South East | Urban with City and Town
E07000010 | Fenland | East of England | Largely Rural
E07000112 | Folkestone and Hythe | South East | Urban with Significant Rural
E07000080 | Forest of Dean | South West | Mainly Rural
E07000119 | Fylde | North West | Urban with City and Town
E08000037 | Gateshead | North East | Urban with Major Conurbation
E07000173 | Gedling | East Midlands | Urban with Minor Conurbation
E07000081 | Gloucester | South West | Urban with City and Town
E07000088 | Gosport | South East | Urban with City and Town
E07000109 | Gravesham | South East | Urban with Major Conurbation
E07000145 | Great Yarmouth | East of England | Urban with Significant Rural
E09000011 | Greenwich | London | Urban with Major Conurbation
E07000209 | Guildford | South East | Urban with City and Town
E09000012 | Hackney | London | Urban with Major Conurbation
E06000006 | Halton | North West | Urban with City and Town
E07000164 | Hambleton | Yorkshire and The Humber | Mainly Rural
E09000013 | Hammersmith and Fulham | London | Urban with Major Conurbation
E07000131 | Harborough | East Midlands | Mainly Rural
E09000014 | Haringey | London | Urban with Major Conurbation
E07000073 | Harlow | East of England | Urban with City and Town
E07000165 | Harrogate | Yorkshire and The Humber | Urban with Significant Rural
E09000015 | Harrow | London | Urban with Major Conurbation
E07000089 | Hart | South East | Urban with Significant Rural
E06000001 | Hartlepool | North East | Urban with City and Town
E07000062 | Hastings | South East | Urban with City and Town
E07000090 | Havant | South East | Urban with City and Town
E09000016 | Havering | London | Urban with Major Conurbation
E06000019 | Herefordshire, County of | West Midlands | Largely Rural
E07000098 | Hertsmere | East of England | Urban with Major Conurbation
E07000037 | High Peak | East Midlands | Largely Rural
E09000017 | Hillingdon | London | Urban with Major Conurbation
E07000132 | Hinckley and Bosworth | East Midlands | Largely Rural
E07000227 | Horsham | South East | Largely Rural
E09000018 | Hounslow | London | Urban with Major Conurbation
E07000011 | Huntingdonshire | East of England | Mainly Rural
E07000120 | Hyndburn | North West | Urban with City and Town
E07000202 | Ipswich | East of England | Urban with City and Town
E06000046 | Isle of Wight | South East | Mainly Rural
E06000053 | Isles of Scilly | South West | Mainly Rural
E09000019 | Islington | London | Urban with Major Conurbation
E09000020 | Kensington and Chelsea | London | Urban with Major Conurbation
E07000146 | King's Lynn and West Norfolk | East of England | Largely Rural
E06000010 | Kingston upon Hull, City of | Yorkshire and The Humber | Urban with City and Town
E09000021 | Kingston upon Thames | London | Urban with Major Conurbation
E08000034 | Kirklees | Yorkshire and The Humber | Urban with Major Conurbation
E08000011 | Knowsley | North West | Urban with Major Conurbation
E09000022 | Lambeth | London | Urban with Major Conurbation
E07000121 | Lancaster | North West | Urban with Significant Rural
E08000035 | Leeds | Yorkshire and The Humber | Urban with Major Conurbation
E06000016 | Leicester | East Midlands | Urban with City and Town
E07000063 | Lewes | South East | Urban with Significant Rural
E09000023 | Lewisham | London | Urban with Major Conurbation
E07000194 | Lichfield | West Midlands | Urban with Significant Rural
E07000138 | Lincoln | East Midlands | Urban with City and Town
E08000012 | Liverpool | North West | Urban with Major Conurbation
E06000032 | Luton | East of England | Urban with City and Town
E07000110 | Maidstone | South East | Urban with Significant Rural
E07000074 | Maldon | East of England | Mainly Rural
E07000235 | Malvern Hills | West Midlands | Largely Rural
E08000003 | Manchester | North West | Urban with Major Conurbation
E07000174 | Mansfield | East Midlands | Urban with City and Town
E06000035 | Medway | South East | Urban with City and Town
E07000133 | Melton | East Midlands | Mainly Rural
E07000187 | Mendip | South West | Mainly Rural
E09000024 | Merton | London | Urban with Major Conurbation
E07000042 | Mid Devon | South West | Mainly Rural
E07000203 | Mid Suffolk | East of England | Mainly Rural
E07000228 | Mid Sussex | South East | Urban with City and Town
E06000002 | Middlesbrough | North East | Urban with City and Town
E06000042 | Milton Keynes | South East | Urban with City and Town
E07000210 | Mole Valley | South East | Urban with Significant Rural
E07000091 | New Forest | South East | Urban with Significant Rural
E07000175 | Newark and Sherwood | East Midlands | Largely Rural
E08000021 | Newcastle upon Tyne | North East | Urban with Major Conurbation
E07000195 | Newcastle-under-Lyme | West Midlands | Urban with City and Town
E09000025 | Newham | London | Urban with Major Conurbation
E07000043 | North Devon | South West | Largely Rural
E07000038 | North East Derbyshire | East Midlands | Urban with City and Town
E06000012 | North East Lincolnshire | Yorkshire and The Humber | Urban with City and Town
E07000099 | North Hertfordshire | East of England | Urban with Significant Rural
E07000139 | North Kesteven | East Midlands | Mainly Rural
E06000013 | North Lincolnshire | Yorkshire and The Humber | Urban with Significant Rural
E07000147 | North Norfolk | East of England | Mainly Rural
E06000061 | North Northamptonshire | East Midlands | Urban with Significant Rural
E06000024 | North Somerset | South West | Urban with Significant Rural
E08000022 | North Tyneside | North East | Urban with Major Conurbation
E07000218 | North Warwickshire | West Midlands | Mainly Rural
E07000134 | North West Leicestershire | East Midlands | Largely Rural
E06000057 | Northumberland | North East | Largely Rural
E07000148 | Norwich | East of England | Urban with City and Town
E06000018 | Nottingham | East Midlands | Urban with Minor Conurbation
E07000219 | Nuneaton and Bedworth | West Midlands | Urban with City and Town
E07000135 | Oadby and Wigston | East Midlands | Urban with City and Town
E08000004 | Oldham | North West | Urban with Major Conurbation
E07000178 | Oxford | South East | Urban with City and Town
E07000122 | Pendle | North West | Urban with City and Town
E06000031 | Peterborough | East of England | Urban with City and Town
E06000026 | Plymouth | South West | Urban with City and Town
E06000044 | Portsmouth | South East | Urban with City and Town
E07000123 | Preston | North West | Urban with City and Town
E06000038 | Reading | South East | Urban with City and Town
E09000026 | Redbridge | London | Urban with Major Conurbation
E06000003 | Redcar and Cleveland | North East | Urban with Significant Rural
E07000236 | Redditch | West Midlands | Urban with City and Town
E07000211 | Reigate and Banstead | South East | Urban with City and Town
E07000124 | Ribble Valley | North West | Mainly Rural
E09000027 | Richmond upon Thames | London | Urban with Major Conurbation
E07000166 | Richmondshire | Yorkshire and The Humber | Mainly Rural
E08000005 | Rochdale | North West | Urban with Major Conurbation
E07000075 | Rochford | East of England | Urban with City and Town
E07000125 | Rossendale | North West | Urban with City and Town
E07000064 | Rother | South East | Largely Rural
E08000018 | Rotherham | Yorkshire and The Humber | Urban with Minor Conurbation
E07000220 | Rugby | West Midlands | Urban with City and Town
E07000212 | Runnymede | South East | Urban with Major Conurbation
E07000176 | Rushcliffe | East Midlands | Largely Rural
E07000092 | Rushmoor | South East | Urban with City and Town
E06000017 | Rutland | East Midlands | Mainly Rural
E07000167 | Ryedale | Yorkshire and The Humber | Mainly Rural
E08000006 | Salford | North West | Urban with Major Conurbation
E08000028 | Sandwell | West Midlands | Urban with Major Conurbation
E07000168 | Scarborough | Yorkshire and The Humber | Urban with Significant Rural
E07000188 | Sedgemoor | South West | Largely Rural
E08000014 | Sefton | North West | Urban with Major Conurbation
E07000169 | Selby | Yorkshire and The Humber | Mainly Rural
E07000111 | Sevenoaks | South East | Largely Rural
E08000019 | Sheffield | Yorkshire and The Humber | Urban with Minor Conurbation
E06000051 | Shropshire | West Midlands | Largely Rural
E06000039 | Slough | South East | Urban with City and Town
E08000029 | Solihull | West Midlands | Urban with Major Conurbation
E07000246 | Somerset West and Taunton | South West | Largely Rural
E07000012 | South Cambridgeshire | East of England | Largely Rural
E07000039 | South Derbyshire | East Midlands | Urban with Significant Rural
E06000025 | South Gloucestershire | South West | Urban with City and Town
E07000044 | South Hams | South West | Mainly Rural
E07000140 | South Holland | East Midlands | Largely Rural
E07000141 | South Kesteven | East Midlands | Largely Rural
E07000031 | South Lakeland | North West | Mainly Rural
E07000149 | South Norfolk | East of England | Mainly Rural
E07000179 | South Oxfordshire | South East | Mainly Rural
E07000126 | South Ribble | North West | Urban with City and Town
E07000189 | South Somerset | South West | Largely Rural
E07000196 | South Staffordshire | West Midlands | Urban with Significant Rural
E08000023 | South Tyneside | North East | Urban with Major Conurbation
E06000045 | Southampton | South East | Urban with City and Town
E06000033 | Southend-on-Sea | East of England | Urban with City and Town
E09000028 | Southwark | London | Urban with Major Conurbation
E07000213 | Spelthorne | South East | Urban with Major Conurbation
E07000240 | St Albans | East of England | Urban with City and Town
E08000013 | St. Helens | North West | Urban with Major Conurbation
E07000197 | Stafford | West Midlands | Urban with Significant Rural
E07000198 | Staffordshire Moorlands | West Midlands | Largely Rural
E07000243 | Stevenage | East of England | Urban with City and Town
E08000007 | Stockport | North West | Urban with Major Conurbation
E06000004 | Stockton-on-Tees | North East | Urban with City and Town
E06000021 | Stoke-on-Trent | West Midlands | Urban with City and Town
E07000221 | Stratford-on-Avon | West Midlands | Mainly Rural
E07000082 | Stroud | South West | Urban with Significant Rural
E08000024 | Sunderland | North East | Urban with Major Conurbation
E07000214 | Surrey Heath | South East | Urban with City and Town
E09000029 | Sutton | London | Urban with Major Conurbation
E07000113 | Swale | South East | Largely Rural
E06000030 | Swindon | South West | Urban with City and Town
E08000008 | Tameside | North West | Urban with Major Conurbation
E07000199 | Tamworth | West Midlands | Urban with City and Town
E07000215 | Tandridge | South East | Urban with Significant Rural
E07000045 | Teignbridge | South West | Largely Rural
E06000020 | Telford and Wrekin | West Midlands | Urban with City and Town
E07000076 | Tendring | East of England | Largely Rural
E07000093 | Test Valley | South East | Urban with Significant Rural
E07000083 | Tewkesbury | South West | Largely Rural
E07000114 | Thanet | South East | Urban with City and Town
E07000102 | Three Rivers | East of England | Urban with Major Conurbation
E06000034 | Thurrock | East of England | Urban with Major Conurbation
E07000115 | Tonbridge and Malling | South East | Urban with Significant Rural
E06000027 | Torbay | South West | Urban with City and Town
E07000046 | Torridge | South West | Mainly Rural
E09000030 | Tower Hamlets | London | Urban with Major Conurbation
E08000009 | Trafford | North West | Urban with Major Conurbation
E07000116 | Tunbridge Wells | South East | Urban with Significant Rural
E07000077 | Uttlesford | East of England | Mainly Rural
E07000180 | Vale of White Horse | South East | Largely Rural
E08000036 | Wakefield | Yorkshire and The Humber | Urban with City and Town
E08000030 | Walsall | West Midlands | Urban with Major Conurbation
E09000031 | Waltham Forest | London | Urban with Major Conurbation
E09000032 | Wandsworth | London | Urban with Major Conurbation
E06000007 | Warrington | North West | Urban with City and Town
E07000222 | Warwick | West Midlands | Urban with City and Town
E07000103 | Watford | East of England | Urban with Major Conurbation
E07000216 | Waverley | South East | Largely Rural
E07000065 | Wealden | South East | Mainly Rural
E07000241 | Welwyn Hatfield | East of England | Urban with City and Town
E06000037 | West Berkshire | South East | Urban with Significant Rural
E07000047 | West Devon | South West | Mainly Rural
E07000127 | West Lancashire | North West | Urban with Significant Rural
E07000142 | West Lindsey | East Midlands | Mainly Rural
E06000062 | West Northamptonshire | East Midlands | Urban with Significant Rural
E07000181 | West Oxfordshire | South East | Mainly Rural
E07000245 | West Suffolk | East of England | Largely Rural
E09000033 | Westminster | London | Urban with Major Conurbation
E08000010 | Wigan | North West | Urban with Major Conurbation
E06000054 | Wiltshire | South West | Largely Rural
E07000094 | Winchester | South East | Largely Rural
E06000040 | Windsor and Maidenhead | South East | Urban with City and Town
E08000015 | Wirral | North West | Urban with Major Conurbation
E07000217 | Woking | South East | Urban with Major Conurbation
E06000041 | Wokingham | South East | Urban with City and Town
E08000031 | Wolverhampton | West Midlands | Urban with Major Conurbation
E07000237 | Worcester | West Midlands | Urban with City and Town
E07000229 | Worthing | South East | Urban with City and Town
E07000238 | Wychavon | West Midlands | Mainly Rural
E07000128 | Wyre | North West | Largely Rural
E07000239 | Wyre Forest | West Midlands | Urban with Significant Rural
E06000014 | York | Yorkshire and The Humber | Urban with City and Town